## Monthly Meetings
Great Waltham Parish Council - Monthly Meeting Action Tracker
May 2023 - April 2024 inclusive (with carried forward items)
2023-07-23
Meeting Date | Agenda Item Ref. No. | Agenda Item (in bold) with narrative from meeting discussion | Resolution(s), if any | Open/ Closed | X/refer | Action Owner(s) | Last Updated | Date Closed | Update Log
2022-04-25 | 22/1097 | Consider proposed revisions to those policy documents contained in the file circulated prior to the meeting. • Allotment allocation policy • Disciplinary and grievance policy • Financial regulations, • Grievance procedure for employees, • Media relations policy, • Policy statement on the recruitment of ex-offenders • Training policy | 1. The policies were approved 2. Cllr Gilbert to draft approved supplier process. | Closed |  | Cllr Gilbert | 2023-08-22 |  | Carried forward from previous period Process has been drafted. Draft Supplier approval process has been written. Two approvers are currently reviewing the document. - Is this still required ? Both approvers have completed feedback Update at the next F&GP. Pause process.
2022-06-13 | 22/1172 | Discuss replacing the junior goal at Great Waltham recreation ground. Some parents have approached the Parish Council for use of the recreation ground for football training. Consideration to remove the old single goal that needs work. £721 portable single junior goal as a guide. Around £1000 for a pair of goals. | 1. Cllr Martin to get 3 quotes for moveable goals 2. Purchase new sockets and Postcrete. Descale the posts and repaint with appropriate paint. Expenditure of up to £250 approved. | Open |  | Cllr Martin | 2023-06-19 |  | Carried forward from previous period To be discussed t the Recreation Meeting on the 08.08.2022 Item was discussed and options put in to a report for the members of the committee.. Recommendation to refurbish the Junior Goals and insert new spikes in to the pitch. Poste Crete and Sockets to be purchased. Sockets have been purchased and will be dropped off at the Pavilion Handyman is working on the posts. Potential Working Party
2022-06-13 | 22/1174 | Discuss membership of the Emergency Planning Sub Committee (Chair, Vice Chair plus three councillors representing all areas of the Parish) and if it is still required. A report was placed on the website with the agendas. During discussions it was noted that the committee had not met in over 8 years, but an updated Emergency Action Plan would be useful. | 1. An emergency plan to be drawn up by Cllr Steel 2. Dissolve the emergency planning committee. | Open |  | Cllr Gilbert | 2023-06-19 |  | Carried forward from previous period August - No update September No update October - No update No Update Dec- Document has been issued to be kept as live document and discussed at the January 2023 meeting. March - Defer Cllr Steel to discuss a revision with Karen Buttress the Chelmsford City Council Community Safety Lead officer. 17/07/2023 meeting - response received from Karen Buttress - Cllr Gilbert to progress
2022-05-26 | 11 | Inventory at the Pavilion (Action from Pavilion working group) |  | closed |  | Cllr Gilbert | 2022-12-19 | 2023-08-22 | Carried forward from previous period 18/3/2022 (WG): Await purchase/installation of cleaning equipment, items from current Parish Office. 12/04/2022 (WG): Awaiting installation of equipment, furniture etc. 26/05/2022 (WG): Agreed now in position to create inventory. AM to provide list of purchased items to SG to create document in 'house' style. Action to remain open, but transferred to PC monthly action tracker (Clerk to arrange). The Inventory list was provided 30.05.2022. Cllr Gilbert to provide the data in the in-house style A version is held in the Pavilion Hire file . Final Version to be Issues in January 2023.
2022-08-15 | 22/1230 | To consider refurbishment/cleaning the war memorial at Banbury Square prior to the 2022 Remembrance Sunday parade. A briefing note was discussed around the item. Further information supplied in relation to previous enquiries indicates that the lettering cannot be re-cut or painted in. The memorial is usually cleaned every 5 years, but permission is required before any work is undertaken. | 1. The Clerk to contact the War Memorial Trust to understand options and time frames and report back to the Parish Council. | Open | 23/1550 23/1574 23/1575 | Clerk | 2022-12-19 |  | Carried forward from previous period CLERK AWAITING UPDATE Clerk to seek a new plan to cover 2023. WMT have asked for a new set of pictures. Clerk has sent in pictures. Awaiting an update. December.
2022-10-17 | 22/1293 | The Parish Council has all the necessary documents and policies in place to achieve Local Council Award Scheme (LCAS) Foundation level and wishes to proceed to adjudication paying all relevant fees. • £50 registration fee to NALC. • £80 accreditation fee to EALC. | 1. Approved to start the process for LCAS accreditation. | Open |  | Clerk | 2023-05-22 |  | Carried forward from previous period LCAS process started. GWPV is registered with EALC to start the process. £50 Invoice has been received.. Clerk around halfway through paperwork. The Paperwork has been submitted for review.
2023-02-20 | 22/1404 | To agree the wording of the proposed agreement between the Council and Great Waltham Horticultural Society in relation to the hut at the Brook Mead allotment garden (see document circulated prior to the meeting). | 1. The wording of the agreement was approved | Open |  | Cllr Gilbert/Clerk | 2023-07-17 |  | Carried forward from previous period Proposed wording has been discussed with HS and some minor changes proposed. Revised wording currently with HS for agreement.
2023-04-24 | 23/1454 | Proposal for funding of 2 trail cameras for Brookmead allotments. Due to 3 recent break ins. At Brook Mead allotments a padlock was cut off. Other locks have been removed. Small items have been removed such as secateurs. Proposed to install the trail cameras and gather data .Cost of approximately £100. It was noted that we will need CCTV notices and a CCTV Policy. | 1. In principle spend up to £100 on two cameras subject to establishing the legal position and requirements, | Open |  | Cllr Palmer | 2023-06-19 |  | Carried forward from previous period Carried forward for update at July meeting. 17/07/2023 meeting - Camera has been gifted and may avoid need for purchase of new equipment. However, use would still be subject to establishing legal position and requirements.
2023-04-24 | 23/1455 | Discuss the grant request from Ford End Village Hall to support a community event to mark the Kings Coronation at Ford End recreation ground. Ford End Village Hall is putting on a free for all event with attendees asked to bring their own food. The Parish Council has £2,000 in the budget for grants. It is not known who will bring their own gazebo. | 1. Cllr Palmer to contact Great Waltham School to borrow two gazebos. 2. In principle the Parish Council will purchase two gazebos if required. 3. The Parish Council will grant an amount of up to £500. 4. Clerk to contact JCM for an additional grass cut for Ford End recreation ground. | Closed |  | Clerk | 2023-07-14 | 2023-07-17 | Carried forward from previous period Vh / Clerk Invoices received from FEVH - payment without grant amount agreed (£495.87). See July Confirmation of payments (23/1571) 17/07/2023 Meeting - The Coronation grant for the Ford End Village Hall has been paid.
2023-04-24 | 23/1460 | Update on the Ford End Recreation Ground CIF grant towards a perimeter path and if necessary, agree the next steps. The meeting agreed to continue with the plan. The path will be ninety-eight meters from the car park to the picnic benches. The full perimeter is 298 meters. Three quotes have been obtained but the specification created a large difference in price ranging from £42,000 (Caloo), £7,500 (JCM) to £6,000. The work will require four inches excavated from the surface and the installation of side bars and a type 1 base, covered by compacted fine gravel. This will be suitable for ground maintenance and wheelchair access. The footpath can potentially be removed if circumstances change with the plans for the recreation area. | 1. The Parish Council resolves to spend up to £5000 (exclude Vat) of CIF grant subject to agreement from EALC to make a slightly shorter path than originally proposed for the grant. 2. Suspend financial regulations to accept the quotation from CAW Building Services as it has been difficult to get quotes and the funding is time limited. | Open | 23/1548 | Cllr Martin | 2023-07-14 |  | Carried forward from previous period Work contracted to CAW Building Services - to be completed by and August in accordance with requirements of CIF grant.
2023-04-24 | 23/1467 | To agree the Highways & Transport Committee's recommendation that the Council lobbies the relevant authorities/agencies to change the A120 back-up diversionary route from the B1008 to the B1256. Build a report for Highways England to lobby for the change. The B1256 is the old A120 that runs parallel to the current A120. An approach to the Department for Transport was unsuccessful. | 1. Agreed. Lobby Highways England. | Open |  | Cllr Gilbert | 2023-07-14 |  | Carried forward from previous period share with Barnston Parish Council Response from Highways England to request for data relating to road closures during upgrade work on A120 received, but they do not collect any relevant information. Recommended way forward to be discussed at H&TC meeting 24/7/2023.
2023-04-24 | 23/1468 | To agree the Highways & Transport Committee's recommendation that the Council lobbies for measures to ensure the B1008 is not used as a preferred route once the NE by-pass is completed. What will be planned into the Northeast (NE) bypass design for the use of the new bypass? What will be done as part of the NE Bypass to encourage usage? Lobby the Essex County Council Cabinet Member and Cllr Steel. Work to influence the design rather than react after its been built. | 1. Agreed. Lobby the Cabinet Member for Highways and Cllr. Steel at Essex County Council. | Open |  | Cllrs Gilbert & Martin | 2023-07-14 |  | Carried forward from previous period Cllr Steel made contact with Infrastructure Manager 17/07/2023 meeting - awaiting more detailed information on progress of by-pass project.
2023-05-22 | 23/1472 | Election of Chair (for the next 12 months) | 1. Cllr Gilbert was elected. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1473 | Acceptance of Office by the new Chair and signature of paperwork. Cllr Gilbert signed the paperwork. |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1474 | Election of Vice Chair | 1. Cllr Martin was elected. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1475 | Chair’s Welcome: • The Chair addressed the meeting and welcomed Cllr Bradley as a new member of the Council. • Currently the Council is three members short of its full complement – the co-option policy arrangements will be discussed during the meeting. • The Chair requested for all members to actively engage and make a full contribution to the new session of the Council and to assume roles to support its work. • There have been occasions during the period of the last Council when the high standards required by the code of conduct have not been fully achieved. There should be robust but civil and respectful interactions between both members and the public. Should the occasion arise, members should be able to disagree without being disagreeable. Chair: Gilbert Cllrs: Bradley, Martin, Jackson, McDevitt, Palmer, Jenkins and Steel |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1476 | Apologies None required. |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1477 | Declarations of interests (existence and nature) with regard to items on the agenda and any request for dispensation. Cllr Martin – Planning item 23/00740/FUL is directly in front of the member’s house |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1478 | Public Participation session for any items regardless of its existence on the agenda One member of the public (the applicant) attended to discuss planning item 23/00740/FUL for an access road to Lavender Farm. The track is currently only used in the summer months and has a dropped kerb to access the B1008. Currently farm machinery often uses Pleshey Road and Woods Road for access. The applicant wants direct access on to the main road so that the farm track can be used all year round. The track is next to the public footpath. |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1479 | To review the terms of reference for committees and appointment of Committees, as follows: • Finance and General Purposes Committee (Chair, Vice Chair plus four councillors). Members – Cllr Jackson, Cllr Martin, Cllr Gilbert, Cllr Bradley and 2 vacancies • Recreation Committee (Chair, Vice Chair plus five councillors) Members – Cllr Gilbert, Cllr Martin, Cllr Jenkins, Cllr Palmer, Cllr Jackson, Cllr Bradley and 1 vacancy. • Staffing Committee (3 councillors). Members - Cllr Jenkins, Cllr Palmer and Cllr Steel. • Highways and Transport Committee (Chair, Vice Chair plus 3 Councillors & Parish Council Transport Representative). Members – Cllr Gilbert, Cllr Martin, Cllr Palmer, Cllr McDevitt, Cllr Jenkins and Cllr Bradley. • Planning Committee (All members of the Council are represented on this Committee and are called to full meetings of the Council which are dedicated to planning). |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1480 | Review of arrangements, including any charters and agency agreements, with other local authorities and review of contributions made to expenditure incurred by other local authorities | 1. There has been no expenditure incurred. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1481 | Appointment of Essex Association of Local Councils representatives (Chair, Clerk plus one Councillor). | 1. Cllr Gilbert, Cllr Martin and the Clerk were appointed. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1482 | Appointment of representatives to the Chelmsford City Council Planning Forum (one Councillor) | 1. Cllr McDevitt was appointed | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1483 | Appointment of representative on Great Waltham Village Hall Committee (one Councillor). | 1. Cllr Palmer was appointed | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1484 | Appointment of a representative on Great Waltham Community Network (one Councillor). | 1. Defer to the next meeting. | Open
2023-05-22 | 23/1485 | Appointment of representatives for Great Waltham Parish Jubilee Twinning Association (Chair plus one other nomination). | 1. Cllr Steel was appointed. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1486 | Appointment of representative to the Alms House Charity | 1. Mr A. Micklem was appointed. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1487 | Appointment of Allotment Inspector | 1. Cllr Palmer was appointed. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1488 | Appointment of Routine Playground Inspector | 1. Defer to the next Recreation Committee meeting. | Closed | RC 12/07/2023 (10) |  |  | 2023-07-23 | Inspection mechanism agreed at Recreation Committee meeting 12/07/2023(10)
2023-05-22 | 23/1489 | Review and adoption of the Standing Orders. | 1. The Standing Orders were adopted. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1490 | Review and adoption of the Financial Regulations. | 1. The Financial Regulations were adopted. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1491 | Review of arrangements (including legal agreements) with other local authorities, not-for-profit bodies, and businesses. • Great Waltham Village Hall – Hire of Blue Room until October 2023. • Great Waltham Village Hall – Hire of Village Hall Parking Spaces on an annual basis. • Chelmer Housing Partnership – Access and use of free parking spaces in Blossom Way. • Allotments in Great Waltham – Hire agreement (currently a five-year term which commenced in September 2022). • Great Waltham Recreation Ground (Part of) – Donation. Lease period continues until August 2038. • Howe Street Recreation ground – Hire. |  | Closed |  |  |  | 2023-05-22 | The meeting noted these arrangements.
2023-05-22 | 23/1492 | Review of representation on or work with external bodies and arrangements for reporting back. |  | Closed |  |  |  | 2023-05-22 | The meeting noted Cllr Jackson continues to sit on CCC’s Governance Committee.
2023-05-22 | 23/1493 | Consider if the Council has become eligible to exercise the general power of competence. • Elected Councillors – The elected Councillors must equal or exceed (3/4) = 8 • Clerk – Must hold the CilCa qualification or an equivalent. | 1. The Parish Council meets the criteria to exercise the general power of competence. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1494 | Review of inventory of land and other assets including buildings and office equipment. • Add the beacon – currently located at the churchyard, estimated value £400. • Defibrillators – add the Littley Green and North End units. • The F&GP Committee will consider the format of the asset register at a future meeting. | 1. Items to be added/deleted throughout the year, as necessary. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1495 | Confirmation of arrangements for insurance cover in respect of all insurable risks. | 1. The renewal of insurance via BHIB was confirmed. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1496 | Review of the Council’s and/or staff subscriptions to other bodies. • Essex Association of Local Councils (E.A.L.C.) • National Association of Local Councils (N.A.L.C.) • Rural Community Council of Essex (R.C.C.E.) • Campaign to Protect Rural England (C.P.R.E.) | 1. Continue to circulate to members the information from each body. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1497 | Review of the Council’s complaints procedure. | 1. This was approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1498 | Review of the Council’s policies, procedures, and practices in respect of its obligations under freedom of information and data protection legislation. | 1. The policies were approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1499 | Review of the Council’s policy for dealing with the press/media. | 1. The policies were approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1500 | Review of the Council’s employment policies and procedures. | 1. The policies were approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1501 | Review of the Council’s expenditure incurred under s.137 of the Local Government Act 1972 or the general power of competence. |  | Closed |  |  |  | 2023-05-22 | It was noted there was £0 expenditure.
2023-05-22 | 23/1502 | Determining the time and place of ordinary meetings of the Council up to and including the next annual meeting of the Council. | 1. Revise the schedule with four meetings in Ford End. 2. The rest of the meetings will be held at the Pavilion in Great Waltham. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1503 | Report by County Councillor - Cllr Mike Steel. A full report is available on the website |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1504 | Report by Chelmsford City Councillor – Cllr Mike Steel. The full report is available on the website. |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1505 | Note the minutes of the Highways and Transport Committee meeting held on 17th April 2023. | 1. The minutes were noted. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1506 | Confirmation of the minutes of the monthly meeting held on 24th April 2023. | 1. The minutes were confirmed. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1507 | Local Planning Authority Decisions. |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1508 | Planning Applications 1. Reference: 23/00740/FUL Address: Land Between Little Dene And Bridge Cottage Main Road Little Waltham (sic) Chelmsford. Description of works: Surfacing of an Agricultural Access Track. • See item 23/1478 above – the applicant provided details of rationale and extent of the proposed works. • The meeting noted that two residents had raised concerns over potential slow moving agricultural vehicles joining the main road and of potential air pollution in the area. • The meeting identified the benefit of the reduction of farm vehicle traffic on Pleshey Road and Woods Road. 2. Reference: 23/00659/FUL Address: Recreation Ground South Street Great Waltham Chelmsford Description of works: Siting of a storage container adjacent to the pavilion • Cllr Steel withdrew from the item and declared a conflict of interest. 3. Reference: 23/00576/FUL Address: Garnetts Farm Mashbury Road Great Waltham Chelmsford Description of works: Proposed single storey detached garden building. | 1. Reference: 23/00740/FUL - The Parish Council supports this application. 2. Reference: 23/00659/FUL - The Parish Council cannot comment on its own application as it would be regarded as a conflict of interest. 3. Reference: 23/00576/FUL - No objection. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1509 | Finance Report |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1510 | Approval to purchase the Handyman additional Ryobi One batteries as he only has a 1.5 AH and 5 AH restricting use of non-fossil fuel driven equipment. (Lawnmower, hedge cutter, bush cutter) at £51.99 (includes VAT) for two. – The Clerk. | 1. This was approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1511 | Approval to purchase a multi charger for the Handyman in the Ryobi One range at £89.18 (includes VAT).- The Clerk. | 1. This was approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1512 | Approval to purchase a strimmer for the handyman at a cost of £74.49 (includes VAT) – The Clerk. | 1. This was approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1513 | Approval to purchase a replacement hedge cutter as the Stihl has failed. A Ryobi battery unit is £109.95 (incl vat). | 1. This was approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1514 | Confirmation of payments: |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1515 | Review and approval of the financial standing order on the bank account. £316.09 To Great Waltham Village Hall – Monthly for the use of the Blue Room - until October 2023. £250.00 To Great Waltham Charities – Annual donation for the use of the land at the Great Waltham Recreation Ground. | 1. This was approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1516 | Review and approval of the financial direct debits on the bank account. £ Variable SSE – Utilities – Pavilion. £ Variable Wave – Utilities – Allotment and Pavilion £35.00 Information Commissioner’s office (I.C.O.) | 1. This was approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1517 | Discuss and approve setting up standing orders for staff salaries (Clerk and Handyman). | 1. This was approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1518 | Nominate additional signatories to the bank account (Currently three). | 1. Cllr Gilbert and Cllr Martin to be added. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1519 | Monthly Bank Reconciliation | 1. The chair approved this as there is not a chair of the F&GP until its first meeting is held. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1520 | To agree actions and activities in relation to co-option of councillors for the new council. | 1. Start the process to identify and select new councillors as laid out in the Councillor Co-option Policy document. | Closed |  | Cllr Gilbert | 2023-07-14 | 2023-07-17 | Process commenced and completed. Update at July monthly meeting. 17/07/2023 meering - The Co-option process for councillors has concluded with three new councillors elected today.
2023-05-22 | 23/1521 | Review new information in relation to the previous resolution to purchase a whiteboard for the pavilion. The meeting noted the cost (£376) for a projector friendly whiteboard. The advantages for this solution would be its potentially attractiveness for hirers and for use by the Council at its meetings. This item went to a vote to purchase the projector friendly version. The votes cast being equal, the Chair’s deciding vote carried the motion. | 1. The improved whiteboard to be purchased | Closed |  | Clerk/Cllr Martin | 2023-08-22 | 2023-08-22 | Whiteboard ordered. To be installed on delivery. Whiteboard installed July 2023.
2023-05-22 | 23/1522 | To agree allocation of due policy document reviews (see review schedule circulated with the agenda of the meeting. A number of policies due for review were considered and agreed earlier in the meeting. A number of documents relating to the use of the Pavilion remained to be allocated. | 1. Pavilion documentation review allocated to Cllr Gilbert and Cllr Martin | Open |  | Cllrs Gilbert & Martin | 2023-07-17 |  | Updated wordings agreed at June monthly meeting (23/1555). Fire risk assessment remains outstanding.
2023-05-22 | 23/1523 | To agree that the Council seeks to secure a loan to fund one-half of the costs to install an average speed camera system on the B1008 through Ford End village (see briefing note circulates with the agenda of the meeting). [See minutes on website for full narrative and record of voting]. • A named vote on the motion was requested and agreed. • The motion was: To agree that the Council seeks to secure a loan to fund one-half of the costs to install an average speed camera system on the B1008 through Ford End village. | 1. The motion was carried. | Open |  | Cllr Gilbert/Clerk | 2023-07-17 |  | Confirmation received from ECC that consideration will be given to match funding when GWPC confirms it has available its 50%. Discussions with EALC to understand process to access PWLB funding. Application to PWLB in progress. 17/07/2023 meeting - Application for PWLB loan implies need for consultation. However, precise position to be established (given PC resolution to raise a loan alreday made).
2023-05-22 | 23/1524 | Update on the Action Tracker – all. Ford End Recreation Ground CIF grant. A firm understanding of the time available to utilise the grant has been sought since October. The matter should be resolved imminently and the matter will be discussed at the next scheduled Recreation Committee meeting (31/7/2023). |  | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1525 | To agree use of Blossom Way car parking spaces adjacent to Scout hut, for Scout breakfast 8am to 11am Sunday 11th June, subject to CHP having no objections – Cllr Steel. Cllr Steel declared a nonpecuniary interest and withdrew from the agenda item. | 1. This was approved. | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1526 | To consider grant request from Waltham’s Scout Group for work for upgraded electrics whilst HQ ceiling is not in position. • Cllr Steel declared a nonpecuniary interest and withdrew from the agenda item. • The meeting noted the need to quickly address the electrics upgrade during the short window available. • The application was considered and it was proposed and seconded that based on the quotes indicated a grant of £1,750 should be offered. | 1. A grant of £1,750 to the Walthams Scout Group was approved | Closed |  |  |  | 2023-05-22
2023-05-22 | 23/1527 | Discuss and approve any items for the “Parish Council News” section of the Parish News. • Co-option of Councillors • Precis of the minutes • Defibs • HS multiplay |  | Closed |  |  |  | 2023-05-22
2023-06-19 | 23/1528 | Chair’s Welcome: Chair: Gilbert Cllrs: Steel, Jackson, McDevitt, Bradley, Jenkins, and Martin |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1529 | Apologies Cllr Palmer |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1530 | Declarations of interests (existence and nature) with regard to items on the agenda and any request for dispensation. Cllr Jackson – Allotments Cllr Bradley – Planning – Family member. 23/00784/FUL |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1531 | Public Participation session for any items regardless of its existence on the agenda 4 Members of the public. • Ref. No: 23/00784/FUL - Applicant to discuss the planning. Generational house. Front dormers. • Planning item 23/00824/FUL. The natural burial ground has been open 6 years. There are 5 members of staff. Grave digging has now been bought inhouse. All the equipment to support this needs to be stored securely and safely. |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1532 | Report by County Councillor - Cllr Mike Steel. The full report is online in the agenda section of the website |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1533 | Report by Chelmsford City Councillor – Cllr Mike Steel. The full report will be online in the agenda section of the website. |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1534 | Confirm the minutes of the Extraordinary meeting held on 1st June 2023. | 1. The Minutes were confirmed. | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1535 | Confirm the minutes of the Annual General Meeting held on 22nd May 2023. | 1. The Minutes were confirmed. | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1536 | Note the minutes of the Recreation Committee meeting held on 31st May 2023. | 1. The minutes were noted. | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1537 | Local Planning Authority Decisions. |  | Closed |  |  |  | 2023-06-19 | The decisions were noted.
2023-06-19 | 23/1538 | Planning Applications 1. Reference: 23/00808/FUL Address: Burmead Main Road Great Waltham Chelmsford Description of works: Loft conversion and single storey rear extension with rear dormer. Creating additional bedrooms on first floor 2. Ref. No: 23/00784/FUL 60 Cherry Garden Road Great Waltham Chelmsford Essex CM3 1DJ. Two storey side extension. Front porch extension. Loft conversion with rear dormer. Addition of 2no. front dormer windows at first floor level and 6no. front and rear roof lights at second-floor level. Associated landscaping. Extensive upgrade. One neighbour has objected. 3, Reference: 23/00824/FUL Address: Old Park Meadow Natural Burial Ground Coppice Lane High Easter Dunmow. Description of works: Proposed workshop/store and office building with associated hardstanding and parking. Initial impression is that it’s a large building – Barn like. Suggestion that the proposed building should be screened from The Butchers Arms. 4. Reference: 23/00933/FUL Address: Lyndhurst Ringtail Green Great Waltham Chelmsford Description of works: Demolition of the existing oil tank outbuilding, side entrance porch, and rear lean-to. Reinstatement of the original front entrance door and first floor sash window, replacing the side porch entrance with a single storey side addition. Single storey side addition to replace the oil tank structure and a two-storey rear addition in place of the rear lean-to. | 1. Reference: 23/00808/FUL - No objections. 2. Ref. No: 23/00784/FUL - No objections. 3, Reference: 23/00824/FUL - The Parish Council supports this application as this supports growth in the local business community. 4. Reference: 23/00933/FUL - No objections. | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1539 | Finance Report Current Account; £12,982.28 Reserve Account; £56,745.33 • £10,000 Ford End Speed Cameras • £5,000 Ford End Path • £700 Allotment deposits • £32,500 Capital Works • £8,545.33 General Reserve Total £69,727.61 |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1540 | Confirmation of payments |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1541 | Monthly Bank Reconciliation. | 1. The account balanced with no variance | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1542 | To receive an update on co-option of councillors for the new council. The 3 vacancies have been advertised in social media and will be in the July edition of the parish news. Early July for the process to be run |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1543 | Update on the Action Tracker – all. The tracker will be updated and posted online |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1544 | Update on the Great Waltham storage container planning application and agree next steps Cllr Steel declared an interest and took no part in any discussion. Planning permission has been granted by Chelmsford City Council Planning. The cost of the container (delivered to site) is £2,740 (plus VAT). Planned for week commencing 17th July 2023. | 1. Clerk to arrange purchase order and payment for the container | Closed |  | Clerk | 2023-07-14 | 22./08/2023 | Purchase process is progressing. Container purchased and installed in July 2023.
2023-06-19 | 23/1545 | Update on the EALC CIF grant extension and next steps. The path around Ford End recreation ground. At this stage with current funding available the path will run from the car parking to the picnic bench area running within 1m of the perimeter fence. The path will be built before the end of august to keep within the EALC funding requirements. |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1546 | Discuss and support the Recreation Committee’s proposal to form a working group to develop the plans and strategies for the Great Waltham play area project. The working group will be created from the members of the recreation committee and interested members of the parish that have appropriate skills to support this project. |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1547 | Discuss and support the Recreation Committee’s proposal to spend some of this year’s income from the Pavilion for decorating materials and include a budget for Pavilion maintenance in future budget plans. £811.88 income from the Pavilion 2022-2023 (renting to outside organisations started Sept 22). | 1. Agreed to spend up to £150 on paint for internal Pavilion maintenance. 2. Cllr Martin to arrange purchase and work party. | Closed |  | Cllr Martin | 2023-07-17 |  | Re-painting has been completed.
2023-06-19 | 23/1548 | Discuss and support the Recreation Committee’s proposal to make an ECC Locality Fund application to provide a seat at Ford End Recreation Ground as part of the improvement project. Cllr Steel declared an interest. It was noted that it would cost £638.79 for a recycled bench . | 1. Cllr Martin to contact Essex County Council Member Councillor Steel with an application. | Closed | 23/1460 | Cllr Martin | 2023-07-14 | 2023-07-17 | Application for funding successful. Order for bench in progress. Installation will be by CAW Building Services as part of FE RG improvement works (23/1460). 17/07/2023 meeting - A new Locality funding request from Essex County Council was approved and a new bench has been ordered for Ford End.
2023-06-19 | 23/1549 | Update on the Howe Street Multi Play replacement. This was installed on over several Saturdays. The unit has been fully installed and will be inspected prior to use by the public. |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1550 | To select a contractor to complete the works to apply enamel paint to the inscriptions on the war memorial at Banbury Square Quotes requested from Art in Stone, Bradford Memorials and Universal Stone. | 1. Defer until next month. 2. Clerk to get examples of the work undertaken. | Open | 22/1230 23/1574 23/1575 | Clerk | 2023-07-14 |  | Update at July monthly meeting. See notes on 23/1574.
2023-06-19 | 23/1550 (sic) | To consider the mechanism(s) to consult/update parishioners on proposed works on the war memorial at Banbury Square. | 1. Defer until next month. | Open | 22/1230 23/1574 23/1575 | Cllr Gilbert |  |  | See notes on 23/1575.
2023-06-19 | 23/1551 | To agree to send a representative of the Council to the public consultation and exhibition on the proposals for an integrated retirement community in Little Waltham. Development brochure was put through every door in the parish. | 1. Cllr Gilbert will attend the open session and report back to the Parish Council. | Open |  | Cllr Gilbert | 2023-07-14 |  | Report from public consultation and exhibition circulated to members. Opus are willing to present their plans at a future GWPC meeting. 17/07/2023 - consider invitation at September meeting subject to known developments of project.
2023-06-19 | 23/1552 | To agree the purchase of computer software module(s) to allow the Council to introduce and operate a paperless, cloud-based operating system for its administrative functions (see briefing paper circulated with the agenda). The Council asked for clarification on two points: Is there a cooling off period? Is there a 25 year back up system for playground inspections? | 1. Subject to clarification of the two points above the Clerk to place the order for the software. | Open |  | Clerk | 2023-07-14 |  | Answers to questions: there is a 14-day cooling off period; data backed up and retained indefinitely. Purchase completed and training on modules acquired has commenced. 17/07/2023 meeting - software acquired, training has commenced.
2023-06-19 | 23/1553 | To agree that only new plot holders to an allotment site are required to pay a £50 deposit to hire a plot. | 1. The £50 deposit is to be paid once even if an allotment holder moves sites or takes on additional plots | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1554 | To agree the scope of and remuneration in relation to an Allotment Maintenance Contract for areas of Council responsibility at the Brook Mead and Bury Lane allotment sites (see draft document circulated with the agenda). | 1. This was agreed. 2. Advertise in the Parish News and on social media. | Closed |  | Cllr Gilbert | 2023-07-14 | 2023-08-22 | Advertisement place in Parish News. Will be circulated on social media when PN edition published. Nick De'Ath appointed for 2023.
| 23/1555 | To agree revised wordings for the Pavilion documents circulated with the agenda. | 1. The documents were agreed. | Closed |  |  |  | 2023-06-19
| 23/1556 | Report from the defibrillator project working group and confirmation of the training arrangements. The defibrillator training has been booked at Ford End village hall for up to 50 people for 2 hours. A weekday evening is the best solution from the training provider . The defibrillator working group will recommend a budget for Broads Green in the October for the 2024 budget and installation. |  | Closed |  |  |  | 2023-06-19
2023-06-19 | 23/1557 | To consider how to progress the setting up of a community orchard on the Bury Lane allotment site. | 1. Cllr Jackson to discuss with the landowner | Open |  | Cllr Jackson | 2023-07-14 |  | Initial contact made. Further discussion to take place.
2023-06-19 | 23/1558 | Discuss Gigaclear offer for meeting. | 1. Clerk to arrange a meeting with Giga Clear at the next monthly meeting. | Open |  | Clerk | 2023-07-14 |  | Update at July monthly meeting. 17/07/2023 - invitation to future meeting to be arranged.
2023-06-19 | 23/1558 (sic) | Discuss and approve any items for the “Parish Council News” section of the Parish News. • Precis of the minutes |  | Closed |  |  | 2023-06-19
2023-07-17 | 23/1559 | Chair’s Welcome: Chair: Gilbert Cllrs: Martin, Jackson, McDevitt, Bradley, Steel, Jenkins and Palmer |  | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1560 | To consider and agree recommendations for co-opting new members to the Council. The Chair reported that in accordance with the Council’s co-option policy applicants had been interviewed and selections agreed. It was recommended that the Council accepts Oliver Micklem, Christine Page and Roger Stephenson as new councillors. This would bring the Council up to its full complement of eleven members. | 1. The recommendation was agreed and Cllrs Micklem, Page and Stephenson were elected and welcomed to the Council. | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1561 | Apologies None were given. |  | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1562 | Declarations of interests (existence and nature) with regard to items on the agenda and any request for dispensation. Planning (item 23/1569) Cherry Trees, Chelmsford Road – Cllr Micklem as a near neighbour. Allotment items – Cllrs Jackson, Bradley and Palmer – Allotment leasers. |  | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1563 | Public Participation session for any items regardless of its existence on the agenda There were no members of the public at the meeting. |  | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1564 | Report by County Councillor - Cllr Mike Steel. The full report will be online in the agenda section of the website. |  | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1565 | Report by Chelmsford City Councillor – Cllr Mike Steel. The full report will be online in the agenda section of the website. |  | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1566 | Confirm the minutes of the ordinary meeting 19th June 2023. | 1. These were confirmed | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1567 | Note the minutes of the Recreation Committee held on 12th July. Under item 5. The first resolution should read: ‘New plot holders will uncover their plots and the Council will store the material’. | 1. Subject to the above change the minutes were noted. | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1568 | Local Planning Authority Decisions. |  | Closed |  |  |  | 2023-07-17 | The decisions were noted.
2023-07-17 | 23/1569 | Planning Applications 1. Reference: 23/00838/FUL Address: Littley Park, The Dairy Littley Park Lane Great Waltham Chelmsford Description of works: Change of use of remaining sections of historic agricultural range to enlarge existing single dwelling. Remodelling of courtyard range and altering form of roof. Single storey extension within courtyard to create entrance vestibule. Associated alterations and operations. Minor landscaping works. 2. Reference: 23/00839/LBC Address: Littley Park, The Dairy Littley Park Lane Great Waltham Chelmsford Description of works: Change of use of remaining sections of historic agricultural range to enlarge existing single dwelling. Remodelling of courtyard range and altering form of roof. Single storey extension within courtyard to create entrance vestibule. Associated alterations and operations. Minor landscaping works. 3. Reference: 23/00602/FUL Address: Great Waltham C Of E School South Street Great Waltham Chelmsford Description of works: Erection of free-standing timber canopy to early years play area. 4. Reference: 23/00898/FUL Address: Greenways Church Lane Great Waltham Chelmsford Description of works: Replacement Dwelling. It was noted that the Council has awarded the applicant’s company the contract for work to be carried out on the Ford End Recreation Ground path. This is a substantially similar application to one made previously. The Parish Council did not object to the previous application. 5. Reference: 23/01050/FUL Address: Cherry Trees Chelmsford Road Great Waltham Chelmsford Description of works: First floor side extension, single storey rear extension. Cllr Micklem declared an interest as the neighbour and took no part in the discussion. This is a second application following a previously refused application. The Council objected to the previous application. The new application addresses the Council’s original concens. | 1. Reference: 23/00838/FUL - No objections. 2. Reference: 23/00839/LBC - No objections. 3. Reference: 23/00602/FUL - Support the application. 4. Reference: 23/00898/FUL - No objections. 5. Reference: 23/01050/FUL - No objections. | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1570 | Finance Report. Current Account; £6,273.78 Reserve Account; £34,845.25 • £10,000 Ford End Speed Cameras • £5,000 Ford End Path • £700 Allotment deposits • £12,101.66 Capital Works • £7,043.59 General Reserve Total £41,119.03 The Finance Report was noted. |  | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1571 | Confirmation of payments |  | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1572 | Monthly Bank Reconciliation | 1. There is zero difference. This was approved. | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1573 | Update on the Action Tracker The full tracker was reviewed and these items were closed as completed: • 23/1455 – The Coronation grant for the Ford End Village Hall has been paid. • 23/1520 – The Co-option process for councillors has concluded with three new councillors elected today. • 23/1548 – A new Locality funding request from Essex County Council was approved and a new bench has been ordered for Ford End. |  | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1574 | To select a contractor to complete works to apply enamel paint the inscriptions on the war memorial at Banbury Square (deferred from previous meeting) Members remained wary of approving works without further examples from those carried out elsewhere. Members are mindful of not wishing to authorise changes which could prove harmful in the medium- or long-term. | 1. Defer this item to next month to allow for additional details to be sought from the War Memorials Trust and Universal Stone – one of the possible contractors. | Open | 22/1230 23/1550 23/1575 | Cllr Gilbert | 2023-07-17
2023-07-17 | 23/1575 | To consider the mechanism(s) to consult/update parishioners on proposed works on the war memorial at Banbury Square (deferred from previous meeting). | 1. Defer this item to next month to allow for additional details to be sought from the War Memorials Trust and Universal Stone – one of the possible contractors. | Open | 22/1230 23/1550 23/1574 | Cllr Gilbert | 2023-07-17
2023-07-17 | 23/1576 | To discuss and agree the Council’s response to National Grid’s The Great Grid Update Norwich to Tilbury consultation. • The North West and South West of Chelmsford Parishes Group is working to formulate a common text objecting to the latest proposals. The preference remains for an offshore route/grid. • National Grid’s position is that all previous objections have been considered in its latest proposals and the route has been changed to minimise the issues raised. • Lattice pylons are unattractive – potentially the T pylons are the least unattractive. • Underground installation is a very disruptive, demanding a 100m wide trench. The trench system requires a large building (converter) at either end of each section of trench. The ground will take 10 years to recover after the trench works completed. • The meeting discussed a request from a resident to purchase printed flyers and banners drawing attention to the proposals. The Council decided against purchasing banners at this stage, not least due to complications in securing various permissions in placing them on private land. | 1. Cllr McDevitt will draft the Council’s response to the latest consultation taking into account further input from the North West and South West of Chelmsford Parishes Group. The draft will be shared with members for comment. 2. The Council agreed the aspiration to put a leaflet through every door in the parish. Cllr. Palmer to make social media posts requesting volunteers for delivering the flyers, provided they can be sourced. 3. Cllr. Steel to identify whether the c.1,000 leaflets required to cover the parish can be sourced at no cost. | Open |  | 1. Cllr McDevitt 2. Cllr Palmer 3. Cllr Steel | 2023-07-17
2023-07-17 | 23/1577 | To confirm that the Council will lead on November Remembrance Sunday events and form a committee including the British Legion, church, and other local organisations. | 1. Confirmed. | Open |  | Cllr Gilbert/Clerk | 2023-07-17
2023-07-17 | 23/1578 | To agree the Council’s representatives at the Remembrance Sunday events at Great Waltham and Ford End. | 1. Cllrs Martin and Stephenson to agree on the Ford End representative. 2. Cllr Gilbert is the representative at Great Waltham. | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1579 | To authorise the purchase of two wreaths for the Remembrance Sunday services. | 1. Approval up to £50 via the British Legion. | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1580 | To appoint two additional members to fill the vacancies on the Finance & General Purposes Committee. | 1. Cllrs Micklem and Stephenson were elected to the roles, | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1581 | To appoint one additional member to fill the vacancy on the Recreation Committee. | 1. Cllr Page was elected to the committee. | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1582 | Discuss the Findings of the Internal Auditors report. No major issues were raised. Clean audit for 2022-2023 |  | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1583 | Discuss the potential parking options for the Great Waltham School. Cllr. Steel reported on his conversations with Essex Highways Sustainable Travel Planning Officer to whom he has explained the issues in detail. These have included the availability of the public car parking spaces in Blossom Way which are currently underutilised and could be considered by school staff or parents for parking (either during the day or when dropping off pupils). | 1. Cllr. Steel to make contact with the School to ensure there is an awareness of the availability of the Blossom Way facility. | Open |  | Cllr Steel | 2023-07-17
2023-07-17 | 23/1584 | Discuss the costs for the continuing improvements to the allotment areas and authorise the expenditure for both materials and labour if required. Four or five rolls of covering material are still required for Bury Lane. Brook Mead can be covered with the existing coverings that have been reclaimed. Ebay would offer the best commercial purchase price. | 1. A total expenditure amount of £162 was approved. | Closed |  |  |  | 2023-07-17
2023-07-17 | 23/1585 | Discuss options to enable the cleaning of benches and other equipment for the handyman. The three options in the briefing paper were discussed: a manual hand pump power washer, or a battery driven pump power washer, or a petrol-powered power washer. The flexibility and power available from the battery driven power washer was selected as the best balance between power and portability. | 1. The Clerk to purchase a Ryobi battery driven power washer. | Open |  | Clerk | 2023-07-17
2023-07-17 | 23/1586 | Discuss and approve any items for the “Parish Council News” section of the Parish News. • Pylon notice. • Precis of the minutes. • Allotment open day. • Public transport update. • Play in the Park update . |  | Closed |  |  |  | 2023-07-17

## Recreation Committee
Great Waltham Parish Council - Recreation Committee Meetings Action Tracker
May 2023 - April 2024 inclusive (with carried forward items)
2023-07-19
Meeting Date | Agenda Item Ref. No. | Agenda Item (in bold) with narrative from meeting discussion | Resolution(s), if any | Open/ Closed | X/refer | Action Owner(s) | Last Updated | Date Closed | Update Log
2022-11-07 | 8 | Update on discussions regarding the Horticultural Society Hut at Brook Mead and any implications identified for GWPC. The Chairman of the Great Waltham Horticultural Society (GWHS) has confirmed that they hold insurance and own the building. The provision of tool storage space for allotment users was discussed and agreed that it was not within the Council’s remit to offer space in the hut. | 1. Cllr Gilbert to review the allotment hire conditions. | Open |  | Clerk | 2023-09-04 |  | Carried forward from previous period Clerk to confirm letter has been sent. Face two face meeting to be arranged. A response was recived with additional chnages. Version 2 send after the Face 2 Face meeting. Additional correspondance has been received. - September 2023
2022-11-07 | 9 | Update on the status of the overgrown trees at Brook Mead allotments. It is noted that the trees are under tree protection orders (TPO). The landowner is waiting on Chelmsford City Council tree officer to visit the site. The Parish Council is concerned that the tree is causing problems for the allotments. There is a concern that the trees may cause damage to the allotments and GWHS building if any branches fall. | 1. Allotment Inspector to continue to monitor the situation. | Open |  | Cllr Palmer | 2023-09-04 |  | Carried forward from previous period Barrack Lane tree has been trimmed (TPO) around the CHP . Cllr Palmer to make enquires of the Tree Officer. Plans have been submitted.
2022-11-07 | 14 | Discuss recent vandalism to the perimeter fence at Ford End recreation ground and consider the quote to add further security fencing. A quote to replace 10m of security fence to close this gap £1870 (+vat) had been obtained. There was a discussion about the ongoing trespass through to the fields and the need to keep the Recreation Ground play area secure. | 1. The committee to recommend to the Parish Council to plan to repair the fence at Ford End recreation ground. | Open |  | All | 2023-05-01 |  | Carried forward from previous period Potential task to be done depending on the rest of the project
2022-11-07 | 16 | Review responses to the consultation invitation to identify a suitable Multi-play replacement for the Howe Street recreation ground and agree next steps. It has previously been agreed that the wooden play equipment needs replacement as it has aged. The consultation was contained within the September edition of the Parish News, however there were no responses. The Local Parish Councilor proposes to replace the existing unit with a similar multi play for 3–12-year-olds. The budget is in the region of £15,000. | 1. Cllr Jackson, Cllr Palmer, Cllr Huggins and Cllr Martin to make a decision on the appropriate piece of equipment. The information should be shared with residents in an article for Parish News, post through letter boxes , the school’s newsletter and social media. | Closed |  | Cllrs Jackson, Palmer, Huggins and Martin | 2023-05-01 | 04.09.2023 | Carried forward from previous period On the agenda Due to install June 3/4 Unit installed. Close item.
2022-11-07 | 18 | Pavilion update including bookings and feedback and outstanding work to include storage container options update. Door blinds and obscuration film had been considered but it was suggested that a removable fire proof curtain is a better option for the door and side panels at night to give some hirers some privacy. In the last few weeks the exterior of the building has been re pointed by Cllrs Martin and Huggins. A second quote on the shutters has been sought and found to be more competitive. It is anticipated that there will be a 3-week manufacturing time for the units after the order has been placed. It was also discussed that there is an option to pull forward the purchase and installation of the storage container into this financial year as some unexpected CIL income has be remitted to the Parish Council. An 8 foot ex shipping container would be within budget. | 1. The committee recommends the purchase of a single use shipping container for placement beside the pavilion. | closed |  | All | 2023-05-01 | 04.09.2023 | Carried forward from previous period Pre Application advice has be sought. Application has been made. Update June 13. Installed July 21 Item complete. Close item.
|  | Junior Goals - to be refurbished |  | Open | 31/05/2023 (28) |  | 2023-09-04 |  | Carried forward from previous period We have paint , got the sockets. Attempted to get 3 quotes. Awaiting responses.
|  | Fe Goals to be filled |  | closed |  |  | 04/09.2023 | 04.09.2023 | Carried forward from previous period Soil is at ford end. Working party have completed the action and used all the soil.. Close Item.
2023-05-31 | 1 | Elect a Chair. Cllr Martin was elected. |  | Closed |  |  |  | 2023-05-31
2023-05-31 | 2 | Chair’s Welcome Chair: Martin Cllrs: Jackson, Gilbert, Palmer, Jenkins, Bradley |  | Closed |  |  |  | 2023-05-31
2023-05-31 | 3 | Apologies for Absence None required. |  | Closed |  |  |  | 2023-05-31
2023-05-31 | 4 | Declarations of interests (existence and nature) regarding items on the agenda and to consider any dispensations required to transact the business on the agenda. Cllr Bradley , Cllr Jackson, and Cllr Palmer – Allotment holders. |  | Closed |  |  |  | 2023-05-31
2023-05-31 | 5 | Public Participation session with respect to items on the agenda or any items that they wish to bring to the Councils attention. One member of the public attended to discuss item 26. There was a discussion on the creation of a community orchard at Bury Lane allotments on plot 13 and potentially plots 11 and 12. The proposal is to plant some fruit trees which would be supplied, planted and maintained by the individual. |  | Closed | 31/05/2023 (26) & 23/1557 |  |  | 2023-05-31
2023-05-31 | 6 | Update on available plots on Brook mead and Bury lane Brookmead x 2b,2c,2d, 1,18A,23,25C Bury Lane x 2 (A/B/C), 3 (A) , 5 , 6 ,13. | 1. Clerk to enquire with plot holder about Plots 11 and 12 at Bury lane are not being worked. 2. Clerk to confirm status of Plot 25C on brookmead. 3.Move a copy of the allotment master to drop box to aid the allotment inspector with her monthly report. | closed |  | Clerk | 04/09.2023 | 04.09.2023 | Plot 11 and 12 is being worked and covered. Cllr Palmer and Jackson have both been in contact with tenant. Close the item.
2023-05-31 | 7 | Clerks report on general state of three playgrounds | 1. A list of defects to be consolidated by the next meeting | closed |  | Clerk | 2023-07-01 | 04.09.2023 | Report due at July Rec meeting Cllr Palmer reported onoy issue with GW goal - now fixed. Close item.
2023-05-31 | 8 | Report from Allotments Supervisor. The condition of the Council’s Ryobi strimmer will be reviewed after it was reported that it has failed/burnt out – it has a 3-year warranty. |  | Open |  | Clerk | 04.09.2023 |  | Clerk to check with Handyman. Confirmed tht the unit is working fine.
2023-05-31 | 9 | Agree the remit and form a working group for the replacement play equipment project at Great Waltham Recreation Ground. The purpose of the working group would be to develop a replacement strategy including a review of appropriate play equipment, replacement timescale and funding proposals. The working group would include all members of the Recreation Committee and the wider community to aid consultation. | 1. The committee agrees to this and recommends it to the Council. | closed |  | Cllr Martin | 04.09.2023 | 04.09.2023 | Accepted at June PC meeting Working group has met twice and is running. Close Item.
2023-05-31 | 10 | Discuss the offer from HAGS to provide initial support to the play equipment working group. | 1. Cllr Martin to set up a meeting. | Closed |  | Cllr Martin | 2023-07-01 | 2023-07-12 | Meeting arranged for July 18th
2023-05-31 | 11 | Update on the EALC request and subsequent decision to carry over the Ford End recreation ground CIF grant and agree to the next steps. The EALC has agreed to an extension to the time allowed to complete the work and have specified that the path has to be completed by August 31st. CAW Building Services will be instructed to start the work. | 1. Cllr Martin to proceed with the path works. | closed |  | Cllr Martin | 04.09.2023 | 04.09.2023 | Quote obtained - work planned to commence within 4 weeks Path completed and invoice paid. Close item.
2023-05-31 | 12 | Report back on the Allotment Open Day held on April 23rd. The allotment supervisor reported that there was some interest and two plots were rented out at Brook Mead. Bury Lane did not get any visitors. Consideration to be given to a second event in August/September to help advertise the availability of the plots. | 1. Consider this event being made an annual or 6 monthly events in line with the growing seasons. | Closed |  |  |  | 2023-05-31
2023-05-31 | 13 | Update on the request made to the landowner to hold income generation events at Great Waltham Recreation Ground. After careful consideration, the landowner suggested that the recreation ground should only be used by charitable endeavours for fundraising purposes. |  | Closed |  |  |  | 2023-05-31
2023-05-31 | 14 | Update on the storage container planning application and agree next steps. The decision of Chelmsford City Council planning department is due on June 15th, 2023. |  | Closed |  |  |  | 2023-05-31
2023-05-31 | 15 | Update on the allotment sites following the previous resolution for the handyman to spend an agreed amount of time at the allotments each month and discuss any outstanding issues and proposed solutions. Following a discussion it was proposed that the allotments are split out from the current handyman role and advertised as a contractor role for an estimated 24 hours during the spring/summer months. | 1. The specification of the role to be agreed and documented. The role can then be advertised. | closed |  | Cllr Gilbert | 04.09.2023 | 04.09.2023 | Advert to be placed in August Parish News. Contractor appointed for 2023. Close item.
2023-05-31 | 16 | Update on the Pavilion facilities and consider the need for occasional internal decorating. It was proposed that the cost of materials should be funded from hiring income. Proposals for the cost of paint will be submitted to the next monthly meeting and that the Council should consider a separate budget line and accounts from the next budget. | 1. Information to be added to the October budget round. | Open |  | Cllr Martin | 2023-07-01 |  | Budget for decorating materials agreed at June PC meeting
2023-05-31 | 17 | Confirm arrangements for the 2023 Play in the Park date.Chelmsford City Council have confirmed the booking for August 16th for the play in the park. It was agreed that a DBS checked charity (e.g. local pre-school or Scouts) should be offered use of the pavilion for fund raising, selling teas, coffees and cakes. The recreation ground gates are to be kept locked during the sessions. | 1. Cllr Palmer to approach local charitable organisations to gauge interest. 2. Cllr Palmer to approach local charitable organisations to gauge interest. | closed |  | Cllrs Palmer & Jenkins | 2023-09-04 | 04.09.2023 | Up Up and Away had a refreshment concession. The Play in the Park completed succesfully. Close the item.
2023-05-31 | 18 | Use of the GW rec ground for parking purposes to support the School fete on 30 th June 3.30pm to 7pm. The Friends of Great Waltham School Charity (FOGS) has planned a major event to support the school’s fundraising and have requested access to the recreation ground for car parking. The land owner supports the request subject to the weather conditions. | 1. The Committee supports the use of the field as long as suitable | Closed |  |  |  | 2023-05-31
2023-05-31 | 19 | Review of the Pavilion paperwork. | 1. Cllr Gilbert will review the documents. 2. Clerk to investigate and confirm position on Performing Rights Society. | closed |  | Cllr Gilbert & Clerk | 04.09.2023 | 04.09.2023 | Documents complete. PRS - the council has no requirement for PRS. Each individual user needs a PRS license if they use music.
2023-05-31 | 20 | Discuss laying back the hedges in November in support of improving them. The advantages were discussed but it was felt that it was inappropriate at this time. | 1. Cllr Bradley will make an enquiry on a conservation basis. | closed |  | Cllr Bradley | 04.09.2023 | 04.09.2023 | Investigation highlighted that the hedge has already been laid back. No ongoing requirement. Close Item.
2023-05-31 | 21 | Following the trial period, review the role of Playground Inspector and make any necessary amendments. An elected member has covered the weekly inspections at Great Waltham recreation ground. The Howe Street recreation ground and Ford End recreation ground are checked by the parish handyman. The Clerk provides holiday cover. All three individuals have been certified and trained in routine playground inspections. | 1. Defer any decision until the next monthly meeting. | closed |  |  | 04.09.2023 | 04.09.2023 | Succesful trial. Close item.
2023-05-31 | 22 | Consider the proposal to apply for an ECC Locality Grant for the purchase of a seat for Ford End Recreation Ground. The path work at Ford End recreation grounds provides an opportunity to complete another part of the overall project at the same time subject to a successful grant application | 1. The committee supports an application to the locality fund. | closed |  | Cllr Martin | 2023-07-01 | 04.09.2023 | June PC meeting supported the application. Successful application. Money received. Close Item.
2023-05-31 | 23 | Proposal- to offer a ‘free’ rent period for plot 26a as the neighbouring plot holder has cleared, strimmed, and cultivated it. The rent period and service charge will not be charged until October. The plot holder has supported the Council by clearing the plot and it was deemed appropriate to waive the plot holders rent until October. A discussion also took place on how allotment deposit charges are implemented for existing plot holders. | 1. Set up the hire period at Zero cost. 2. The £50 allotment deposit is only paid by new potholders to the site. | Closed | 23/1553 |  |  | 2023-05-31
2023-05-31 | 24 | Proposal- to contact the landowners with reference to the unkempt and unsafe area by the shop and find a solution together on its usage and upkeep. ( On behalf of parishioners). | Resolution: Defer to full council on June 19 th . | Open |  | Cllr Palmer | 2023-05-31 |  | to be refered to the parish Council
2023-05-31 | 25 | Proposal – to introduce a policy for our ‘waste’ and a system of recording for disposal. The Parish Council already has a process in place to ensure general waste is recycled and this item referred to the disposal of redundant equipment that would not be disposed of in the normal way. | 1. Cllr Gilbert and Cllr Palmer will draft a policy . | Open |  | Cllr Gilbert & Palmer | 04.09.2023 |  | template created Proposed policy Paperwork to be circultaed to all members
2023-05-31 | 26 | Discuss the request to change Plot 13 at Bury lane allotments into a community Orchard. In principle the committee supported the suggestion but a number of points would need further clarification, namely consideration on access to the bury allotments by members of the public, site specification - the area required, number of trees, types of trees, arrangements to return the plot back to the state required by the landlord etc. | 1. Cllr Jackson to prepare a briefing note for the next Parish Council meeting. | closed | 23/1557 | Cllr Jackson | 2023-07-01 | 04.09.2023 | Parish Council montly meeting. No update. Close item.
2023-05-31 | 27 | Consider a request for dog-proof fencing at Howe Street recreation area to allow dogs to be exercised off the lead. The Howe street fence is currently a three-wire fence with wooden posts. There is also a fence outside of the Parish Council fence. Concern were raised over the concept and the potential cost to fence the perimeter of the recreation ground. | 1. No action at this point. | Closed |  |  |  | 2023-05-31
2023-05-31 | 28 | Updates on the Action Tracker . Several items were closed as the actions were complete, and two items were added to the tracker: Ford End Goals to have soil added and the Great Waltham junior goals to be refurbished by the handyman and re-instated by volunteers. |  | Closed |  |  |  | 2023-05-31
2023-07-12 | 1 | Chair’s Welcome. Chair: Martin. Cllrs. Jackson, Gilbert, Bradley, Palmer. |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 2 | Apologies for Absence. Cllr Jenkins |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 3 | Declarations of interests (existence and nature) regarding items on the agenda and to consider any dispensations required to transact the business on the agenda. Cllrs Palmer, Jackson and Bradley – Allotments. |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 4 | Public Participation session with respect to items on the agenda or any items that they wish to bring to the Councils attention. There were no members of the public in attendance. |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 5 | Update on available plots on Brook Mead and Bury Lane. Brook Mead x 2b, 2c, 2d, 1, 18A, 23. Bury Lane x 2 (A/B/C), 3 (A), 5, 6, 7, 13. The list is still current with no enquiries underway. It was noted that compared with previous years we have additional vacant plots.5 or 6 plots need to be covered. |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 6 | Report on Playground Inspections. No additional issues have been raised. Reports are still a mix of hardcopy and softcopy but the recently purchased electronic system that operates with a tablet will in future ensure all inspections are recorded in one way. Training for the new process is underway. |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 7 | Report from Allotments Supervisor. Some issues with maintenance of the paths due to lawnmower issues were reported and it was confirmed that plot holders are responsible for cutting around their own plots. Brookmead is already starting to re-grow from the recent cut back exercise. Bury does not look as bad but it was cut a couple of weeks after the Brook Mead plots. Brookmead plot 9 – Issues with additional materials that are being kept off the plot. A deadline of 16th July had been proposed for the plot holder to move the items on to the plot. | 1. Clerk to write a letter to Plot holder of plot 9 both an electric copy and a hardcopy. | Open |  | Clerk | 04.09.2023 |  | Clerk confirmed the allotment holder was written to. Suggestion that due to good standing of plot holder that allotment supervisor discuss with the plot holder.
2023-07-12 | 8 | Updates on the Action Tracker - All. |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 9 | Discuss the 2023 Annual Playground Inspection Reports for Great Waltham, Howe Street and Ford End, review the findings and agree proposals to improve routine maintenance. 291 minor (Low/Very Low) defects were reported which is an improvement on previous years, probably as a result of improved maintenance and inspections. The Howe Street multi play replacement has since cleared 16 of these. It was agreed that defects can be reduced further by a focus on preventative maintenance. It was also noted that several of the comments are advisory and relate to legislation changes via British Standards which are not retrospectively applicable. A spreadsheet listing the defects has been created and will be used for clearance of these minor defects with allocation to different owners. Current issues will be added to the tracker as they are identified by the inspectors. Consideration will be given to focusing on one piece of equipment at a time to manage and clear the issues. The report will be kept live. It was agreed that we need to make the areas look more inviting for user groups. Great Waltham currently looks cosmetically worse than the two other sites, mainly because of the aging wooden equipment. | 1. A process to be discussed and agreed. | Open |  | Clerk/Cllr Gilbert | 04.09.2023 |  | Spreadsheet of defects has been created and is a standard agenda item.
2023-07-12 | 10 | Following the trial period, review the role of Playground Inspector and make any necessary amendments – deferred to the May meeting. Cllr Palmer’s certificate expires in September 2024. A discussion was held on the process of councilors carrying out the inspections which started as a trial. It was noted that the RPII certified course is expensive, especially with 3 certificate holders from the Parish Council. The benefit of freeing up the handypersons time was noted and it was agreed to consider expanding the role to other elected members so that a granular view of the equipment is spread through the Council. New software is coming online which will improve the inspection process. | 1. Cllr Palmer will discuss with Rospa an alternative training quote. 2. The principle of 3 playground inspectors will continue. | close | 23/1488 | Cllr Palmer | 2023-07-12 | 04.09.2023 | the spreadsheet is being monitored at recreation committee meetings. No update close item.
2023-07-12 | 11 | Discuss the Great Waltham Recreation Ground play area project working group meeting planned for July 18th and agree objectives for the meeting. Simon Carson from HAGS will run a meeting with the working group. The previous decision to move away from wood to more attractive modern units will be discussed along with funding options and the best routes to make the improvements. After a site visit and discussions with stakeholders a 3D design will be created. There is a potential for a Community Trust Company to be created to undertake funding options across the spectrum of fund-giving bodies. All HAGS work will be free of charge but enables the possibility of a preferred supplier. Initial ideas included something similar to the Maldon area for a fully accessible area for scooters, bikes and skateboards which it was felt would be supported within the community. The potential may be for a 5-year plan with individual items being replaced each year. It was noted that young individuals may use equipment in a different way to how it’s planned by adults. |  | closed |  |  | 2023-07-12 | 04.09.2023 | Working Group update at each meeting of the committee. Team has met and reviewed the proposal. Close Item.
2023-07-12 | 12 | Update on Pavilion maintenance work and storage container installation plans. The magnolia walls were painted on Tuesday 11th July but have already been marked up by a user group. However, the new paint is washable and it is hoped the marks can be removed. The decorating materials are in stock and the white surfaces will be painted in two weeks’ time. The area for the container has been cleared by a local volunteer and the storage container is on order and will be delivered towards the end of the month. The green unit requested is in Southampton rather than London so additional costs were considered. It is anticipated the cost of providing power and lighting inside the container will cost around £80 in electrical parts using volunteer labour. |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 13 | Review the installation of the replacement Multi Play unit at Howe Street Recreation Ground. A volunteer working group was created with Cllr Jenkins, Palmer , Huggins, Jackson. Consultation took place via the Parish news – but no responses were received. 3 suppliers were approached for quotes as per financial regulations. Installation via Premier Playgrounds of the HAGS unit took place over 3 weekends. The process of splitting the unit purchase from the installation has been successful on two occasions now so is accepted as the standard process. The new unit was used thoroughly at the recent Howe Street annual big picnic. It was also noted that the see-saw was not really used. A write-up of the picnic and the new unit for the Parish News would be welcomed. The cost was around £20,000 and was in line with the budget agreed by the Parish Council. |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 14 | Update on the path works at Ford End Recreation Ground. Following the extension of the grant period by the EALC the quote for the path work from the gate entrance to the picnic area has been received from CAW and the works have been approved to proceed. The work will be undertaken before the end of August. The cost is £5,000 plus VAT. The ECC Locality fund application has been approved for a seat to be installed at Ford End. A seat has been sourced from Glasdon and will be installed during the path works. The cost of the seat is £638. The committee is grateful for Cllr Steel’s support for the application. |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 15 | Confirm plans for autumn allotments open day. Opens Days are seen as an opportunity to showcase the allotments. It was suggested it would take place around mid-September subject to the necessary grounds maintenance taking place. |  | Closed |  |  |  | 2023-07-12
2023-07-12 | 16 | Update on allotment maintenance role following the Parish Council decision to outsource the work. An advertisement for the role has been placed in the Parish News. It is hoped that the role will be filled by mid-August. |  | Closed |  |  |  | 2023-07-12

## F&GP Committee
Great Waltham Parish Council - Finance & General Purposes Committee Meetings Action Tracker
May 2023 - April 2024 inclusive (with carried forward items)
2023-08-01
Meeting Date | Agenda Item Ref. No. | Agenda Item (in bold) with narrative from meeting discussion | Resolution(s), if any | Open/ Closed | X/refer | Action Owner(s) | Last Updated | Date Closed | Update Log
2022-08-28 | 10 | To consider and agree enhancements in financial reporting, including identifying additional accounting tools (such as software packages) to streamline processes and improving access to management information. Consider potential options to reduce the resource investment by the RFO and consider potential savings by moving to a software package. | 1. The RFO to investigate potential options and feedback to the committee. | Closed | 23/01/2023 (9) 23/1552 | Clerk/RFO |  | 2023-07-31 | Carried forward from previous period 31/07/2023 meeting - Clerk reported that software acquired, training completed and proposal is to move financial reporting to the new AdvantEdge system.
2023-01-23 | 7 | Review of Budget Performance 2022-2023 and any actions required. There was a careful review of the spend to date. This covered observations on each spend area. The current forecast is a slight underspend to budget overall. | 1. Accruals for expected but not received demands to be included in the general reserves. | Closed |  | Clerk |  | 2023-07-31 | Carried forward from previous period 31/07/2023 meeting - action completed. Agreed to close following further review of 2022/23 performamce.
2023-01-23 | 8 | Review planned budget 2023-2024 make recommendation to full council for any changes. No changes are envisioned at this time. | 1. Defer until the next meeting. | Closed |  | All | 23.01.23 | 2023-07-31 | Carried forward from previous period 31/07/2023 meeting - item closed - 2023/24 YTD performance reviewed at the meeting.
2023-01-23 | 9 | Review of software packages and recommendation to this committee. The Clerk provided an overview of both commercially available and specific parish council software. The Committee requested clarification on several areas of the recommended (AdvantEdge) software: • If possible, testimonials from local users of the software. • How many councils overall use the software? • What happens to the playground inspection sheets if the software company ceases to trade? • When can a new system be implemented? E.g. is a mid-financial year implementation possible? The Committee also requested a cost benefit analysis which can be used to support what is currently an unbudgeted expenditure. | 1. The Clerk to gather the data requested for the Committee. | Closed | 23/1552 | Clerk |  | 2023-07-31 | Carried forward from previous period 31/07/2023 meeting - Clerk reported that software acquired, training completed and proposal is to move financial reporting to the new AdvantEdge system.
2023-01-23 | 11 | Review the budget for the Howe St Multi Play replacement and consider recommending an increase. A Budget of £15,149 of the £21,000 capital works budget is allocated to this project. Supply costs have been received from Proludic at £16,072.32 inc. VAT and delivery; Wickstead £33,269.16 inc. VAT and delivery; and HAGS £10,690.34 inc. VAT and delivery. A separate cost of installation of £8,090 also has to be considered. Resolution There are sufficient funds within the capital works budget to accommodate the increased costs if the HAGS unit is approved. It was noted that some other planned items may be deferred. Resolution To recommend that in the consultation document to Howe Street residents the HAGS unit is cited as the preferred option, subject to its costs being approved by the Council. | 1. There are sufficient funds within the capital works budget to accommodate the increased costs if the HAGS unit is approved. It was noted that some other planned items may be deferred. 2. To recommend that in the consultation document to Howe Street residents the HAGS unit is cited as the preferred option, subject to its costs being approved by the Council. | Closed | 23/1549 | All |  | 2023-07-31 | Carried forward from previous period Advert placed in the Feb 2023 parish News. 31/07/2023 - item closed as things have moved n since January - unit purchased and installed following consultation.
2023-01-23 | 12 | Review the cost of Pavilion storage container options and make a recommendation to the Parish Council. • The Parish Council previously resolved to install a container at Great Waltham Recreation Ground. However, after feedback from some residents that live close by other options have been explored. • A standard storage container is 2260mm (H) x 2200mm(W) x 2438mm (L) with a cost of £2640 (exVAT). • An Armorgard unit is either 2065mm (H) x 2075mm (W) x 2960 (L) with a cost of £2625.08 (ex VAT) and comes flat packed and needs assembly, or slightly smaller at 2065mm (H) x 2075mm (W) x 2010mm (L) at a cost of £2064.86 ex VAT) and also comes flat packed and needs assembly. • Planning requirements for the container are being investigated by Cllr. Huggins. | 1. Confirm that the different sizes will meet the handyman’s requirements. | Closed | 23/1544 | Clerk |  | 2023-07-31 | Carried forward from previous period 31/07/2023 - item closed as things have moved on since January - container has been purchased and installed.
2023-07-31 | 1 | Elect a Chair Cllr Gilbert was proposed and elected. |  | Closed |  |  |  | 2023-07-31
2023-07-31 | 2 | Chair’s Welcome: Chair: Gilbert. Cllrs: Stephenson, Martin, Bradley. The Chair noted this was the first F&amp;GP meeting since January (the April meeting was not quorate), so some agenda items have been carried forward. |  | Closed |  |  |  | 2023-07-31
2023-07-31 | 3 | Apologies for Absence. Cllrs: Micklem and Jackson. |  | Closed |  |  |  | 2023-07-31
2023-07-31 | 4 | Declarations of interests (existence and nature) with regard to items on the agenda and requests for dispensation. There were no declarations. |  | Closed |  |  |  | 2023-07-31
2023-07-31 | 5 | Public Participation session - items do not need to on the agenda. One member of the public attended to discuss the proposed National Grid electricity pylons scheme from Norwich to Tilbury and commented that:  The pylons will be 50metres high.  There are concerns both in relation to health issues associated with living close to pylons and the perceived loss in the value of houses due to visual blight.  In conjunction with the publicity campaign opposing the scheme (leaflets, articles, banners etc.), that use of land in South Street can be offered for a banner to be installed. The Chair confirmed that:  The Parish Council will continue to object to the current proposals (as included in the second informal consultation by National Grid) and will submit a response accordingly.  The Northwest and Southwest of Chelmsford Parishes Group of which Great Waltham is a member are working on a collective response.  The delivery to parish households of leaflets opposing the proposals has been organised.  The Council will add an agenda item to its next meeting (on 22 nd August) to discuss funding the supply of banners. |  | Closed |  |  |  | 2023-07-31
2023-07-31 | 6 | To review open items on the Action Tracker circulated prior to the meeting. All open items were reviewed and confirmed complete, and closed accordingly. |  | Closed |  |  |  | 2023-07-31
2023-07-31 | 7 | Review of the Budget Performance 2022-2023 (deferred from the previous meeting's agenda). The information was viewed on the new whiteboard/ projector screen. Each budget heading was reviewed and discussed to understand the reasons for differences between the original budget provisions and actual payments. This awareness of the dynamics involved will assist future budget setting. | 1. The figures were noted, and lessons learnt will be rolled into the budget for 2024-2025. | Open |  | All | 2023-07-31
2023-07-31 | 8 | Review of Budget Performance 2023 - 2024 The spreadsheet was reviewed but needs to be updated. The budget headings do not contain all the information. However, the overall spend is correct and accurate but the allocations need to be reviewed. | 1. The Clerk to review and update the spreadsheet and re issue to the Committee. | Open |  | Clerk | 2023-07-31
2023-07-31 | 9 | Discuss additional items for the 2024-2025 financial year (deferred from the previous meeting's agenda) | 1. A working group to be formed and to meet in September to consider the optimal format and presentation of information at the October meeting (where the Committee will look to recommend the 2024/25 budget). 2. The projected costs of purchasing and installing a defibrillator at Broads Green to be added to the plan. 3. The committed spend plan and its presentation format to be reviewed and updated. The three-year time frame to be maintained to help the budget process. | Open |  | 1. Clerk/Chair 2. Clerk 3. Clerk/All | 2023-07-31
2023-07-31 | 10 | To consider and agree the continued development of a procurement policy document (deferred from the previous meeting's agenda) After careful consideration of the original policy requirements (to consider introducing an approved supplier process), given the scope of existing Financial Regulations, it was agreed to pause the introduction of the policy at this time. If the Council finds that its activities come to demand a bespoke policy the work carried out to date can be quickly restarted. |  | Closed |  |  |  | 2023-07-31
2023-07-31 | 11 | To receive an update on implementation and use of the new finance software package The Clerk confirmed that he has had 3 training sessions on the software. The accounts have been entered up to mid-July on the system and the accounts have been reconciled online for April, May and June. The Clerk will stop using the MS Excel sheets in August once the July bank reconciliation has been completed. The system has a number of report production features which the Committee/Council may wish to utilise. | 1. The Clerk and the Chair to review the suite of reports available and make recommendations for future meetings. | Open | 28/08/2022 (10) 23/01/2023 (9) 23/1552 | Clerk/Chair | 2023-07-31
2023-07-31 | 12 | To discuss the Council’s reserving policy in light of comments in the Council’s latest internal audit report. A discussion was held around the levels of reserves that should be held. The Council has previously approved a General Reserve of £17,000 (although the methodology in arriving at this figure is unclear but seems to equate to holding reserves to cover 4 months of the operational costs applicable when it was agreed). The Council’s reserving policy now offers guidance on how a revised assessment can be made. However, the meeting noted that a broad-based technically calculated figure may not necessarily accurately reflect the likely circumstances of the Council needing to draw on its reserves (that is, reserves should always be adequate, but not overinflated because a model calculation takes account factors not relevant to GWPC). | 1. The working group to look at the reserving policy methodology and create a calculation process reflecting the Council’s activities. | Open | 23/1582 |  | 2023-07-31
2023-07-31 | 13 | To consider the introduction of an internal financial control document (as indicated in the Council’s latest internal audit report). The internal audit report was discussed. In view of the existing safeguards in Financial Regulations and Standing Orders the requirements of the auditor are unclear. | 1. The Clerk to contact the internal auditor to clarify the requirements. | Open | 23/1582 |  | 2023-07-31
2023-07-31 | 14 | To discuss and agree the format for recording the Council’s assets (to make clear any differences between financial reporting figures and insurance valuations). The asset list and insurance documents to be reviewed. The JPAG document for 2023 to be used as a guide. The asset list currently records the purchase cost of items. It was noted that some assets have not been professionally valued for some time. There are likely to be costs involved in securing revaluations. | 1. The Clerk and Chair to review the various sources and recommend the route forward to the Committee, including indications of out-of-date valuations. 2. Asset values should be reviewed, especially where there has been significant change over time, e.g. items such as the War Memorials. | Open |  |  | 2023-07-31
2023-07-31 | 15 | To receive an update on the application for a loan in relation to the proposed average speed camera system at Ford End, and to consider its impact on budgetary considerations going forwards. The Clerk has reviewed the process of securing a Public Works Loan Board (PWLB) loan, and identified that it is quite onerous and time consuming. Additional details are required on cost, consultation and the impact on the precept before the process can be started. The meeting noted that while a PWLB loan is not the only possible source of securing funding, it is likely to be the most cost effective in terms of interest rates. However, other (potentially less onerous) sourcing options can continue to be evaluated. | 1. Clerk to draft the process and issue to the Committee members. | Open |  |  | 2023-07-31

## H&T Committee
Great Waltham Parish Council - Highways & Transport Committee Meetings Action Tracker
May 2023 - April 2024 inclusive (with carried forward items)
2023-07-25
Meeting Date | Agenda Item Ref. No. | Agenda Item (in bold) with narrative from meeting discussion | Resolution(s), if any | Open/ Closed | X/refer | Action Owner(s) | Last Updated | Date Closed | Update Log
2021-04-26 | 21/705 | To address the reduction of pavement widths in the parish due to encroachment of the verges and determine what action can be taken to recover them Several Pavement footpaths are becoming overgrown in Ford End, Main road, Great Dunmow end of Ford End , Sandon Hill, main Road Ford End , Main road Chelmsford. Also footpath between Ford End and North End, and footpath rom Langley’s South lodge to Ash Keys. | Resolution Ford End highway pavements to be raised with Highways Rangers. Resolution Other areas identified to be added to the action tracker for future referral to Highway rangers | Closed |  | Clerk | 2023-07-24 | 2023-07-24 | Carried forward from previous period Highways Rangers wont work on the footpath from Kings farm down in to the Village as it has no backing. Highways Rangers recommend a LHP approach. Reported to Essex Highways 2726389 LHP scheme in use 09/04/2023 Essex Highways website: Enquiry Reference: 2726389 Issue: footway defects Street: Main Road, Chelmsford Last updated: 16/10/21 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues. The H&TC meeting (17/4/2023) noted that the LHP scheme raised (LCHE182010) has been archived, which, with the demise of the Highway Rangers, leaves the problem unresolved. The meeting agreed to produce a paper with new evidence making the case for recommending that the scheme is resurrected. 17/07/2023: The agenda for the meeting on 24/07/2023 contains an item to discuss a proposal (in conjunction with associated issues regarding traffic through Ringtail Green). 24/07/2023 meeting - see update in 24/07/2023(10) - supercedes this item which can be closed.
| 2755500 (Essex Highways) | Hoe Lane . Blocked Drain. Reported Essex Highways. 31.12.2021 |  | Closed |  | Clerk | 2023-07-24 | 2023-07-24 | Carried forward from previous period Blocked Culvert recorded. Repairs to be scheduled. 09/04/2023 Essex Highways website: Enquiry Reference: 2755500 Issue: highway drainage problems Street: Hoe Lane, Chelmsford Last updated: 09/02/22 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues. The H&TC meeting (17/4/2023) noted that the defect may have been fixed but the EH has not been updated. 24/07/2023 meeting - agreed individual defects should nt be recorded on tracker - item closed.
| 2758382 (Essex Highways) | Cherry Garden Road near number 62. Drain cover appears to be blocked. |  | Closed |  | Clerk | 2023-07-24 | 2023-07-24 | Carried forward from previous period 09/04/2023 Essex Highways website: Blocked drain. To be considered for repairs. Issue: highway drainage problems Street: Cherry Garden Road, Chelmsford Last updated: 02/02/22 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues. The H&TC meeting (17/4/2023) noted that the defect may have been fixed but the EH has not been updated 17/07/2023: The Essex Highways website still states: Enquiry Reference: 2758382 Issue: highway drainage problems Street: Cherry Garden Road, Chelmsford Last updated: 02/02/22 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues. However, if the defect has been fixed, it is recommended that the item is closed. 24/07/2023 meeting - agreed individual defects should nt be recorded on tracker - item closed.
| 2771004 (Essex Highways) | Dead Ash Tree at corner of Lucks Lane , main road , Howe Street . Potential to close the road. Dead Ash tree. |  | Closed |  | Clerk | 2023-07-24 | 2023-07-24 | Carried forward from previous period 09/04/2023 Essex Highways website: Enquiry Reference: 2771004 Issue: vegetation problems Street: Lucks Lane, Chelmsford Last updated: 23/03/23 Status: The issue was reported on a road that has been inspected and identified issues are recorded and actioned in line with our maintenance strategy. The H&TC meeting (17/4/2023) noted that the defect may have been fixed but the EH has not been updated. 17/07/2023: No longer shown on Essex Highways map. Recommend item is closed. 24/07/2023 meeting - agreed individual defects should nt be recorded on tracker - item closed.
2022-06-13 | 22/1177 | Discuss a request for double yellow lines at the junction of Duffries Close and South Street – both ends. Following a previous request from a local resident for double yellow lines at the end of Duffries Close to prevent dangerous parking some members inspected the site but did not feel double yellow lines were necessary at this time. Discuss a request for double yellow lines at the junction of Duffries Close and South Street – both ends. | 1. Move to the action tracker. 2. Clerk to write to write to resident and confirm that we will continue to monitor | Closed |  | All | 2023-07-24 | 2023-07-24 | Carried forward from previous period The Parish Council will monitor the situation Continue to monitor 17/07/2023: Over a year since issue raised - unless further communications, recommend item is closed. 24/07/2023 meeting - agreed to close item.
| 2788600 (Essex Highways) | Church Lane. Ford End. Overgrown trees and hedges |  | Closed |  | Clerk | 2023-07-24 | 2023-07-24 | Carried forward from previous period Potential to be done this week 09/04/2023 Essex Highways website: Enquiry Reference: 2788600 Issue: vegetation problems Street: Church Lane, Chelmsford Last updated: 23/03/23 Status: The issue was reported on a road that has been inspected and identified issues are recorded and actioned in line with our maintenance strategy. The H&TC meeting (17/4/2023) noted that the defect may have been fixed but the EH has not been updated. 17/07/2023: Reference 2788600 no longer shown on Essex Highways tracking map, although the map also shows this issue for Church Lane: Enquiry Reference: 2736721 Issue: vegetation problems Street: Church Lane, Chelmsford Last updated: 29/11/21 Status: We've carried out an initial assessment of this issue. We are getting more information to decide what action to take. However, given absence of original item and date of 2736721, recommend this item is closed. 24/07/2023 meeting - agreed individual defects should nt be recorded on tracker - item closed.
2023-07-18 | 22/1204 | To consider the merit of requesting roadside parking restrictions adjacent to the Hatchfields entrance gate to Great Waltham Recreation Ground. The meeting noted the poor condition of some parts of the wooden entrance gate. The case for applying for parking restrictions was discussed. The relatively low volume of traffic and the need for residents’ parking spaces were mentioned. | 1. Clerk to get a quote to replace the wooden entrance structure with the same style of structure. 2. Clerk to add advisory signs to the new structure reminding people exiting the park about the dangers of the road (inside) and asking drivers not to park directly adjacent to the gate (outside). 3. Any traffic restrictions to be delayed and the situation monitored. | Closed |  | Clerk | 2023-07-24 | 2023-07-24 | Carried forward from previous period New fence being quoted on. Once the fence is added a notice to be attached. Continue to monitor. 17/07/2023: No further issues have been raised. Recommend this item is closed. 24/07/2023 meeting - agreed to close item.
2022-05-23 | 22/1133 | To discuss actions to be taken at Ringtail Green following the extraordinary meeting at Ford End. A report was circulated with 4 proposals: 1. Install Ringtail Green Name plates with a drive slowly message. 2. Pursue Quiet Lane status for the lane – approximate cost £2,000. 3. Paint Slow road markings at either side of the bend. 4. Advisory road signs at either side of the bend e.g., maximum speed and chevrons. | 1. Item 1 – Clerk to contact the street naming team at Chelmsford City Council 2. Clerk to raise LHP requests via Cllr Steel for items 3 and 4. | Closed |  | Clerk & HT&C | 2023-07-24 | 2023-07-24 | Carried forward from previous period Item 1 - Has been sent in to the LHP - this has been validated and will now go into the queue for funding. Item 2 - Is already in the LHP queue. - this will not proceed as this did not get the support of the other members of the LHP.“Awaiting Funding” list – LCHE212014 Item 3 - LHP request to be raised by the Clerk - On item 3 – Painted ‘Slow’ road markings at either side of the bend I discussed this with the LHP Manager. He believes that to have SLOW written on the road, you also have to have a triangular warning sign as well. This would be determined as part of the design process. However, it would need to get through the LHP validation process first to go to the design stage, which is unlikely to happen given that the recorded speeds were an average 22mph, 85th percentile 27mph and there are no reports of accidents in that area . These measurements were made on the straight patch as specified by GWPC. However, if GWPC wish to fund this option, the LHP Manager estimated a cost between £5K and £10K. To refine the cost estimate would need the design work to be undertaken, which is usually about a third of the cost Item 4 - LHP request to be raised by the Clerk - Advisory road signs at either side of the bend, e.g. advisory max speed or right/left hand bend signs Advisory speed limits would have the same issues as Item 3 above – maybe more onerous scrutiny. The Price guide suggests that “Change of single speed limit which is uncontentious and where minimal infrastructure is required. £15,000” As this is not actually a change, it may not be as high as that. Again, to refine the estimate would need a funded design The H&TC meeting (17/4/2023) noted that it has only been possible to progress one proposal (LCHE222014). The meeting agreed to produce a paper with new evidence making the case for recommending that previously rejected schemes are reconsidered, especially taking account the impact of the archived scheme LCHE182010. 17/07/2023: The agenda for the meeting on 24/07/2023 contains an item to discuss a proposal (in conjunction with associated issues regarding traffic through Ringtail Green). 24/07/2023 meeting - see update in 24/07/2023(10) - supercedes this item which can be closed.
2022-08-15 | 22/1212 | 22/1212 Report by County Councillor - Cllr Mike Steel 20’s Plenty campaign. The scope of the campaign locally is likely to be predicated by an outstanding update by Safer Essex Roads Partnership to its Functional Route Hierarchy Review, to be followed then by a revision of the Essex Speed Management Strategy. There is no published date for completion of these reviews. | 1. The Clerk to write to Safer Essex Roads Partnership for an update on the timetable for completion. | Open |  | Clerk | 2023-07-24 |  | Carried forward from previous period Clerk to update next meeting. The H&TC meeting (17/4/2023) noted that the Clerk will chase a response to the outstanding query. 24/07/2023 meeting - noted that Hierarchy Review continues with no agreed issue date. Agreed to monitor progress, but to ensure any relevant GWPC representations continue to be fed into the process.
2022-08-15 | 22/1233 | 22/1233 To report back to the Parish Council on the online seminar hosted by Essex association of Local Councils on - 20’s Plenty - attended by Cllrs Palmer and Martin. [See Update Log comments for full narrative of reported items] Resolution Fact finding from other councils and consideration of further engagement and action deferred to the Highway and Transport Committee. | 1. Fact finding from other councils and consideration of further engagement and action deferred to the Highway and Transport Committee. | Closed |  | Cllrs. Palmer & Martin | 2023-07-24 | 2023-07-24 | Carried forward from previous period Reported items: Cllrs Palmer and Martin reported that: • Nationally there are already many streets currently set to a maximum of 20mph. • 121 delegates covering seventy-nine different organisations (including 75 Town and Parish Councils across Essex) were able to attend the two sessions. • 20’s Plenty southeast representative was the principal speaker. • There are different campaigns being run around the county, but Essex Highways are not actively considering such initiatives at the moment (see item 22/1212 above). • Parish Councils will be more effective working together. • Speeds of 20mph or less within new developments are easier to achieve as they are built to feel they are low speed areas and thus tend to be as self-enforcing. This desired outcome is often more difficult in rural areas. • The campaign suggests each parish council should consider passing a resolution to request from Essex County Council an acknowledgment that 20mph is appropriate for many of their roads. • The seminar noted that in 30mph areas a significant percentage of drivers will drive at 40mph, so a 20mph limit would have the effect of reduce the level of speeding to nearer, say thirty mph. Cllrs. Palmer & Martin to update next meeting. 24/07/2023 meeting - agreed this item can be closed
2022-09-07 | 7 | Discuss and agree which of Council’s current ongoing activities now come within the remit of the Committee. Cllr Palmer is the Parish Council Public Transport Representative. The existing items listed on the action tracker to be reviewed and validated (see below). The Parish Transport representative to consider a monthly report for the Parish News. | 1. Clerk to investigate if the Public Transport forum of Essex County Council plans to hold meetings where the Committee can be represented. 2. Cllr Palmer to prepare a draft of the role of the Parish Council Public Transport Representative. 3. Cllr Gilbert to be the point of contact for all transport related matters. | Open |  | 1. Clerk 2. Cllr Palmer | 2023-07-24 |  | Carried forward from previous period 1. Transport Meetings March 2023. Meeting agenda was passed to the parish transport representative 2nd Feb. Clerk to update next meeting. 24/07/2023 meeting - agreed this item can be closed. 2. Outstanding. The H&TC meeting (17/4/2023) noted that this remains outstanding. Carried forward to next meeting. 24/07/2023 meeting - carried forward to next meeting
2022-09-07 | 8 | Review and validate outstanding items on the Highways tab on Tracker document. | Consider adding [scheme to address reduction of pavement width in Ford End] to a list of potential LHP projects | Closed |  | Clerk | 2023-07-24 | 2023-07-24 | Carried forward from previous period Clerk to update next meeting. 17/07/2023: The agenda for the meeting on 24/07/2023 contains an item to discuss a proposal (in conjunction with associated issues regarding traffic through Ringtail Green). 24/07/2023 meeting - see update in 24/07/2023(10) - supercedes this item which can be closed.
2023-02-13 | 11 | To review the Speed Watch reports for Ford End and Great Waltham. • The meeting received an update from a member of the Ford End Speed Watch group. • There are 4 members of the group in Ford End. Additional volunteers would be welcomed. • Data from the weekly checks was shared with the Committee. • While it was noted that PSV and HGV slow down the traffic, there are still plenty of high-speed drivers . Anyone travelling in excess of 36 mph is recorded. • There are four designated recording locations. Traffic travelling in both directions is recorded . The time of the checks is random but tend to be early morning (9.00-10.00am) or late afternoon. A reported driver will receive a warning from Essex Police. | 1. Standing invitation to Committee meetings for the parish’s Speed Watch co-ordinators. | Closed |  | Clerk | 2023-07-24 | 2023-07-24 | Carried forward from previous period Clerk to update next meeting. The H&TC meeting (17/4/2023) agreed that once all coordinators have been notified of the opportunity to attend meetings the item can be closed. 24/07/2023 meeting - agreed item can be closed.
2023-02-13 | 17 | To consider the installation of deer signs around the village due to the increased levels of deer. The meeting agreed that with more information a request for new signs could be offered for consideration. | 1. Add to the list of LHP requests for discussion should further information be forthcoming. | Closed |  | Cllr. Lockwood | 2023-07-24 | 2023-07-24 | Carried forward from previous period Update required. H&TC meeting 17/04/2023. Resolution: Contact Cllr. Lockwood for details or we will look to archive. 24/07/2023 meeting - Clerk confirmed Cllr Lockwood contacted, but no response. Agreed to close item and reopen if future contact.
2023-04-17 | 5 | To note the latest positions and developments for items on the Committee’s action tracker document and to agree actions and/or make any recommendations to the Council to facilitate their completion and closure. The meeting noted that the Essex Highways defects tracking map shows approximately 80 outstanding defects of one type or another on or immediately adjacent to the B1008 in Ford End (between Kings Farm and Ford End School). | 1. Chair and Clerk to draft an e-mail to Essex Highways to confirm the status of defects noted on action tracker (as some seem to have been resolved without the EH database having been updated). 2. Clerk to request details of all defects shown as outstanding on the Essex Highways website that are in the Parish of Great Waltham. 3. Clerk to establish the existence (or not) of Playground signage for the Great Waltham Recreation Ground at both entrances. | Open |  | Cllr Gilbert & Clerk | 2023-07-24 |  | Carried forward from previous period 24/07/2023 meeting 1. & 2. requests have been made but no response to date. 3. Clerk confirmed no playground signage at Great Waltham. The meeting agreed to establish position at FE & HS grounds, and will consider whether to discuss requesting provision of signs at next meeting.
2023-04-17 | 7 | To note the latest positions and developments on LHP schemes for works in the parish and to agree actions and/or make any recommendations to the Council in relation to their prioritisation and progress. | 1. Remove the individual defects reported by members of the Committee from the tracker. | Closed |  | Clerk | 2023-07-24 | 2023-07-24 | Carried forward from previous period Recommend close this item as only existing individual defects being monitored (and being recommended for closure) and no new ones being added. 24/07/2023 meeting - agreed individual defects should nt be recorded on tracker - item closed.
2023-04-17 | 9 | To consider and make recommendations for the Council’s strategy in relation to enforcement of permitted uses of the Blossom Way public car park spaces. | 1. Recommend to the Council that the purchase and installation of replacement permitted parking signs at the Blossom Way car park – (laminated signs). | Closed |  | Cllr Gilbert | 2023-07-24 | 2023-07-24 | Carried forward from previous period 17/07/2023: Signs have been prepared and are awaiting installation. 24/07/2023 meeting - Clerk confimed signs have been installed. Item closed.
2023-04-17 | 11 | To recommend that the Council lobbies the relevant authorities/agencies to change the A120 backup diversionary route from the B1008 to the B1256. The upgrade work to the A120 showed that drivers used the B1256 (old A120) as their preferred diversionary route, notwithstanding signage directing them to the B1008. Unless a diversion required traffic to travel through Rayne village (which typically would not be required), this seems to be an obvious change to make. If the B1008 were to be downgraded from a PR1 status route it is understood that it would receive a lower level of maintenance compared to a non-PR1, but this would be offset by reduced volumes. | 1. Recommend to the council that it lobbies the relevant authorities/agencies to change the A120 backup diversionary route from the B1008 to the B1256. | Closed | 24/07/2023 (11) | Cllr Gilbert | 2023-07-24 | 2023-07-24 | Carried forward from previous period 17/07/2023: Cllr Gilbert wrote to National Highways on 22/05/2023 to obtain more information on impact of use of B1008 as a diversionary route during the period of the upgrade work to the A120. Update on response to be provided at meeting on 24/07/2023. 24/07/2023 meeting - National Highways response discussed as separate agenda item (24/07/2023 (11)). Close this item.
2023-04-17 | 12 | To recommend that the Council lobbies for measures to ensure the B1008 is not used as a preferred route once the NE by-pass is completed (given that it would remain the shortest and fastest route between the A120 at Gt. Dunmow and the new by-pass junction on the A131 at Gt. Leighs). Because it would still be the shortest and fastest route, the meeting identified the prospect of the B1008 remaining the road of choice for drivers (and their satnav systems) despite the suggestion that the new by-pass would automatically draw traffic away. | 1. Recommend to the council that it lobbies for measures to ensure the B1008 is not used as a preferred route once the NE by-pass is completed. | Open |  | Cllr Gilbert | 2023-07-24 |  | Carried forward from previous period 24/07/2023 meeting - carry forward to next meeting as further investigatory work required to recommend position to adopt.
2023-04-17 | 13 | To recommend that the Council lobbies for the reinstatement of the signage at Sheepcotes roundabout, which directs traffic to the A131/A120, so as to reduce use of the B1008. The meeting discussed securing access to the actual policy wording relevant to this item. The incongruity of having the originally installed signs which had the effect all parties desired (of signposting the use of the A131/A120 rather than the B1008) replaced by ones which now have the opposite effect simply to satisfy a policy guidance remains manifestly apparent. | 1. Recommend to the council that it lobbies for the reinstatement of signage at Sheepcotes roundabout which directs traffic to the A131/A120. | Open |  | Cllr Gilbert | 2023-07-24 |  | Carried forward from previous period 24/07/2023 meeting - carry forward to next meeting as further investigatory work required to recommend position to adopt.
2023-04-17 | 15 | Discuss drainage and surface issues at Church Lane, Ford End and determine the appropriate course of action. The kerbs and drain are being damaged by HGVs turning. The drain has been compressed and destroyed but may belong to a private landowner rather than being the responsibility of Essex Highways. Ideally, the drain should be within the verge rather than on the edge of the road. | 1. Clerk to write to Essex Highways and raise concerns about the demolished drain and request it to be moved back onto the verge. | Closed |  | Clerk | 2023-07-24 | 2023-07-24 | Carried forward from previous period 24/07/2023 meeting - issue has been raised as a defect, but as meeting agreed individual defects should nt be recorded on tracker, item closed.
2023-07-24 | 1 | Elect a committee Chairman. Cllr Gilbert was elected. |  | Closed |  |  |  | 2023-07-24
2023-07-24 | 2 | Chair’s Welcome: Chair: Cllr Gilbert. Councillors: Cllr Martin, Cllr Bradley, Cllr McDevitt and Cllr Jenkins. |  | Closed |  |  |  | 2023-07-24
2023-07-24 | 3 | Apologies for Absence. Cllr Palmer |  | Closed |  |  |  | 2023-07-24
2023-07-24 | 4 | Declarations of interests (existence and nature) with regard to items on the agenda and requests for dispensation. Cllr Bradley works for Essex County Council Highways. |  | Closed |  |  |  | 2023-07-24
2023-07-24 | 5 | Public Participation session - items do not need to on the agenda 2 members of the public |  | Closed |  |  |  | 2023-07-24
2023-07-24 | 6 | Update from the Speedwatch respresentatives from Ford End and Great Waltham. Great Waltham representative: • A recruitment drive was advertised in the Parish News and a team of 5 is now in place. • The team go out fortnightly within the hours of 08.00-09.00 or 16.00-18.00. • There are 2 approved sites: Hatchfields/Chelmsford Road junction and South Street/Cherry Garden Road. Usually, it’s a 1 hour session. • At the Hatchfields site they get 30 to 40 vehicles travelling over 37mph in the session. On some occasions vehicles are travelling over 50mph in the 30mph zone. • Some visual and verbal abuse has been received from drivers. Several residents of the village have been recorded speeding. • The maximum speed recorded by the team is 55mph. At the South Street/CGR location the team gets 10-12 speeding vehicles per session. • Overall, around 33% of the vehicles viewed are speeding. Ford End Representative: • The previous Speedwatch coordinator has had to step back due to other commitments. • Vehicles enter the village at over 40mph from both ends of the village. • The position of the Speed Indication Device (SID) by the school helps to reduce the number of speeding vehicles recorded by Speedwatch. Can an additional unit be considered for purchase? Can a permanent unit be considered? • Speedwatch is out once a week for approximately an hour (from 09.30 or 15.00). At least 12 vehicles are found to be travelling over 36mph in the 30mph zone. • Additional volunteers are sought for weekend monitoring. |  | Closed |  |  |  | 2023-07-24
2023-07-24 | 7 | Update from the Parish public transport representative. Defer to the next meeting |  | Open |  | Cllr Palmer | 2023-07-24
2023-07-24 | 8 | Discuss the public footpaths around the Parish and discuss options to improve the cutbacks potentially via a parish footpath partnership Great Waltham footpaths seem to be cut back towards the end of August. This leads to several paths being unusable for some of the year. Hand cutting tools around the key areas of the parish. Perhaps farmers could be incentivized to cut vegetation more regularly with funding from Essex County Council. The status of the footpath partnership was unclear. Does it still exist and what work does it organize/carry out? More information is needed. | 1. Cllr Bradley and the Clerk to gather data and report back to the Committee. | Open |  | Cllr Bradley/Clerk | 2023-07-24
2023-07-24 | 9 | To receive updates on all open Action Tracker items (based on the Tracker document circulated with the agenda) The tracker was reviewed, and several items closed. See the updated tracker. |  | Closed |  |  |  | 2023-07-24
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE182009 B1008 Ford End - Kerbing improvements |  | Closed |  | H&TC | 2023-07-24 | 2023-07-24 | Carried forward from previous period Raised kerbs at six bus stops through village as first stage Total scheme budget - £48,000 17/04/2023. In progress, completion imminent (1 kerb still to be completed). 17/07/2023: Scheme completed, item can be closed 24/07/2023: Work completed - close item
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE203002 Barrack Lane j/w Cherry Garden Road, Great Waltham - Footway Improvements |  | Open |  | H&TC | 2023-07-24 |  | Carried forward from previous period Design team advised footway may need regrading and could need land acquisition. Due to change in scheme scope agreed at June 2022 panel to make this a Design Only as first stage Design costs - £6,500 17/04/2023. Design agreed. Works delayed due to funding prioritisations, but completion expected in 2023/24. 17/07/2023: Works schemed for 2023/24 - yet to be commenced. 24/07/2023 meeting - noted work yet to commence, continue to monitor progress.
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE202036 Littley Park Cottages, Littley Park Lane, Hartford End - Road markings |  | Open |  | H&TC | 2023-07-24 |  | Carried forward from previous period Signage improvements and vegetation clearance, possible SLOW road marking Total scheme budget - £10,800 17/04/2023. On Hold. Works not undertaken. Agreed to chase reason for delay. 17/07/2023: Works schemed for 2023/24 - yet to be commenced. 24/07/2023 meeting - noted work yet to commence, continue to monitor progress.
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE182010 B1008 Ford End - Footway improvements |  | Closed | 24/07/2023 (10) | H&TC | 2023-07-24 | 2023-07-24 | Carried forward from previous period Highway Rangers to routinely side existing footways to fully open up available footway width 17/04/2023. This has been archived. Agreed that paper with new evidence should be produced, making the case for recommending that previously rejected scheme is reconsidered. 17/07/2023: The agenda for the meeting on 24/07/2023 contains an item to discuss a proposal (in conjunction with associated issues regarding traffic through Ringtail Green). 24/07/2023 meeting - see update in 24/07/2023(10) - supercedes this item which can be closed.
2023-07-24 | 9 | Action Tracker review item Ford End Average Speed Cameras |  | Open | 23/1523 | All | 2023-07-24 |  | Carried forward from previous period DfT: It was also suggested that DfT be contacted in relation to the B1008 through Ford End and its status as a back-up for the A130. I have spoken to the Transportation Planning & Infrastructure Manager at ECC Highways whose initial reaction was that DfT would not contribute any funds to a speed camera. I followed up on the verbal conversation with a request to ask DfT to downgrade the road so it was no longer a back-up route. This is the response I have received. “As you are aware he issue with the B1008 has been around now ever since the reclassification on the section of A130 from the A131 to Great Dunmow was undertaken. § When DfT approved the reclassification they did heavily caveat that the section from the A131 to Great Dunmow was required to remain available for all traffic as it was the route that traffic would expect to use if there was any event on the A120 or A131, that meant that no physical traffic calming, or weight limits could be applied. The situation to be reviewed when the Chelmsford Northeast bypass was completed. § We have previously investigated speed cameras and there is not a speeding issue or a collision problem therefore no justification. Traffic calming will create more issues than it solves, may increase emissions and noise as well as possible ground borne vibration. § I appreciate this is not new as such to you but reflects where we are at present.” . Recommendation for the Parish Council to re iterate its support for this cameras. Cllr Lee Scott is to confirm funding is available for 50% of the Unit. Cllr. Scott confirmed (3/4/2023): 'In terms of any LHP Match Funding I believe it was always the case that the Panel were waiting on GWPC to arrange their part of the funding. The Panel has to date not been informed that GWPC has their Match Funding contribution available'. The H&TC meeting (17/4/2023) noted the update and that the issue of whether the Council raises a loan to fund half of the cost of an ASC system will be discussed at the May monthly meeting. 17/07/2023: GWPC monthly meeting 22/5 agreed that PC should secure a loan to cover 50% of costs. Cllr. Lee Scott has subsequently confirmed the PC needs to show it has raised the loan and then 'the next step would be for the Local Highways Panel to make a funding recommendation towards the scheme'. The PC is ging through the process of submitting an application for a loan from the Public Works Loan Board. 24/07/2023 meeting - update provided at full council meeting 17/07/2023 (see 23/1523) reiterated.
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE192028 Ford End - Average speed cameras |  | Open | 23/1523 | All | 2023-07-24 |  | Scheme was design only in 2020/21, new revised costing £120,920. Suggestion previously was Match Funding from Parish Council and LHP, which would now require £60,460 from each source Implementation costs (for GWPC): £60,460 17/04/2023. Awaiting match funding. Parish Council reviewing options. Await outcome of discussion at May monthly meeting. 17/07/2023: GWPC monthly meeting 22/5 agreed that PC should secure a loan to cover 50% of costs. Cllr. Lee Scott has subsequently confirmed the PC needs to show it has raised the loan and then 'the next step would be for the Local Highways Panel to make a funding recommendation towards the scheme'. The PC is going through the process of submitting an application for a loan from the Public Works Loan Board. 24/07/2023 meeting - update provided at full council meeting 17/07/2023 (see 23/1523) reiterated.
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE212013 Ringtail Green, Great Waltham - Traffic management improvements |  | Closed | 24/07/2023 (10) | H&TC | 2023-07-24 | 2023-07-24 | Validation - 30mph - Northeast bound 21.8mph & Southwest bound 22.1mph. Very good speed compliance. Parish would still like consideration of Quiet Lane status, 17/04/2023. This has been archived. Agreed that paper with new evidence should be produced, making the case for recommending that previously rejected scheme(s) are reconsidered. Resolution: Case to be made for LCHE212013 to be reinstated. 17/07/2023: The agenda for the meeting on 24/07/2023 contains an item to discuss a proposal (in conjunction with associated issues regarding traffic through Ringtail Green). 24/07/2023 meeting - see update in 24/07/2023(10) - supercedes this item which can be closed.
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE222014 Ringtail Green, Great Waltham - Gateway signs |  | Open |  | H&TC | 2023-07-24 |  | Awaiting highway boundary information 17/04/2023. Works delayed due to funding prioritisations, but completion expected in 2023/24. 24/07/2023 meeting - await funding decision, continue to monitor.
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE223011 Great Waltham Primary School, South Street, Great Waltham - Signage improvements |  | Open |  | H&TC | 2023-07-24 |  | Validation - Recommends changing Patrol sign to School, need to check sign/pole as could be sticker or may need new pole/sign Total scheme budget - £6,500 17/04/2023. Low-cost scheme. Potential stickers rather than new signs. Funding decision pending. 24/07/2023 meeting - await funding decision, continue to monitor.
2023-07-24 | 10 | To consider the report Proposals to address the outstanding maintenance works on the footways alongside the B1008 through Ford End and for the introduction of enhanced traffic calming measures through Ringtail Green, Ford End circulated with the agenda, and to agree recommended actions The meeting acknowledged the contents of the report and agreed that because the situation remains unsatisfactory the recommended actions cited should be pursued. | These actions are recommended to the full council for approval: 1. To further lobby all relevant authorities and agencies for traffic calming and maintenance works as they affect the footways alongside the B1008 in Ford End and the road through Ringtail Green. 2. In particular, as a minimum, given the new evidence cited in this paper, to lobby for the reconsideration of all previously contemplated schemes (that is, Quiet Lane status for the lane, ‘SLOW’ road markings at either side of the bend, and advisory road signs at either side of the bend, e.g., maximum speed and chevrons). This would be achieved by working with its city and county council representatives to formulate submission documents for improvement schemes. 3. To request a meeting with Essex Highways to discuss the interpretation of ATC data and to seek its expertise on the range of traffic calming measures available for the road through Ringtail Green (notwithstanding any current absence of funding). That is, to understand what other innovative solutions it can recommend as the subject matter expert. 4. To seek clarification of how works previously undertaken by the Highways Rangers will be carried out in future. Even if this results in an understanding that such works will not now be completed, GWPC will be able to confirm to its parishioners that a valuable service has been withdrawn and alert them to the possible consequences. 5. To establish and communicate the mechanisms available for individual residents and businesses in the parish to complain about the loss of amenity (state of the footways alongside the B1008) and the hazards imposed because of increased pedestrian traffic on the road through Ringtail Green. And in addition, to draft a template wording which complainants could consider using. | Open |  | Cllr Gilbert | 2023-07-24 |  | 24/07/2023 meeting - items to be added to agenda of August monthly meeting.
2023-07-24 | 11 | To receive an update on the response from National Highways concerning the request for information in relation to the designation of the B1008 as the diversionary route for the A120 (see copy of letter circulated with agenda) and agree any further recommended actions. The alternative route B1256 is suitable apart from the section around Rayne due to the traffic calming features in place there. It was noted that National Highways does not collect data to monitor the success (or otherwise) of the diversion routes it introduces. The meeting agreed that there is benefit in responding to National Highways and to engage Essex Highways in the process, as the rationale for the current designation of the B1008 seems significantly weakened by the absence of any empirical evidence to indicate it is actually needed in its current format. | 1. The Committee to respond to National Highways’ correspondence and copy in Essex Highways with its feedback and comments. | Open |  | Cllr Gilbert | 2023-07-24
2023-07-24 | 12 | Proposal for SID pole at Church end on approach the Village. Defer to the next meeting. |  | Open |  | Cllr Palmer | 2023-07-24
2023-07-24 | 13 | Agenda item- to ask that cones are put in place by The Rose every weekend to deter vehicles from blocking paths Defer to the next meeting. |  | Open |  | Cllr Palmer | 2023-07-24