## Rules agreed
Minute Refrence | Detail of resolution | Date Originated | Action By | Last Updated | Current position
19/378 | 19/378 Discuss Media Channels – Facebook, Tick/Tock and Instagram Resolution Promote the website Resolution Promote the Agendas and Minutes on Waltham and Broomfield face book. | 16.03.2020 | Clerk | 2020-09-01 | Ongoing
20/373 | Discuss the recent spate of vandalism around Great Waltham Village and Park. The frequency of incidents appear to have increased. Residents are being encouraged to report to 101 or police on-line, and also to CHP ASB site if applicable. Police and CHP have been engaged and the number of incidents appear to have reduced. Resolution: Continue to monitor the situation. | 22nd April 2020 | All | 2020-09-01 | Use 101 on any incidents
20/436 | To consider what action GWPC can take to address hedges overhanging pavements and causing safety hazard Overgrown hedges are an offence under the 1980 Highways act. Discussion on hedges being cut back to within the householder’s boundary. 3 properties identified in Great Waltham and Howe street. Resolution Cllr Palmer to be point of contact for issues in Great Waltham and Cllr Jackson to be point of contact for Howe Street. Ford End to be dealt with by the Clerk via letter. Other Cllrs to raise any issues with the Clerk for passing these on. | 20th July 2020 | All | 2020-09-01 | Householders have been contacted in person.
20/445 | To review the need for the provision of a GWPC mower at Bury Lane Allotments following new information that allotment holders have not had access to the “communal mower”, and are using their own to keep their surrounding area tidy Resolution Communal areas to be strimmed by Handyman, plot holder to continue to mow their surroundings. | 20th July 2020 | Handyman | 2020-07-01 | Ongoing
FGP - Line item 5 | Resolution Review the Office equipment spend Resolution Split the Pension Payments in to Employee and Employer for the next budget Resolution review the accuracy of the budget for the next precept | 27th July 2020 | RFO | 2020-09-01
20/474 | Blanket authorization for the Clerk to use Facebook sites – The Waltham Grapevine, Broomfield & the Waltham’s and Ford enders to improve community engagement by broadcasting any relevant Govt notifications and consultations. | 17th August 2020 | Clerk | 2020-09-01 | Ongoing
19/017 | 19/017. To reflect on the biannual parish litter pick with reference to frequency and publicity. During the debate it was agreed that the nomination of a coordinator in each Village or hamlet would make the process better. Ford End currently do not have a nominated person. Additional Publicity from the coordinator should improve attendance. Resolution: Clerk to ensure that the item is on the agenda in January and August to enable publicity. | 15th April 2019 | Clerk | 01.08.2020 | Ongoing
Monthly Meeting 23.04.2018 - Item 35 | 35. Items for the Next Agenda The Chairman stated that he wanted future agenda items to be made in writing and phrased in terms of a proposal or motion and these are to be clear and unambiguous on what the item is about. This is in line with EALC guidelines to ensure that other Cllrs and members of the public know enough about the issue so as to be prepared in advance. The Clerk would ensure these objectives were met and that the agendas included the name of the proposer so that they can introduce the item at the meeting. | 23rd April 2020 | Clerk |  | Ongoing
20/536 | Clarify Parish Council Standing Orders In Relation To The Allocation Of Tasks. It was decided that resolutions would be clear and defintitive in line with standing orders. Resolution: To be clear on allocation of tasks and support. | 19.10.2020 | Clerk |  | Ongoing

## Tracker of Actions
Minute Refrence | Detail of resolution | Date Originated | Action By | Last Updated | Current position
19/175 | To propose further communication and initiate action on cobbled area at shop / beehive. Concerns had been passed to Councillors about the trip hazard at the cobbles area. Resolution : The Clerk to write to the landowner to highlight the concerns and request proposals to make changes | 19th August 2019 | Clerk | 2019-09-01 | Landowner agred that a proposal can be sent from the Parish Council to make chnages.
19/172 20/468 | 19/172 Discuss the complaint about parking at the Rose and Crown on the pavement during a recent event. Recent correspondence received by the Clerk had complained about car drivers parking on the pavement and not leaving space for Pedestrians. There is no restrictions on parking on the roads around the Rose & Crown. The Parish Council is pleased that the business is continuing to be a success and has already extended its own car park. Resolution: The Clerk to write to the Landlord to request patrons are advised to park on the road. 20/468 To consider complaints from the public in regard of Rose and Crown users cars parked along Chelmsford Road causing pavement to be blocked. Several complaints about the pavement being blocked to pushchairs and mobility scooters were received by Councillors. The item was discussed previously at the 19th August 2019 meeting. It is currently not illegal to park on the pavement outside of London, blocking the pavement may be. Even with cars part parked on the pavement, single file traffic still applies this would be the same if the cars were parked on the road. Resolution Cllrs Palmer / Bloomfield / Huggins to meet with landlord to discuss his plans | 19th August 2019 17th August 2020 | Clerk Cllrs Huggins / Palmer / Bloomfield | 01/09/2019 01/09/2020 | Letter Sent to the Landlord. Landlord put posters up on the surrounding area. LandLord of the pub is looking in to flyers for windscreens , In discussion for additional parking space for customers or staff, Looking to Council to cut back the grass that spread over the pavement and looking to add parking bays to the car park. Noted there is currently government consultation on parking on the pavement.
19/342 | To highlight the concerns with vehicular parking on greens and unauthorised access over greens for parking in front of homes. A proposal to explore the options for alleviating congestion/ parking difficulties in Cherry Garden Road. To engage highways and CHP in management/ cooperation in finding solutions where possible. The area does not provide enough off-road parking for modern households and road parking is a problem. Cars and Vans are parking on the green areas, causing contention and damage. The green areas are owned by Chelmsford City Council. Requests for driveways across the greensward appear to be addressed inconsistently by the Chelmsford City Council Planning department. Associated drop kerbs and driveways need to paid for by individual houseowners. The Parish Council can appreciate that residents should have more of a say in their environment and it is important to understand their views. Resolution: The Parish Council to create a specific survey of Cherry Garden Road and discuss the results with CHP and CCC if appropriate. | 17th Febuary 2020 | Clerk | 2021-02-01 | Survey created. To be debated at Oct 2020 meeting. Item Paused due to the Pandemic Cllr Steel to engage CCC in a productive discussion on their position.
20/442 20/472 | Recommendations Following Recreation Ground RoSPA Reports Review of the workload split down by skill set for internal and external workload. Resolution Additional meeting required to review the high cost items. Resolution Cllr Martin to review the play equipment and make recommendations. 20/472 Update on the Playground equipment maintenance works. The report was reviewed and accepted. It was noted that no new wooden equipment had been installed since 2009-2010. Resolution Reporting and Maintenance communication to be improved Resolution Identify an appropriate company or competent person to carry out remedial work Resolution A revised list of defect work to be passed to the handyman Resolution A schedule of repairs and replacement of defective equipment to be developed and agreed | 20/07/2020 24/08/2020 | Cllr Martin | 03.03.2021 | Spreedsheet of defects and workload built and issued Issues from 2020 reviewed and status agreed on items closed. Working Party created 03.03.2021
20/469 | 20/469 To consider public request to extend double yellow lines on South Street slightly beyond the point where the road starts to widen. A request from the public has asked if the double yellow lines could be extended further along South street, from the Chelmsford Road junction, such that vehicles were prohibited from parking until the road further widens. Resolution Reduce the on-street parking by one parking space the space nearest to the junction. Resolution The Clerk to make the request to the South Essex Parking Partnership. | 2020-08-17 | Clerk | 01.08.2020 | South Essex Parking Partnership to assign a technican to inspect the road and make a recommendation.
Recreation September 2020. Item 8 | 8. Discuss installing a drop down post at Broads Green so that the contractors Tractor can enter the green to cut it. Resolution Clerk to investigate if wooden lockable bollards are possible. | 2020-09-07 | Clerk | 20.09.2020 | Woodscape Contacted for quote. Quotes availabe on a wood effect drop down post £500.
Recreation September 2020. Item 8 | 8. Discuss installing a drop down post at Broads Green so that the contractors Tractor can enter the green to cut it. Resolution Cllr Steel to inspect the bollards and the one at Duffries close |  | Cllr Steel
Recreation September 2020. Item 8 | 8. Discuss installing a drop down post at Broads Green so that the contractors Tractor can enter the green to cut it. Resolution Clerk to discuss additional grass cutting costs with JCM |  | Clerk |  | No update
20/537 | Sheepcotes Roundabout – Removal Of M11 Direction Signs Signposts that point motorists to M11/Stansted from Sheepcote roundabout via the A130 were put in by the LHP some years ago. The recent upgrade of Sheepcote roundabout had removed these. Resolution: Clerk to write to Cllr Bentley to reinstate the original signs to point the M11 access via Great Leighs. Cllr Martin to support with the letter. | 01.11.2020 | Clerk & Cllr Martin | 15.02.2021 | Letter sent and received from Cllr Bentley Cllr Steel . Martin & Aldridge to have a meeting with Cllr Bentley to discuss - 2021 Meeting Held. Problem with consequential roundabouts and signage for M11
20/569 | 20/569 Agree to purchase and install new football goals at Great Waltham Recreation Ground. A set of New Junior goals to be installed at Great Waltham Recreation ground on the main pitch. Chelmsford City Council to be contacted to arrange the installation of sufficient sockets to enable the goal posts to be moved to avoid wear patterns. After reviewing the three quotes it was approved to place the order on Stadia Sports at a cost of £674.40 and likely cost of £400 per goal from Chelmsford City Council. Resolution Clerk to order units from Stadia Sports Resolution Clerk to arrange socket installation with Chelmsford City Council. Resolution Position the goals on the recreation ground to provide a football pitch suitable for under 9/10 junior football. Cllr Martin, Cllr Huggins and the Clerk to agree location. | 16.11.2020 | Clerk | 08.02.2021 | delay ordering the Goals as there is a requirement to Co ordinate - Chelmsford City Council , Goal Post Delivery and Recreation room works. Pause the ordering of the goals as there is currently no requirment for additional Junior goals.
20/570 | 20/570 Agree to progress the next stage of work at Great Waltham Recreation Ground Changing Rooms. The three quotes were carefully reviewed and the additional quote to consolidate phase 2 and 3 in to one phase was approved as this will reduce overall cost.(It was agreed that henceforth we would refer to the building as the “Pavilion”) Resolution Agree the layout as shown in the meeting of a single accessible toilet, a kitchen area and a large single open space. Resolution: The work to be awarded to Bg Premier Bathrooms & Plumbing. Resolution: Confirm whether a Change of Use, or Building Regulations application is required | 16.11.2020 | Clerk | 08.02.2021 | Purchase Order NOT issued Yet Planning and Change of use to be filled with CCC
20/592 | Proposal to install a seesaw at Howe Street, provided free by Broomfield Parish Council, for just the installation cost Resolution Agreed to proceed and use reserves. | 12.01.2021 | Cllr Steel | 18.01.2021 | Cllr Steel Has been in contact with Playquip to arrange installation. Cllrs Martin and Jackson to be notified of installation.
20/598 | Does the Parish Council want to replace the bin at Great Waltham Bus stop at the war memorial? Resolution Agree in principle to replace the bin subject to requirements of Chelmsford City Council street clean team. Resolution Clerk to confirm any requirement for a license | 12.01.2021 | Clerk | 08.02.2021 | City Council to Confirm Bin size / type and cost. Confirmation of license requirement awaited -

## Land within the Parish unowned
Description of the area | Update
Small piece of grass between the Shop and the CHP bungalows at Brook Mead | The Ownership is unknown
The Land between Hatchfields entrance and the CHP bungalows backing on to Main road | The Ownership is unknown
The Car Park and green area in DickeyMoors - Sits outside of South House Trust | The Green areas were passed to Chelmsford City Council Control
The Ownership of the Car park is unknown
The Domestic heating Oil Pump Station building = Junction of The Old School House / Village Hall/ Hatchfields | The Ownership is unknown
The Path in to the Chrurchyard theough the "Millenium Gateway" | The Ownership is unknown

## Closed Items
Minute Refrence | Detail of resolution | Date Originated | Action By | Last Updated | Current position
19/176 | To address concerns about the untidy state of the front garden of 73 Cherry Garden Road Resolution: An initial request to clear the area be sent to the resident. | 19th August 2019 | Clerk | 2019-09-01 | Letter sent to the resident. No Response. Noted that some of the debris has been removed.
20/464 | 20/464 Discuss quote to remove Ash tree at the Brook Mead allotments that is suffering from Ash Die Back. Resolution The removal of the tree was approved. Resolution As only one quote has been received Cllr Palmer to seek additional quotes. The Clerk to award the work to the lowest cost for cutdown and removal from site. | 2020-08-17 | Cllr Palmer |  | 16.11.2020 - Three quotes received. 16.11.2020 - Tree has been cut down this week.
20/473 | 20/473 Safety concerns of footpaths in the vicinity of agricultural reservoirs and the possible effects of adverse weather conditions. Concern raised about clay lined agricultural reservoirs drying out in the hot weather and then a deluge of water may cause cracking. ECC confirmed that the reservoir maintenance is the Landowners responsibility. Any issue with the footpath will be discussed by the Public Rights of Way officers with the Landowner. The 1975 Reservoirs Acts places an inspection regime in place depending on the volume of water above water level. Resolution The Clerk to write to the environment agency to verify if the inspections are taking place in Great Waltham Parish. | 2020-08-17 | Clerk | 01.10.20 | Information sent out to the Council on Reservoirs.
20/571 | 20/571 Consider results of traffic survey through Broads Green Review of the data supplied by Highways did not show a speed problem but did determine that the HGV volumes were around 1% and the LGV/MGV around 11%The survey is not able to determine whether this is traffic traversing the hamlet, or accessing it. On the basis of these volumes, it is highly unlikely that a weight restriction will be granted but we may be able to get “unsuitable for large Vehicles” signs Resolution Clerk to explore the possibility of requesting the Local Highways Panel to install an “Unsuitable for Large Vehicles/HGV” sign at either end of the Broads Green. | 16.11.2020 | Clerk | 14.12.2020 | LHP Bid submitted . Chased again 14.12.2020 LHP will not take this item forward.
20/432 20/470 20/568 | Proposal to discuss with the village hall increasing the trade bin in size to accommodate rubbish generated by the Parish for which the Parish is responsible for. Discussion on the types of waste generated in the Parish by the public. General waste and the dry mixed recycling. Resolution Agree with proposal to increase the general waste bin at the Village Hall to a suggested 660L unit and to add a new DMR unit of 660L.Costs to be split 50/50. Resolution Purchase recycling bins with Lids for the recreation areas in the Parish. Bins to have clear plastic bags. 20/470 Discuss proposal from the Village Hall on joint waste collection and Dry Mixed Recycling. The VH committee have made a proposal to jointly fund a larger fortnightly collection of general waste and a weekly collection of Dry Mixed Recycling. Costs of £57 pcm to be split equally between the Village Hall and the Parish Council. Resolution The proposal was accepted Resolution Cllr Huggins to prepare Work instructions / process for the teams. 20/568 Proposal to share cost of waste and recycling with GW Village Hall Cost of approximately £31 per month. Village Hall have agreed to an initial estimate of dry mixed recycling and general waste. One collection receptacle for Dry Mixed Recycling and one collection receptacle for general waste will be installed. Resolution Cllr Huggins approved to contract with the Village Hall with a delegated authority to agree any potential increase up to 10%. | 20/07/2020 17/08/2020 | 1. VH Committee 2. Cllr Huggins 3 Clerk | 2020-11-16 | Waiting on the Village Hall Committee. Reset due to chnages at VH. 16/11 - Cllr Huggins discussing with the VH as per minutes of the 16/11/2020 Agred with VH to 50/50 on costs - item closed
20/512 | To consider making an induction file for new councillors Cllr Gilbert offered his assistance to pull together with Cllr Palmer and the Clerk. This is not to replace the EALC training but is aimed at co-opted Councillors. Resolution Induction file to be created. | 2020-09-22 | Clerk & Cllr Palmer | 08.02.2020 | Cllr Gilbert has created a file with a lot of details. Additrional review required.
Recreation June 2020 | GW changing room • Quotes for Phase 2 – Doors, Windows and shutters Resolution The Current front doors to be retained Resolution New windows to be installed Resolution New wooden Shutters to be built by Cllr Huggins | 2020-06-22 | Sub Committee | 2020-09-01 | Update at the monthly Meeting
20/537 | Sheepcotes Roundabout – Removal Of M11 Direction Signs Signposts that point motorists to M11/Stansted from Sheepcote roundabout via the A130 were put in by the LHP some years ago. The recent upgrade of Sheepcote roundabout had removed these. Resolution: Clerk to write to Cllr Bentley to reinstate the original signs to point the M11 access via Great Leighs. Cllr Martin to support with the letter. | 01.11.2020 | Clerk & Cllr Martin | 15.02.2021 | Letter sent and received from Cllr Bentley Cllr Steel . Martin & Aldridge to have a meeting with Cllr Bentley to discuss - 2021 Meeting Held. Problem with consequential roundabouts and signage for M11