## Highways Items
Minute Refrence | Detail of resolution | Date Originated | Action By | Last Updated | Current position
1 | Ford End Average Speed Cameras |  |  |  | DfT: It was also suggested that DfT be contacted in relation to the B1008 through Ford End and its status as a back-up for the A130. I have spoken to the Transportation Planning & Infrastructure Manager at ECC Highways whose initial reaction was that DfT would not contribute any funds to a speed camera. I followed up on the verbal conversation with a request to ask DfT to downgrade the road so it was no longer a back-up route. This is the response I have received. “As you are aware he issue with the B1008 has been around now ever since the reclassification on the section of A130 from the A131 to Great Dunmow was undertaken. When DfT approved the reclassification they did heavily caveat that the section from the A131 to Great Dunmow was required to remain available for all traffic as it was the route that traffic would expect to use if there was any event on the A120 or A131, that meant that no physical traffic calming, or weight limits could be applied. The situation to be reviewed when the Chelmsford Northeast bypass was completed. We have previously investigated speed cameras and there is not a speeding issue or a collision problem therefore no justification. Traffic calming will create more issues than it solves, may increase emissions and noise as well as possible ground borne vibration. I appreciate this is not new as such to you but reflects where we are at present.” Alan Lindsay ¦ Transportation Planning & Infrastructure Manager
3 | Quiet lane - Ringtail Green |  |  |  | “Awaiting Funding” list – LCHE212014
21/897 | Discuss the LHP application to make Ringtail Green a Quiet Lane Cllr Steel declared a conflict of interest and did not take part in the debate. Briefing note was discussed. This is available on the website. Single track lane through a small hamlet. Increased number of pedestrians. Concerns raised about the vehicles that were out with the averages Resolution Clerk to write to Essex County Councilor Steel with Concerns about the data interpretation due to the outliers, request the cost of installation and the process and confirm that the current data belonging to ECC and LHP meets the Criteria for a Quiet Lane, and the Scheme can move forward to Validation. Resolution Clerk to draft the letter and share with the full Council. Cllrs Martin and Gilbert to provide the statistical data input. |  | Clerk | 2021-11-15 | ECC Cllr Steel Confirmed receipt of the letter a long explanation of the situation on Ringtail Green on the 26th May 2022 – copy attached. Since then, I have also submitted a signage request to the LHP for Ringtail Green which is in validation - under reference LCHE222014. I had also responded previously with this information
21/705 | To address the reduction of pavement widths in the parish due to encroachment of the verges and determine what action can be taken to recover them. Several Pavement footpaths are becoming overgrown in Ford End, Main road, Great Dunmow end of Ford End , Sandon Hill, main Road Ford End , Main road Chelmsford. Also footpath between Ford End and North End, and footpath rom Langley’s South lodge to Ash Keys. Resolution Ford End highway pavements to be raised with Highways Rangers. Resolution Other areas identified to be added to the action tracke rfor future referral to Highway rangers | 2021-04-26 | Clerk | 01.07.2021 | Highways Rangers wont work on the footpath from Kings farm down in to the Village as it has no backing. Highways Rangers recommend a LHP approach. Reported to Essex Highways 2726389
21/860 | Discuss options for the perceived speeding in Howe Street Some members of the public contacted the Parish Councillors with concerns and suggestions. Move the 60MPH from just outside the Village to beyond the bungalow called – ‘straight’. Suggestions included solid lines on the road, speed bumps, chicanes. The report from the County Council shows GWPC SID measurements were avg 34mph and that there are no collisions recorded. It was suggested that the SID readings are done again and that residents be invited to join the Community Speed Watch (CSW). Part of the process requires that CSW submit a requirement for a “safe” site in Howe Street which needs to be done by the GW coordinator. Resolution Consider adding Howe Street members to the GW speed watch group and registering a safe site in Howe Street Resolution Move SID to Howe Street to run latest data set one week covert, one week with display. | 21.09.21 | Clerk | 01.11.2021 | Sid Data to be run.
20/469 | 20/469 To consider public request to extend double yellow lines on South Street slightly beyond the point where the road starts to widen. A request from the public has asked if the double yellow lines could be extended further along South street, from the Chelmsford Road junction, such that vehicles were prohibited from parking until the road further widens. Resolution Reduce the on-street parking by one parking space the space nearest to the junction. Resolution The Clerk to make the request to the South Essex Parking Partnership. | 2020-08-17 | Clerk | 15.11.2021 | South Essex Parking Partnership to assign a technican to inspect the road and make a recommendation. Technican agrees. But wants to extend by 20m rather than the 2 or 3 m request. No comment from the Parish Council. Lines will be created once funding is available. One Complaint received
2755500 | Hoe Lane . Blocked Drain. Reported Essex Highways. 31.12.2021 | 31.12.21 | Clerk |  | Annual Inspection.
2758382 | Cherry Graden Road near number 62. Drain cover appears to be blocked. | 19.01.2022 | Clerk
2771004 | Dead Ash Tree at corner of Lucks Lane , main road , Howe Street . Potential to close thr road. Dead Ash tree. | 29.03.2022 | Clerk
2771174 | Remove the tactile kerb outside the Great Waltham Village Hall | 30.03.2022 | Clerk
2778851 | Streetlight Issues outside the School | 25.05.2022 | Clerk
22/1177 | Discuss a request for double yellow lines at the junction of Duffries Close and South Street – both ends. Resolution Move to the action tracker. Resolution Clerk to write to write to resident and confirm that we will continue to monitor | 13.06.222 | All |  | The Parish Council will monitor the situation
2788600 | Church Lane. Ford End. Overgrown trees and hedges | 31.07.2022 | Clerk
22/1177 | Discuss a request for double yellow lines at the junction of Duffries Close and South Street – both ends. Resolution: Move to the action tracker. Resolution: Clerk to write to write to resident and confirm that we will continue to monitor | 13.06.2022 | Clerk | 14.06.2022 | Receipt by resident acknowledged
22/1204 | To consider the merit of requesting roadside parking restrictions adjacent to the Hatchfields entrance gate to Great Waltham Recreation Ground. The meeting noted the poor condition of some parts of the wooden entrance gate. The case for applying for parking restrictions was discussed. The relatively low volume of traffic and the need for residents’ parking spaces were mentioned. Resolution: Clerk to get a quote to replace the wooden entrance structure with the same style of structure. Resolution: Clerk to add advisory signs to the new structure reminding people exiting the park about the dangers of the road (inside) and asking drivers not to park directly adjacent to the gate (outside). Resolution: Any traffic restrictions to be delayed and the situation monitored. | 18.07.2022
22/1133 | To discuss actions to be taken at Ringtail Green following the extraordinary meeting at Ford End. A report was circulated with 4 proposals: 1. Install Ringtail Green Name plates with a drive slowly message. 2. Pursue Quiet Lane status for the lane – approximate cost £2,000. 3. Paint Slow road markings at either side of the bend. 4. Advisory road signs at either side of the bend e.g., maximum speed and chevrons. Resolution Item 1 – Clerk to contact the street naming team at Chelmsford City Council Resolution Clerk to raise LHP requests via Cllr Steel for items 3 and 4. | 23.05.2022 | Clerk & Highways Committee | 18.07.2022 | Item 1 - Has been sent in to the LHP - this has been validated and will now go into the queue for funding. Item 2 - Is already in the LHP queue. - this will not proceed as this did not get the support of the other members of the LHP.“Awaiting Funding” list – LCHE212014 Item 3 - LHP request to be raised by the Clerk - On item 3 – Painted ‘Slow’ road markings at either side of the bend I discussed this with the LHP Manager. He believes that to have SLOW written on the road, you also have to have a triangular warning sign as well. This would be determined as part of the design process. However, it would need to get through the LHP validation process first to go to the design stage, which is unlikely to happen given that the recorded speeds were an average 22mph, 85th percentile 27mph and there are no reports of accidents in that area . These measurements were made on the straight patch as specified by GWPC. However, if GWPC wish to fund this option, the LHP Manager estimated a cost between £5K and £10K. To refine the cost estimate would need the design work to be undertaken, which is usually about a third of the cost Item 4 - LHP request to be raised by the Clerk - Advisory road signs at either side of the bend, e.g. advisory max speed or right/left hand bend signs Advisory speed limits would have the same issues as Item 3 above – maybe more onerous scrutiny. The Price guide suggests that “Change of single speed limit which is uncontentious and where minimal infrastructure is required. £15,000” As this is not actually a change, it may not be as high as that. Again, to refine the estimate would need a funded design