## Sheet1
HIGHWAYS AND TRANSPORT COMMITTEE
Reference | Open/Closed | Capital / Maintenance / Future items | Detail of resolution | Date Originated | Action By | Last Updated | Current position
1 | Open | N/a | Ford End Average Speed Cameras |  | All | 2023-07-17 | DfT: It was also suggested that DfT be contacted in relation to the B1008 through Ford End and its status as a back-up for the A130. I have spoken to the Transportation Planning & Infrastructure Manager at ECC Highways whose initial reaction was that DfT would not contribute any funds to a speed camera. I followed up on the verbal conversation with a request to ask DfT to downgrade the road so it was no longer a back-up route. This is the response I have received. “As you are aware he issue with the B1008 has been around now ever since the reclassification on the section of A130 from the A131 to Great Dunmow was undertaken. When DfT approved the reclassification they did heavily caveat that the section from the A131 to Great Dunmow was required to remain available for all traffic as it was the route that traffic would expect to use if there was any event on the A120 or A131, that meant that no physical traffic calming, or weight limits could be applied. The situation to be reviewed when the Chelmsford Northeast bypass was completed. We have previously investigated speed cameras and there is not a speeding issue or a collision problem therefore no justification. Traffic calming will create more issues than it solves, may increase emissions and noise as well as possible ground borne vibration. I appreciate this is not new as such to you but reflects where we are at present.” . Recommendation for the Parish Council to re iterate its support for this cameras. Cllr Lee Scott is to confirm funding is available for 50% of the Unit. Cllr. Scott confirmed (3/4/2023): 'In terms of any LHP Match Funding I believe it was always the case that the Panel were waiting on GWPC to arrange their part of the funding. The Panel has to date not been informed that GWPC has their Match Funding contribution available'. The H&TC meeting (17/4/2023) noted the update and that the issue of whether the Council raises a loan to fund half of the cost of an ASC system will be discussed at the May monthly meeting. 17/07/2023: GWPC monthly meeting 22/5 agreed that PC should secure a loan to cover 50% of costs. Cllr. Lee Scott has subsequently confirmed the PC needs to show it has raised the loan and then 'the next step would be for the Local Highways Panel to make a funding recommendation towards the scheme'. The PC is ging through the process of submitting an application for a loan from the Public Works Loan Board.
21/705 (Apr 2021) | Open | N/a | To address the reduction of pavement widths in the parish due to encroachment of the verges and determine what action can be taken to recover them. Several Pavement footpaths are becoming overgrown in Ford End, Main road, Great Dunmow end of Ford End , Sandon Hill, main Road Ford End , Main road Chelmsford. Also footpath between Ford End and North End, and footpath rom Langley’s South lodge to Ash Keys. Resolution Ford End highway pavements to be raised with Highways Rangers. Resolution Other areas identified to be added to the action tracker for future referral to Highway rangers | 2021-04-26 | Clerk | 2023-07-17 | Highways Rangers wont work on the footpath from Kings farm down in to the Village as it has no backing. Highways Rangers recommend a LHP approach. Reported to Essex Highways 2726389 LHP scheme in use 09/04/2023 Essex Highways website: Enquiry Reference: 2726389 Issue: footway defects Street: Main Road, Chelmsford Last updated: 16/10/21 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues. The H&TC meeting (17/4/2023) noted that the LHP scheme raised (LCHE182010) has been archived, which, with the demise of the Highway Rangers, leaves the problem unresolved. The meeting agreed to produce a paper with new evidence making the case for recommending that the scheme is resurrected. 17/07/2023: The agenda for the meeting on 24/07/2023 contains an item to discuss a proposal (in conjunction with associated issues regarding traffic through Ringtail Green).
2755500 (Essex Highways) | Open | N/a | Hoe Lane . Blocked Drain. Reported Essex Highways. 31.12.2021 | 31.12.21 | Clerk | 2023-04-17 | Blocked Culvert recorded. Repairs to be scheduled. 09/04/2023 Essex Highways website: Enquiry Reference: 2755500 Issue: highway drainage problems Street: Hoe Lane, Chelmsford Last updated: 09/02/22 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues. The H&TC meeting (17/4/2023) noted that the defect may have been fixed but the EH has not been updated.
2758382 (Essex Highways) | Open | N/a | Cherry Garden Road near number 62. Drain cover appears to be blocked. | 19.01.2022 | Clerk | 2023-04-17 | 09/04/2023 Essex Highways website: Blocked drain. To be considered for repairs. Issue: highway drainage problems Street: Cherry Garden Road, Chelmsford Last updated: 02/02/22 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues. The H&TC meeting (17/4/2023) noted that the defect may have been fixed but the EH has not been updated 17/07/2023: The Essex Highways website still states: Enquiry Reference: 2758382 Issue: highway drainage problems Street: Cherry Garden Road, Chelmsford Last updated: 02/02/22 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues. However, if the defect has been fixed, it is recommended that the item is closed.
2771004 (Essex Highways) | Open | N/a | Dead Ash Tree at corner of Lucks Lane , main road , Howe Street . Potential to close the road. Dead Ash tree. | 29.03.2022 | Clerk | 2023-07-17 | 09/04/2023 Essex Highways website: Enquiry Reference: 2771004 Issue: vegetation problems Street: Lucks Lane, Chelmsford Last updated: 23/03/23 Status: The issue was reported on a road that has been inspected and identified issues are recorded and actioned in line with our maintenance strategy. The H&TC meeting (17/4/2023) noted that the defect may have been fixed but the EH has not been updated. 17/07/2023: No longer shown on Essex Highways map. Recommend item is closed.
22/1177 (Jun 2022) | Open | N/a | Discuss a request for double yellow lines at the junction of Duffries Close and South Street – both ends. Resolution Move to the action tracker. Resolution Clerk to write to write to resident and confirm that we will continue to monitor | 13.06.222 | All | 2023-07-17 | The Parish Council will monitor the situation Continue to monitor 17/07/2023: Over a year since issue raised - unless further communications, recommend item is closed.
2788600 (Essex Highways) | Open | N/a | Church Lane. Ford End. Overgrown trees and hedges | 31.07.2022 | Clerk | 2023-07-17 | Potential to be done this week 09/04/2023 Essex Highways website: Enquiry Reference: 2788600 Issue: vegetation problems Street: Church Lane, Chelmsford Last updated: 23/03/23 Status: The issue was reported on a road that has been inspected and identified issues are recorded and actioned in line with our maintenance strategy. The H&TC meeting (17/4/2023) noted that the defect may have been fixed but the EH has not been updated. 17/07/2023: Reference 2788600 no longer shown on Essex Highways tracking map, although the map also shows this issue for Church Lane: Enquiry Reference: 2736721 Issue: vegetation problems Street: Church Lane, Chelmsford Last updated: 29/11/21 Status: We've carried out an initial assessment of this issue. We are getting more information to decide what action to take. However, given absence of original item and date of 2736721, recommend this item is closed.
22/1204 (Jul 2022) | Open | N/a | To consider the merit of requesting roadside parking restrictions adjacent to the Hatchfields entrance gate to Great Waltham Recreation Ground. The meeting noted the poor condition of some parts of the wooden entrance gate. The case for applying for parking restrictions was discussed. The relatively low volume of traffic and the need for residents’ parking spaces were mentioned. Resolution: Clerk to get a quote to replace the wooden entrance structure with the same style of structure. Resolution: Clerk to add advisory signs to the new structure reminding people exiting the park about the dangers of the road (inside) and asking drivers not to park directly adjacent to the gate (outside). Resolution: Any traffic restrictions to be delayed and the situation monitored. | 18.07.2022 | Clerk | 2023-07-17 | New fence being quoted on. Once the fence is added a notice to be attached. Continue to monitor. 17/07/2023: No further issues have been raised. Recommend this item is closed.
22/1133 (May 2022) | Open | N/a | To discuss actions to be taken at Ringtail Green following the extraordinary meeting at Ford End. A report was circulated with 4 proposals: 1. Install Ringtail Green Name plates with a drive slowly message. 2. Pursue Quiet Lane status for the lane – approximate cost £2,000. 3. Paint Slow road markings at either side of the bend. 4. Advisory road signs at either side of the bend e.g., maximum speed and chevrons. Resolution Item 1 – Clerk to contact the street naming team at Chelmsford City Council Resolution Clerk to raise LHP requests via Cllr Steel for items 3 and 4. | 23.05.2022 | Clerk & Highways Committee | 2023-07-17 | Item 1 - Has been sent in to the LHP - this has been validated and will now go into the queue for funding. Item 2 - Is already in the LHP queue. - this will not proceed as this did not get the support of the other members of the LHP.“Awaiting Funding” list – LCHE212014 Item 3 - LHP request to be raised by the Clerk - On item 3 – Painted ‘Slow’ road markings at either side of the bend I discussed this with the LHP Manager. He believes that to have SLOW written on the road, you also have to have a triangular warning sign as well. This would be determined as part of the design process. However, it would need to get through the LHP validation process first to go to the design stage, which is unlikely to happen given that the recorded speeds were an average 22mph, 85th percentile 27mph and there are no reports of accidents in that area . These measurements were made on the straight patch as specified by GWPC. However, if GWPC wish to fund this option, the LHP Manager estimated a cost between £5K and £10K. To refine the cost estimate would need the design work to be undertaken, which is usually about a third of the cost Item 4 - LHP request to be raised by the Clerk - Advisory road signs at either side of the bend, e.g. advisory max speed or right/left hand bend signs Advisory speed limits would have the same issues as Item 3 above – maybe more onerous scrutiny. The Price guide suggests that “Change of single speed limit which is uncontentious and where minimal infrastructure is required. £15,000” As this is not actually a change, it may not be as high as that. Again, to refine the estimate would need a funded design The H&TC meeting (17/4/2023) noted that it has only been possible to progress one proposal (LCHE222014). The meeting agreed to produce a paper with new evidence making the case for recommending that previously rejected schemes are reconsidered, especially taking account the impact of the archived scheme LCHE182010. 17/07/2023: The agenda for the meeting on 24/07/2023 contains an item to discuss a proposal (in conjunction with associated issues regarding traffic through Ringtail Green).
22/1212 (Aug 2022) | Open | N/a | 20’s Plenty campaign. The scope of the campaign locally is likely to be predicated by an outstanding update by Safer Essex Roads Partnership to its Functional Route Hierarchy Review, to be followed then by a revision of the Essex Speed Management Strategy. There is no published date for completion of these reviews. Resolution: The Clerk to write to Safer Essex Roads Partnership for an update on the timetable for completion. | 2022-08-15 | Clerk | 2023-04-17 | Clerk to update next meeting. The H&TC meeting (17/4/2023) noted that the Clerk will chase a response to the outstanding query.
22/1233 (Aug 2022) | Open | N/a | To report back to the Parish Council on the online seminar hosted by Essex association of Local Councils on - 20’s Plenty - attended by Cllrs Palmer and Martin. Resolution Fact finding from other councils and consideration of further engagement and action deferred to the Highway and Transport Committee. | 2022-08-15 | Cllrs. Palmer & Martin | 2023-04-09 | Cllrs. Palmer & Martin to update next meeting.
H&TC_9/22 7 | Open | N/a | Clerk to investigate if the Public Transport forum of Essex County Council plans to hold meetings where the Committee can be represented. | 2022-09-01 | Clerk | 2023-04-09 | Transport Meetings March 2023. Meeting agenda was passed to the parish transport representative 2nd Feb. Clerk to update next meeting.
H&TC_9/22 7 | Open | N/a | Cllr Palmer to prepare a draft of the role of the Parish Council Public Transport Representative. | 2022-09-01 | Cllr. Palmer | 2023-04-17 | Outstanding. The H&TC meeting (17/4/2023) noted that this remains outstanding. Carried forward to next meeting.
H&TC_9/22 7 | Closed | N/a | Cllr Gilbert to be the point of contact for all transport related matters. | 2022-09-01 | N/a | 2023-04-09 | N/a
H&TC_9/22 8 | Closed | N/a | Add a column to the tracker to indicate if items are capital items, maintenance, or ongoing issues. | 2022-09-01 | Clerk | 2023-04-09 | Completed.
H&TC_9/22 8 | Closed | N/a | Recommendation to the Parish Council to confirm its commitment to installing average speed cameras through Ford End. | 2022-09-01 | Cllr. Gilbert | 2023-04-09 | Completed. Agenda item and resolution at September monthly meeting: 22/1269 To consider and agree the Highways & Transport Committee's recommendation that the Council remains committed to the installation of average speed cameras through Ford End. Resolution The £10,000 earmarked reserve for the speed camera to be retained for another 12 months.
H&TC_9/22 8 | Closed | N/a | Recommend to the Parish Council that the Committee writes to Cllr Scott (ECC Highways Maintenance and Sustainable Transport cabinet member) and explain its initiation and to request a meeting to discuss how strategic projects will influence the situation in Ford End in particular, and the parish in general. | 2022-09-01 | Cllr. Gilbert | 2023-04-09 | Completed. Agenda item and resolution at September monthly meeting: To consider and agree the Highways & Transport Committee's recommendation that it contacts ECC's Highways, Maintenance and Sustainable Transport cabinet member to arrange a meeting to discuss how strategic ECC projects will influence road usage in the parish. Resolution This recommendation was agreed. The meeting took place in December 2022.
H&TC_9/22 8 | Closed | N/a | Discuss [Quiet Lane – Ringtail Green] with Cllr Scott at the proposed meeting. | 2022-09-01 | Cllr. Gilbert | 2023-04-09 | Completed. Discussed at meeting in December 2022.
H&TC_9/22 8 | Open | N/a | Consider adding [scheme to address reduction of pavement width in Ford End] to a list of potential LHP projects | 2022-09-01 | Clerk | 2023-04-09 | Clerk to update next meeting. 17/07/2023: The agenda for the meeting on 24/07/2023 contains an item to discuss a proposal (in conjunction with associated issues regarding traffic through Ringtail Green).
H&TC_9/22 8 | Closed | N/a | Perceived speeding in Howe Street. Close this item. | 2022-09-01 | N/a | 2023-04-09 | N/a
H&TC_9/22 8 | Closed | N/a | Cllr Martin to invite Ford End speed watch to the next meeting to raise the profile and discuss how the Committee can support speed watch initiatives. | 2022-09-01 | Cllr. Martin | 2023-04-09 | Completed. Update at February 2023 meeting.
H&TC_9/22 8 | Closed | N/a | South Street double yellow lines. Close this item. | 2022-09-01 | N/a | 2023-04-09 | N/a
H&TC_9/22 8 | Closed | N/a | Variety of Highways references for reported defects. Clerk to review the references and update with latest information from Essex Highways website. | 2022-09-01 | Clerk | 2023-04-09 | Completed.
H&TC_9/22 8 | Closed | N/a | The Committee has no objection and supports the introduction of the northern 40MPH buffer . Were there any technical reasons why the 40MPH zone does not begin earlier? | 2022-09-01 | N/a | 2023-04-09 | N/a. Scheme has been completed.
H&TC_9/22 8 | Closed | N/a | Clerk to write to the LHP and share the resolution of the committee [that the Committee has no objection and supports the introduction of the northern 40MPH buffer]. | 2022-09-01 | Clerk | 2023-04-09 | Completed. Scheme has now been completed.
H&TC_9/22 8 | Closed | N/a | Update the action tracker so that the Highways tab includes items on the current LHP project list. | 2022-09-01 | Clerk | 2023-04-09 | Completed.
H&TC_2/23 7 | Closed | N/a | Recommend that the Parish Council Supports the 20’s Plenty for Essex campaign and drafts a letter for Essex County Council to confirm its stance. | 2023-02-01 | Cllr. Gilbert | 2023-04-09 | Completed. At February 2023 monthly meeting: 22/1407 To agree the Highways and Transport Committee's recommendation that the Council supports the 20's Plenty in Essex campaign, and if agreed, for the Council to write to Essex County Council asking it to note the decision. Resolution: The recommendation was approved.
H&TC_2/23 10 | Closed | N/a | Continue to use the SID in the current format. | 2023-02-01 | N/a | 2023-04-09 | N/a
H&TC_2/23 10 | Open | N/a | Standing invitation to Committee meetings for the parish’s Speed Watch co-ordinators. | 2023-02-01 | Clerk | 2023-07-17 | Clerk to update next meeting. The H&TC meeting (17/4/2023) agreed that once all coordinators have been notified of the opportunity to attend meetings the item can be closed.
H&TC_2/23 15 | Closed | N/a | To consider future requests to the Local Highways Panel. Resolution: Items should be passed to the Clerk for discussion at a subsequent meeting. | 2023-02-01 | All | 2023-04-09 | N/a
H&TC_2/23 15 | Closed | N/a | To consider future requests to the Local Highways Panel. Resolution: List of potential schemes to be created for the next meeting. | 2023-02-01 | Clerk | 2023-04-17 | Clerk to update next meeting. 17/4/2023. The meeting noted that LHP schemes are now shown separately on the Committee’s action tracker. This action can therefore be closed.
H&TC_2/23 16 | Closed | N/a | Discuss the poor condition of the footway between Bennett’s Lane and Parsonage Lane on the B1008 on the North End side. Resolution: Add to the list of LHP requests for discussion. | 2023-02-01 | Clerk | 2023-04-17 | Clerk to update next meeting. The H&TC meeting (17/4/2023) noted that since the issue was originally raised some work has been effected. It was confirmed that any outstanding/necessary work should be added to the new LHP requests list for consideration. On that basis this action can be closed.
H&TC_2/23 17 | Open | N/a | To consider the installation of deer signs around the village due to the increased levels of deer. Resolution: Add to the list of LHP requests for discussion should further information be forthcoming. | 2023-02-01 | Cllr. Lockwood | 2023-04-17 | Update required. H&TC meeting 17/04/2023. Resolution: Contact Cllr. Lockwood for details or we will look to archive.
H&TC_2/23 18 | Closed | N/a | To agree whether to recommend that the council responds to the Chelmer Village Park and Ride expansion – Public online consultation survey. Resolution: The Committee recommends no action on this consultation. | 2023-02-01 | N/a | 2023-04-09 | N/a
H&TC_4/23 6 | Open | N/a | Chair and Clerk to draft an e-mail to Essex Highways to confirm the status of defects noted on action tracker (as some seem to have been resolved without the EH database having been updated). | 2023-04-01 | Cllr Gilbert & Clerk | 2023-04-17
H&TC_4/23 6 | Open | N/a | Clerk to request details of all defects shown as outstanding on the Essex Highways website that are in the Parish of Great Waltham. | 2023-04-01 | Clerk | 2023-04-17
H&TC_4/23 6 | Open | N/a | Clerk to establish the existence (or not) of Playground signage for the Great Waltham Recreation Ground at both entrances. | 2023-04-01 | Clerk | 2023-04-17
H&TC_4/23 7 | Open | N/a | Remove the individual defects reported by members of the Committee from the tracker. | 2023-04-01 | Clerk | 2023-07-17 | Recommend close this item as only existing individual defects being monitored (and being recommended for closure) and no new ones being added.
H&TC_4/23 9 | Open | N/a | To consider and make recommendations for the Council’s strategy in relation to enforcement of permitted uses of the Blossom Way public car park spaces. Resolution: Recommend to the Council that the purchase and installation of replacement permitted parking signs at the Blossom Way car park – (laminated signs). | 2023-04-01 | Cllr Gilbert | 2023-07-17 | 17/07/2023: Signs have been prepared and are awaiting installation.
H&TC_4/23 11 | Open | N/a | To recommend that the Council lobbies the relevant authorities/agencies to change the A120 backup diversionary route from the B1008 to the B1256. Resolution: Recommend to the council that it lobbies the relevant authorities/agencies to change the A120 backup diversionary route from the B1008 to the B1256. | 2023-04-01 | Cllr Gilbert | 2023-07-17 | 17/07/2023: Cllr Gilbert wrote to National Highways on 22/05/2023 to obtain more information on impact of use of B1008 as a diversionary route during the period of the upgrade work to the A120. Update on response to be provided at meeting on 24/07/2023.
H&TC_4/23 12 | Open | N/a | To recommend that the Council lobbies for measures to ensure the B1008 is not used as a preferred route once the NE by-pass is completed (given that it would remain the shortest and fastest route between the A120 at Gt. Dunmow and the new by-pass junction on the A131 at Gt. Leighs). Resolution: Recommend to the council that it lobbies for measures to ensure the B1008 is not used as a preferred route once the NE by-pass is completed. | 2023-04-01 | Cllr Gilbert | 2023-04-17
H&TC_4/23 13 | Open | N/a | To recommend that the Council lobbies for the reinstatement of the signage at Sheepcotes roundabout, which directs traffic to the A131/A120, so as to reduce use of the B1008. Resolution: Recommend to the council that it lobbies for the reinstatement of signage at Sheepcotes roundabout which directs traffic to the A131/A120. | 2023-04-01 | Cllr Gilbert | 2023-04-17
H&TC_4/23 15 | Open | N/a | Discuss drainage and surface issues at Church Lane, Ford End and determine the appropriate course of action. Resolution Clerk to write to Essex Highways and raise concerns about the demolished drain and request it to be moved back onto the verge. | 2023-04-01 | Clerk | 2023-04-17
LHP Schemes | Open
| Open | Status | Scheme | Description | Scheme stage | Budget | Comments
LCHE182009 | Open | Funded | B1008 Ford End - Kerbing improvements | Height of kerbs through Village | Total scheme | 48000 | Raised kerbs at six bus stops through village as first stage 17/04/2023. In progress, completion imminent (1 kerb still to be completed). 17/07/2023: Scheme completed, item can be closed
LCHE203002 | Open | Funded | Barrack Lane j/w Cherry Garden Road, Great Waltham - Footway Improvements | Footway improvements | Design | 6500 | Design team advised footway may need regrading and could need land acquisition. Due to change in scheme scope agreed at June 2022 panel to make this a Design Only as first stage 17/04/2023. Design agreed. Works delayed due to funding prioritisations, but completion expected in 2023/24. 17/07/2023: Works schemed for 2023/24 - yet to be commenced.
LCHE202036 | Open | Funded | Littley Park Cottages, Littley Park Lane, Hartford End - Road markings | SLOW road markings for existing bend warning signs | Total scheme | 10800 | Signage improvements and vegetation clearance, possible SLOW road marking 17/04/2023. On Hold. Works not undertaken. Agreed to chase reason for delay. 17/07/2023: Works schemed for 2023/24 - yet to be commenced.
LCHE182010 | Open | Awaiting Funding | B1008 Ford End - Footway improvements | Width of footway through Village | Validation | N/A | Highway Rangers to routinely side existing footways to fully open up available footway width 17/04/2023. This has been archived. Agreed that paper with new evidence should be produced, making the case for recommending that previously rejected scheme is reconsidered. 17/07/2023: The agenda for the meeting on 24/07/2023 contains an item to discuss a proposal (in conjunction with associated issues regarding traffic through Ringtail Green).
LCHE192028 | Open | Awaiting Funding | Ford End - Average speed cameras | Average speed cameras | Implementation | 60460 | Scheme was design only in 2020/21, new revised costing £120,920. Suggestion previously was Match Funding from Parish Council and LHP, which would now require £60,460 from each source 17/04/2023. Awaiting match funding. Parish Council reviewing options. Await outcome of discussion at May monthly meeting. 17/07/2023: GWPC monthly meeting 22/5 agreed that PC should secure a loan to cover 50% of costs. Cllr. Lee Scott has subsequently confirmed the PC needs to show it has raised the loan and then 'the next step would be for the Local Highways Panel to make a funding recommendation towards the scheme'. The PC is ging through the process of submitting an application for a loan from the Public Works Loan Board.
LCHE212013 | Open | Archived | Ringtail Green, Great Waltham - Traffic management improvements | Request for speed reduction 60mph to 40mph and Quiet Lane status | Validation | TBC | Validation - 30mph - Northeast bound 21.8mph & Southwest bound 22.1mph. Very good speed compliance. Parish would still like consideration of Quiet Lane status, 17/04/2023. This has been archived. Agreed that paper with new evidence should be produced, making the case for recommending that previously rejected scheme(s) are reconsidered. Resolution: Case to be made for LCHE212013 to be reinstated. 17/07/2023: The agenda for the meeting on 24/07/2023 contains an item to discuss a proposal (in conjunction with associated issues regarding traffic through Ringtail Green).
LCHE222014 | Open | Awaiting Funding | Ringtail Green, Great Waltham - Gateway signs | Signage to identify the hamlet | Validation | TBC | Awaiting highway boundary information 17/04/2023. Works delayed due to funding prioritisations, but completion expected in 2023/24.
LCHE223011 | Open | Awaiting Funding | Great Waltham Primary School, South Street, Great Waltham - Signage improvements | Sign to show School not School Crossing Patrol | Total scheme | 6500 | Validation - Recommends changing Patrol sign to School, need to check sign/pole as could be sticker or may need new pole/sign 17/04/2023. Low-cost scheme. Potential stickers rather than new signs. Funding decision pending.