## Log
GWPC Playgrounds Maintenance Log |  |  | 2023-08-30
Site | Source | Item | Finding | Risk Level | Date Added | Action/ Monitor | Owner | Completed (Y/N/Ongoing) | Date Completed | Comments
Great Waltham | PIC Annual Report | Site General | Finding 1 There are trip hazards at the edges of the surface - Reinstate surrounding surface levels to remove the trip points | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Site General | Finding 2 There is algae, silt or moss growth on the surface resulting in slippery conditions - Clean and treat appropriately | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Site General | Finding 3 The wetpour is crumbing in areas - Monitor for any further deterioration and repair as required | 9 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing
Great Waltham | PIC Annual Report | Site General | Finding 4 There are gaps opening between the surfacing and the edging surround or between the joints in the surfacing - Monitor for any further deterioration and repair as required | 9 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing
Great Waltham | PIC Annual Report | Site General | Finding 5 There are significant gaps (over 30mm) between the surface and the edging or between the joints in the surface; these are large enough for a small foot to enter - Repair surfacing | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Site General | Finding 6 The surface is lifting at the edges and creating trip points - Repair perimeter of surfacing to remove trip points | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Site General | Finding 7 There is algae, silt or moss growth on the surface resulting in slippery conditions - Clean and treat appropriately | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Site General | Finding 8 There is weed / vegetation growth on, between, or around the edges of the surfacing - Remove weed / vegetation growth | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Gate - Self Closing | Finding 1 The paintwork on this item has been damaged or worn exposing the metal underneath which is rusting - Treat any rusting components and repaint | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Gate - Self Closing | Finding 2 The surface has eroded and the foundations are exposed - Reinstate surrounding surfaces to cover the foundations | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Gate - Self Closing | Finding 3 There are areas or parts of the timber on the structure that have rotted - Replace all affected timbers | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Gate - Self Closing | Finding 4 The gate is unstable - Repair or replace as required | 9 - Low Risk | 2023-07-07 | A | JB | N |  | Budget to replace gate
Great Waltham | PIC Annual Report | Gate - Self Closing | Finding 5 There are openings that are less than 12mm that could trap or crush fingers - Provide a 12mm gap throughout full range of motion at both sides of gate | 9 - Low Risk | 2023-07-07 | A | JB | N |  | Budget to replace gate
Great Waltham | PIC Annual Report | Gate - Self Closing | Finding 6 The gate is not operating correctly - Take effective action to ensure the gate closes between 4 and 8 seconds | 9 - Low Risk | 2023-07-07 | A | JB | N |  | Budget to replace gate
Great Waltham | PIC Annual Report | Fence | Finding 1 There is some damage to the fence sections - Monitor for any further deterioration and repair as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing |  | Budget to replace gate
Great Waltham | PIC Annual Report | Fence | Finding 2 The surface has eroded and the foundations are exposed - Reinstate surrounding surfaces to cover the foundations | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Sign | Finding 1 It is recommended that signage, with information including the site address, contact information for maintenance issues and emergency contact details are provided for the facility - Provide in accordance with the recommendations | 5 - Very Low Risk | 2023-07-07 | A | Clerk | Y | 23.08.2023 | Recommend approach/policy.
Great Waltham | PIC Annual Report | Gate - Maintenance | Finding 1 The surface has eroded and the foundations are exposed - Reinstate surrounding surfaces to cover the foundations | 8 - Low Risk | 2023-07-07 | A | JB | N |  | Budget to replace gate
Great Waltham | PIC Annual Report | Gate - Maintenance | Finding 2 There is no padlock on the maintenance gate - Provide a padlock to secure the gate | 8 - Low Risk | 2023-07-07 | A | JB | Y | 2023-07-01 | Budget to replace gate
Great Waltham | PIC Annual Report | Gate - Maintenance | Finding 3 There are openings that are less than 12mm that could trap or crush fingers - Provide a 12mm gap throughout full range of motion at both sides of gate | 8 - Low Risk | 2023-07-07 | A | JB | N |  | Budget to replace gate
Great Waltham | PIC Annual Report | Gate - Maintenance | Finding 4 There are areas or parts of the timber fence that have rotted - Replace all affected timbers | 8 - Low Risk | 2023-07-07 | A | Working Group | N |  | Budget to replace gate
Great Waltham | PIC Annual Report | Gate - Maintenance | Finding 5 The gate can be lifted off the hinges - Secure | 8 - Low Risk | 2023-07-07 | A | Working Group | N |  | Budget to replace gate
Great Waltham | PIC Annual Report | Gate - Maintenance | Finding 6 There are projecting bolt thread(s) present - Remove excess thread length and deburr or provide cap | 8 - Low Risk | 2023-07-07 | A | JB | N |  | Budget to replace gate
Great Waltham | PIC Annual Report | Bench | Finding 1 The item is loose in its foundations - Reinstall item to secure | 8 - Low Risk | 2023-07-07 | A | JB | N |  | Working Group to consider long-term solution - moving bench to more suitable location.
Great Waltham | PIC Annual Report | Bench | Finding 2 The paintwork on this item has been damaged or worn exposing the metal underneath which is rusting - Treat any rusting components and repaint | 8 - Low Risk | 2023-07-07 | A | JB | N |  | Working Group to consider long-term solution - moving bench to more suitable location.
Great Waltham | PIC Annual Report | Bench | Finding 3 The surface has eroded and the foundations are exposed - Reinstate surrounding surfaces to cover the foundations | 8 - Low Risk | 2023-07-07 | A | JB | N |  | Working Group to consider long-term solution - moving bench to more suitable location.
Great Waltham | PIC Annual Report | Bench | Finding 4 There are projecting bolt thread(s) present - Remove excess thread length and deburr or provide cap | 8 - Low Risk | 2023-07-07 | A | JB | N |  | caps purchased
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 1 There is moderate damage to the surface - Repair the damaged areas of surfacing | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 2 The surfacing dimensions are short and do not meet with the requirements of the current applicable standard - Monitor - no remedial action recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 3 There is some graffiti present - Remove the graffiti | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 4 There is some damage to the item - Monitor for any further deterioration and repair as required | 8 - Low Risk | 2023-07-07 | A | Playground Inspector | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 5 A number of fixing(s) have worked loose - Secure all loose fixings | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 6 There is some evidence of rot in the timber - Monitor for any further deterioration and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 7 The timber has a number of splits/shakes or air cracks and this may affect the stability or allow water ingress which will accelerate the rotting process - Monitor to ensure the splits do not cross through fixing points of the structure and/or cause any instability | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 8 The item fails to meet the requirements of BS EN 1176 Part 1 4.2.7.2 head and neck entrapment in the ladder - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 9 The paintwork on this item has been damaged or worn exposing the metal underneath which is rusting - Treat any rusting components and repaint | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 10 There is some damage to the roof sections - Repair as required | 8 - Low Risk | 2023-07-07 | A | JB | N |  | Working Group to consider longer term solution - remove roof?
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 11 There is/are finger entrapment/s in the platform and the item fails to meet the requirements of BS EN 1176 Part 1 4.2.7.6 Entrapment of fingers - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 1 The fixings or components for this item were in excess of 2.5m above the standing surface and could not be fully accessed by the inspector. We have completed a visual inspection of the fixings from ground level but a maintenance inspection should be undertaken to assess the condition, security and wear of the components at intervals in accordance with the manufacturers recommendations. - Inspect in accordance with the manufacturers recommendations | 8 - Low Risk | 2023-07-07 | A | JB | N |  | Consider arrangements needed to make full inspection. Working Group activity?
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 2 The seats are too close to each other as defined in BS EN 1176 Part 2; this is a low risk failure and no remedial action is required - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 3 The seats are too close to the frame as defined in BS EN 1176 Part 2; this is a low risk failure and no remedial action is required - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 4 The surfacing width under the seat/s is / are less than 875mm when measured from the centre of the seat outwards, and fails the requirements of BS EN 1176 Part 2 - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 5 The chain links are worn in excess of 40% and require renewing - Replace worn chains | 8 - Low Risk | 2023-07-07 | A | JB/Clerk | N |  | We need to order new chains.
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 6 The bushes are showing signs of wear - Monitor for any further deterioration and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 7 The shackles are worn in excess of 40% and require renewing - Replace worn shackles | 8 - Low Risk | 2023-07-07 | A | JB/Clerk | N |  | We need to order new shackles.
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 8 The chain openings are in excess of 8.6mm and do not meet the recommendations of BS EN 1176 Part 1 - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 9 The connecting links are in excess of 8.6mm and less than 12mm and fail the requirements of BS EN 1176 Part 1; clause 4.2.13, Chains - Monitor use and replace with compliant links at the next maintenance cycle | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 10 The swing seat connectors have some wear present - Monitor for further deterioration and replace when 40% worn | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 11 The connecting lugs are showing signs of wear - Monitor for any further deterioration and repair as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 1 There is some strimmer / machinery damage apparent on the posts, this can penetrate the preservative applied to the timber and accelerate the rotting process - Monitor for any deterioration (rot) and replace as required | 10 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 2 The area around the item has eroded and may become slippery - Reinstate eroded area | 10 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 3 There is insufficient guarding on the steps leading up to the platform that exceeds 1m in height which contravenes the requirements on BS EN 1176 Part 1 - Monitor - No remedial work recommended | 10 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 4 The unit is easily accessible and should have the appropriate barriers installed to meet the requirements of BS EN 1176 Part 1 as the height of the unit exceeds 600mm - Monitor - No remedial work recommended | 10 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 5 The item fails to meet the requirements of BS EN 1176 Part 1 4.2.7.2 head and neck entrapment in the barriers and/or steps - Monitor - No remedial work recommended | 10 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 6 The paintwork on this item has been damaged or worn exposing the metal underneath which is rusting - Treat any rusting components and repaint | 10 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 7 The timber has a number of splits/shakes or air cracks and this may affect the stability or allow water ingress which will accelerate the rotting process - Monitor to ensure the splits do not cross through fixing points of the structure and/or cause any instability | 10 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 8 The surface has eroded and the foundations are exposed - Reinstate surrounding surfaces to cover the foundations | 10 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 9 The ramp supports are not secure - Secure | 10 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 10 There is some evidence of rot in the timber - Monitor for any further deterioration and replace as required | 10 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 11 The ropes/nets are worn/damaged in places - Monitor for any further deterioration and repair or replace as required | 10 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 12 A number of fixing(s) have worked loose - Secure all loose fixings | 10 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 13 Parts of the timber are rough or splintered - Remove all rough or sharp edges | 10 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 14 There are areas or parts of the timber climbing wall that have rotted - Replace all affected timbers | 10 - Low Risk | 2023-07-07 | A | Working Group | N |  | Working Group to consider policy to replace timber structures (or part).
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 15 There are areas or parts of the timber on the structure that have rotted - Replace all affected timbers | 10 - Low Risk | 2023-07-07 | A | Working Group | N |  | Working Group to consider policy to replace timber structures (or part).
Great Waltham | PIC Annual Report | Multi Play (Junior) | Finding 16 There are areas or parts of the timber on the posts that have rotted - Replace all affected timbers | 10 - Low Risk | 2023-07-07 | A | Working Group | N |  | Working Group to consider policy to replace timber structures (or part).
Great Waltham | PIC Annual Report | Embankment Slide | Finding 1 There are a number of dents in the slide surface - Monitor for any further deterioration and repair as required | 9 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Embankment Slide | Finding 2 The side of the slide is damaged - Monitor for any further deterioration and repair as required | 9 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Embankment Slide | Finding 3 The surface has eroded and the foundations are exposed - Reinstate surrounding surfaces to cover the foundations | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Embankment Slide | Finding 4 The timber edge forms a hard object within the free space of the equipment in contravention of the requirements of BS EN 1176 Part 1 - Monitor - No remedial work recommended | 9 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Embankment Slide | Finding 5 The paint is flaking off the metalwork - Rub down and repaint | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Embankment Slide | Finding 6 The slide start section incline is not in the direction of travel; it should slope towards the direction of the sliding surface to meet the requirements of BS EN 1176 Part 3 - Monitor - No remedial work recommended | 9 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Embankment Slide | Finding 7 The surface has subsided in some areas - Monitor for any further deterioration and repair as required | 9 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Embankment Slide | Finding 8 The area around the item has eroded and may become slippery - Reinstate eroded area | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Embankment Slide | Finding 9 There are trip hazards at the edges of the surface - Reinstate surrounding surface levels to remove the trip points | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Embankment Slide | Finding 10 There is some minor damage to the surface - Monitor for any further deterioration and repair as required | 9 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Embankment Slide | Finding 11 There are holes within the slide run out section that objects may become lodged - Repair or replace the slide | 9 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Picnic Table | Finding 1 There is some evidence of fire damage to the item - Monitor for any further deterioration and repair as required | 4 - Very Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay Swing | Finding 1 The surfacing width under the seat/s is / are less than 875mm when measured from the centre of the seat outwards, and fails the requirements of BS EN 1176 Part 2 - Monitor - No remedial work recommended | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay Swing | Finding 2 There is some minor damage to the surface - Monitor for any further deterioration and repair as required | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay Swing | Finding 3 There is some wear to the shackles - Monitor for any further deterioration and replace when 40% worn | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay Swing | Finding 4 The tree canopy overhangs the equipment and is less than 2.0m away - Lift tree canopy to ensure a minimum clearance of 2.0m from the equipment | 6 - Low Risk | 2023-07-07 | A | JB | Y | 2023-07-01 | CUT BACK AND STUMP REMOVED
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 1 The safety surface around the area is beginning to wear - Monitor for any further deterioration and repair as required | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 2 The seats are too close to the frame as defined in BS EN 1176 Part 2; this is a low risk failure and no remedial action is required - Monitor - No remedial work recommended | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 3 The surfacing width under the seat/s is / are less than 875mm when measured from the centre of the seat outwards, and fails the requirements of BS EN 1176 Part 2 - Monitor - No remedial work recommended | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 4 The seats are too close to each other as defined in BS EN 1176 Part 2; this is a low risk failure and no remedial action is required - Monitor - No remedial work recommended | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 5 There is some notable evidence of chain wear - Monitor for any further deterioration and replace when 40% worn | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 6 There is some wear to the shackles - Monitor for any further deterioration and replace when 40% worn | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 7 The bushes are showing signs of wear - Monitor for any further deterioration and replace as required | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 8 The chain openings are in excess of 8.6mm and do not meet the recommendations of BS EN 1176 Part 1 - Monitor - No remedial work recommended | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 9 The surface has subsided in some areas - Monitor for any further deterioration and repair as required | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 10 The swing seat frames are corroding - Monitor for any further deterioration and replace as required | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 11 The split pins are missing from the shackles - Insert split pins to secure the shackles | 6 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 12 The paint is flaking off the metalwork - Rub down and repaint | 6 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Misc Springer | Finding 1 The Handgrips/Footrests rotate and may cause an unexpected movement for the user - Secure Handgrips/Footrests to prevent rotation. | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Spring Bike | Finding 1 The area around the item has eroded and may become slippery - Reinstate eroded area | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | See Saw | Finding 1 The paint is flaking off the metalwork - Rub down and repaint | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | See Saw | Finding 2 The item fails to meet the requirements of BS EN 1176 Part 1 4.2.7.2 for head and neck entrapment in the handles - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | See Saw | Finding 3 There is no gaiter protection for accessible moving parts (possible shear trap) as recommended in BS EN 1176 Part 1; 4.2.6 Moving Parts - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | See Saw | Finding 4 The paintwork on this item has been damaged or worn exposing the metal underneath which is rusting - Treat any rusting components and repaint | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | See Saw | Finding 5 There is surface corrosion present on the item - Consider treating the item | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | See Saw | Finding 6 The fixings have corroded excessively - Replace all corroded fixings | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | See Saw | Finding 7 There is moderate damage to the surface - Repair the damaged areas of surfacing | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Activity Trail | Finding 1 The area around the item has eroded and may become slippery - Reinstate eroded area | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Activity Trail | Finding 2 The timber has a number of splits/shakes or air cracks and this may affect the stability or allow water ingress which will accelerate the rotting process - Monitor to ensure the splits do not cross through fixing points of the structure and/or cause any instability | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Activity Trail | Finding 3 The ropes/nets are worn/damaged in places - Monitor for any further deterioration and repair or replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Activity Trail | Finding 4 The connecting links are in excess of 8.6mm and less than 12mm and fail the requirements of BS EN 1176 Part 1; clause 4.2.13, Chains - Monitor use and replace with compliant links at the next maintenance cycle | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Activity Trail | Finding 5 The item is slightly loose in its foundations - Monitor for any further deterioration and repair as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Activity Trail | Finding 6 There is some evidence of rot in the timber crossbeam - Monitor for any further deterioration and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Activity Trail | Finding 7 There is algae or moss on the surface of the equipment - Clean and treat appropriately | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Log Climber | Finding 1 There is algae or moss on the surface of the equipment - Clean and treat appropriately | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Log Climber | Finding 2 The timber has a number of splits/shakes or air cracks and this may affect the stability or allow water ingress which will accelerate the rotting process - Monitor to ensure the splits do not cross through fixing points of the structure and/or cause any instability | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Log Climber | Finding 3 There is some strimmer / machinery damage apparent on the posts, this can penetrate the preservative applied to the timber and accelerate the rotting process - Monitor for any deterioration (rot) and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Log Climber | Finding 4 The ropes/nets are worn/damaged in places - Monitor for any further deterioration and repair or replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Log Climber | Finding 5 Parts of the timber are rough or splintered - Remove all rough or sharp edges | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Train | Finding 1 The wheels are becoming loose - Secure as required | 10 - Low Risk | 2023-07-07 | A | JB | Y | JU;Y 23 | WHEELS REMOVED AND REBUILT
Great Waltham | PIC Annual Report | Train | Finding 2 The timber stain is in poor condition - Prepare all affected parts and re-stain with an appropriate preservative | 10 - Low Risk | 2023-07-07 | A | JB | Y | 01.07.2023
Great Waltham | PIC Annual Report | Train | Finding 3 There are areas or parts of the timber on the structure that have rotted - Replace all affected timbers | 10 - Low Risk | 2023-07-07 | A | Working Group | y | 01.07.2023 | Working Group to consider policy to replace timber structures (or part).
Great Waltham | PIC Annual Report | Train | Finding 4 There are areas or parts of the timber on the structure that have rotted - Replace all affected timbers | 10 - Low Risk | 2023-07-07 | A | Working Group | y | 01.07.2023 | Working Group to consider policy to replace timber structures (or part).
Great Waltham | PIC Annual Report | Train | Finding 5 There is some evidence of rot in the timber - Monitor for any further deterioration and replace as required | 10 - Low Risk | 2023-07-07 | A | Working Group | y | 01.07.2023 | Working Group to consider policy to replace timber structures (or part).
Great Waltham | PIC Annual Report | Train | Finding 6 There are areas or parts of the timber platform that have rotted - Replace all affected timbers | 10 - Low Risk | 2023-07-07 | A | Working Group | y | 01.07.2023 | Working Group to consider policy to replace timber structures (or part).
Great Waltham | PIC Annual Report | Train | Finding 7 There is/are bolt cap covers missing or damaged on the item - Replace missing or damaged bolt cap covers | 10 - Low Risk | 2023-07-07 | A | JB | y | 01.07.2023
Great Waltham | PIC Annual Report | Cone Climber | Finding 1 The height to the underside of the roundabout ring is less than 400mm and fails the requirements of BS EN 1176 Part 5 - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Cone Climber | Finding 2 The grass mats are silted up, the soil is compacted and the area will become very slippery when the soil is wet. - Reinstate as required | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Cone Climber | Finding 3 There are gaps opening between the grass mat tiles - Provide additional ties or secure / reinstate surface | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Cone Climber | Finding 4 Cable ties have been used on the item and there are sharp projecting ends - Remove if not required or replace with a more appropriate alternative fixing method if used as a fixing | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Cone Climber | Finding 5 The bearing is showing signs of wear - Monitor for any further deterioration and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Table Tennis | Finding 1 The area around the item has eroded and may become slippery - Reinstate eroded area | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Table Tennis | Finding 2 There is some damage to the table - Monitor for any further deterioration and repair as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Great Waltham | PIC Annual Report | Shelter | Finding 1 The surface has eroded and there are trip hazards at the edges of the surface - Reinstate surrounding surface levels to remove the trip points | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Shelter | Finding 2 There is damage to the surface - Repair the damaged areas of surfacing | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Shelter | Finding 3 There is some graffiti present - Remove the graffiti | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Shelter | Finding 4 The paintwork on this item has been damaged or worn exposing the metal underneath which is rusting - Treat any rusting components and repaint | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Shelter | Finding 5 There is/are bolt cap covers missing or damaged on the item - Replace missing or damaged bolt cap covers | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Goalmouth and Basketball Post | Finding 1 A clearly visible facility sign should be provided in a prominent position with the wording as detailed BS EN 15312- the equipment is not intended for children less than 3 years old- the warning - Do not climb on the framework or nets- the warning - Do not hang on the ring (if provided)- the warning - Do not wear rings or other jewellery- name and telephone number of the administrator- number to call in case of accident - Provide signage to BS EN 15312 | 8 - Low Risk | 2023-07-07 | A | Clerk | N |  | Signs Purchased
Great Waltham | PIC Annual Report | Goalmouth and Basketball Post | Finding 2 There are trip hazards at the edges of the surface - Reinstate surrounding surface levels to remove the trip points | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Goalmouth and Basketball Post | Finding 3 The area around the item has eroded and may become slippery - Reinstate eroded area | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Goalmouth and Basketball Post | Finding 4 The bitumen surface is worn or damaged - Repair the bitumen to provide a uniform surface | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Basketball Post | Finding 1 The basketball net has been damaged - Replace damaged item | 10 - Low Risk | 2023-07-07 | A | JB | Y | 2023-07-01 | NEW NET ADDED AND TIE WRAPED
Great Waltham | PIC Annual Report | Basketball Post | Finding 2 There is some graffiti present - Remove the graffiti | 10 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Basketball Post | Finding 3 The item has missing backboard - Consider replacing missing components | 10 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Football Goal | Finding 1 The paintwork on this item has been damaged or worn exposing the metal underneath which is rusting - Treat any rusting components and repaint | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Great Waltham | PIC Annual Report | Football Goal | Finding 2 Cable ties have been used on the item and there are sharp projecting ends - Remove if not required or replace with a more appropriate alternative fixing method if used as a fixing | 8 - Low Risk | 2023-07-07 | A | JB | Y | 2023-07-01 | CUT BACK TO JOINT
Great Waltham | PIC Annual Report | Football Goal | Finding 3 There are projecting bolt thread(s) present - Remove excess thread length and deburr or provide cap | 8 - Low Risk | 2023-07-07 | A | JB | N
Great Waltham | PIC Annual Report | Football Goal | Finding 4 The bracket is missing - Replace missing components | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Great Waltham | PIC Annual Report | Football Goal | Finding 5 The net brackets can be removed - Secure | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Great Waltham | PIC Annual Report | Football Goal | Finding 6 NB: We have undertaken a maintenance inspection only of the football goal(s); full load testing falls outside the scope of our inspection. - Implement load testing as required | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Great Waltham | PIC Annual Report | Litter Bin | Finding 1 The liner of the litter bin is not secured - Ensure the lid/door is kept locked and the liner secured | 6 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Site General | Finding 1 It is recommended that signage, with information including the site address, contact information for maintenance issues and emergency contact details are provided for the facility - Provide in accordance with the recommendations | 5 - Very Low Risk | 2023-07-07 | A | Clerk | N |  | Recommend approach/policy.
Ford End | PIC Annual Report | Fence - Chainlink | Finding 1 There is some damage to the fence sections - Monitor for any further deterioration and repair as required | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | Bench | Finding 1 The grass tile is lifting at the edges and creating trip points - Repair perimeter of surfacing to remove trip points | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Litter Bin | Finding 1 The litter bin is full - Empty and review the collection routine | 6 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Litter Bin | Finding 2 There is some evidence of fire damage to the item - Monitor for any further deterioration and repair as required | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | Litter Bin | Finding 3 The liner of the litter bin is not secured - Ensure the lid/door is kept locked and the liner secured | 6 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Litter Bin | Finding 4 There are post / end caps missing from the item - Replace missing post caps | 6 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Litter Bin | Finding 5 The adjacent foliage is overhanging the litter bin - Cut back and maintain | 6 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Bench | Finding 1 This item is satisfactory - no work required - | 4 - Very Low Risk | 2023-07-07 | A | N/a | Y | 2023-07-07
Ford End | PIC Annual Report | Net Climber | Finding 1 The grass mats are silted up, the soil is compacted and the area will become very slippery when the soil is wet. - Reinstate as required | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Net Climber | Finding 2 There are gaps opening between the grass mat tiles - Provide additional ties or secure / reinstate surface | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Net Climber | Finding 3 The ropes/nets are worn/damaged in places - Monitor for any further deterioration and repair or replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | Net Climber | Finding 4 The height to the underside of the roundabout ring is less than 400mm and fails the requirements of BS EN 1176 Part 5 - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | Net Climber | Finding 5 There is some damage to the surface - Repair the damaged areas of surfacing | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Activity Trail | Finding 1 There is some notable evidence of chain wear - Monitor for any further deterioration and replace when 40% worn | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | Activity Trail | Finding 2 The ropes/nets are worn/damaged in places - Monitor for any further deterioration and repair or replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | Activity Trail | Finding 3 The area around the item has eroded and may become slippery - Reinstate eroded area | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Activity Trail | Finding 4 The step between the items is quite large and users may not be able to complete the step without touching ground, the items could therefore be considered to be within the falling space of each other, however the intention of the play activity continuity is easily apparent and foreseeable to the user - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | Activity Trail | Finding 5 The ropes on this item have been taped and we are unable to fully assess the condition of the rope, ensure no wire strands are broken beneath the tape - Repair or replace as required | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Activity Trail | Finding 6 The timber has a number of splits/shakes or air cracks and this may affect the stability or allow water ingress which will accelerate the rotting process - Monitor to ensure the splits do not cross through fixing points of the structure and/or cause any instability | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | Activity Trail | Finding 7 There is algae or moss on the surface of the equipment - Clean and treat appropriately | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Activity Trail | Finding 8 The inspector has some concerns about the internal condition of the timber and was unable to verify the structural integrity without further testing. We recommend a Resi-PD survey to establish the condition of the timber at it's core. - Contact the Play Inspection Company office for further information | 8 - Low Risk | 2023-07-07 | A | Clerk | N |  | Recommend approach/policy.
Ford End | PIC Annual Report | Activity Trail | Finding 9 There is/are inserts missing - Replace missing inserts | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Activity Trail | Finding 10 The post end cap is loose - Secure | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 1 There are trip hazards at the edges of the surface - Reinstate surrounding surface levels to remove the trip points | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 2 The safety surface around the area is beginning to wear - Monitor for any further deterioration and repair as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 3 The bushes are showing signs of wear - Monitor for any further deterioration and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 4 There is some wear to the shackles - Monitor for any further deterioration and replace when 40% worn | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 5 There is some notable evidence of chain wear - Monitor for any further deterioration and replace when 40% worn | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 6 The chain openings are in excess of 8.6mm and do not meet the recommendations of BS EN 1176 Part 1 - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 7 The seat has minor damage or wear - Monitor for any further deterioration and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 8 There is tree debris on the surface - Remove and maintain | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 9 The seats are too close to each other as defined in BS EN 1176 Part 2; this is a low risk failure and no remedial action is required - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Cradle) | Finding 10 There is excrement on the seats - Clean and maintain area | 8 - Low Risk | 2023-07-07 | A | JB | N |  | Also need to consider possible long-term solution, i.e. bird deterrent.
Ford End | PIC Annual Report | See Saw | Finding 1 The paint has worn off the metalwork - Rub down and repaint | 6 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | See Saw | Finding 2 There are gaps opening between the grass mat tiles - Provide additional ties or secure / reinstate surface | 6 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | See Saw | Finding 3 There is weed / vegetation growth on, between, or around the edges of the surfacing - Remove weed / vegetation growth | 6 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 1 The grass mats are silted up and the soil is compacted; this may have an effect on the impact absorbing properties of the surface - Consider HIC testing impact absorbing properties to ensure the correct surface qualities are maintained for the equipment and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 2 Fixing Pins have been installed in the impact areas of the grass mats - Remove pins from impact areas | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 3 There are gaps opening between the grass mat tiles - Provide additional ties or secure / reinstate surface | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 4 There is some notable evidence of chain wear - Monitor for any further deterioration and replace when 40% worn | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 5 The chain openings are in excess of 8.6mm and do not meet the recommendations of BS EN 1176 Part 1 - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 6 The connecting lugs are showing signs of wear - Monitor for any further deterioration and repair as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 7 The seats are too close to each other as defined in BS EN 1176 Part 2; this is a low risk failure and no remedial action is required - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 8 The seat has minor damage or wear - Monitor for any further deterioration and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 9 There is some wear to the shackles - Monitor for any further deterioration and replace when 40% worn | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | Football Goal (#1) | Finding 1 The net is damaged - Repair or replace as required | 10 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#1) | Finding 2 There are protruding cable ties present - Remove the protrusions | 10 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Football Goal (#1) | Finding 3 The goal is leaning - Reset the goal | 10 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#1) | Finding 4 The net is not secured appropriately - Secure the net | 10 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Football Goal (#1) | Finding 5 The brackets can be easily removed - Secure | 10 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Football Goal (#1) | Finding 6 There is surface corrosion present on the item - Consider treating the item | 10 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#1) | Finding 7 The nets clips are missing on the goal - Replace and secure all missing components | 10 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#1) | Finding 8 NB: We have undertaken a maintenance inspection only of the football goal(s); full load testing falls outside the scope of our inspection. - Implement load testing as required | 10 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#2) | Finding 1 NB: We have undertaken a maintenance inspection only of the football goal(s); full load testing falls outside the scope of our inspection. - Implement load testing as required | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#2) | Finding 2 The net is not secured appropriately - Secure the nets | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#2) | Finding 3 The net is damaged - Repair | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#2) | Finding 4 The net clips are missing on the goal - Replace and secure missing components | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#2) | Finding 5 The goals are not secured in position - Refer to manufacturer recommendations and provide as required | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#2) | Finding 6 A support is missing - Replace | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Ford End | PIC Annual Report | Football Goal (#2) | Finding 7 There are projecting bolt thread(s) present - Remove excess thread length and deburr or provide cap | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Football Goal (#2) | Finding 8 There are protruding cable ties present - Remove the protrusions | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Fence | Finding 1 There are areas or parts of the timber fence that have rotted - Replace all affected timbers | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Fence | Finding 2 The wire mesh is damaged in places - Repair or replace all affected sections | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Fence | Finding 3 There are unsecured timber rails - Secure | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Fence | Finding 4 There are areas or parts of the timber posts that have rotted - Replace all affected timbers | 8 - Low Risk | 2023-07-07 | A | Working Group | N |  | Working Group to consider policy to replace timber structures (or part).
Ford End | PIC Annual Report | Fence | Finding 5 The fence is damaged in places - Repair or replace all affected sections | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Gate - Maintenance | Finding 1 There are projecting bolt thread(s) present - Remove excess thread length and deburr or provide cap | 6 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Gate - Maintenance | Finding 2 The paintwork on this item has been damaged or worn exposing the metal underneath which is rusting - Treat any rusting components and repaint | 6 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Gate - Pedestrian | Finding 1 There are openings that are less than 12mm that could trap or crush fingers - Provide a 12mm gap throughout full range of motion at both sides of gate | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Gate - Pedestrian | Finding 2 The area under the gate has eroded leaving uneven areas, or the concrete foundations exposed, resulting in trip hazards at the entrance/exit to the playground - Reinstate to level with surrounding surfaces | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Gate - Pedestrian | Finding 3 There are trip hazards at the edges of the surface - Reinstate surrounding surface levels to remove the trip points | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Gate - Pedestrian | Finding 4 The timber has a number of splits/shakes or air cracks and this may affect the stability or allow water ingress which will accelerate the rotting process - Monitor to ensure the splits do not cross through fixing points of the structure and/or cause any instability | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Ford End | PIC Annual Report | Gate - Pedestrian | Finding 5 The gate is not operating correctly - Take effective action to ensure the gate closes between 4 and 8 seconds | 8 - Low Risk | 2023-07-07 | A | JB | N
Ford End | PIC Annual Report | Multi Play (Senior) | Finding 1 This item is satisfactory - no work required - | 4 - Very Low Risk | 2023-07-07 | A | N/a | Y | 2023-07-07 | New equipment
Howe Street | PIC Annual Report | Site General | Finding 1 There are gaps opening between the surfacing and the edging surround or between the joints in the surfacing - Monitor for any further deterioration and repair as required | 12 - Moderate Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | Site General | Finding 2 The surface is lifting at the edges and creating trip points - Repair perimeter of surfacing to remove trip points | 12 - Moderate Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Site General | Finding 3 There is weed / vegetation growth on, between, or around the edges of the surfacing - Remove weed / vegetation growth | 12 - Moderate Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Site General | Finding 4 The wetpour is crumbing in areas - Monitor for any further deterioration and repair as required | 12 - Moderate Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | Site General | Finding 5 There are trip hazards at the edges of the surface - Reinstate surrounding surface levels to remove the trip points | 12 - Moderate Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Site General | Finding 6 There is a self-made rope or tyre swing present. This type of construction is not recommended unless the trees/branches and connections have all been independently tested and checked by a competent person for sufficient structural stability, a suitable impact attenuating surface is provided on the seat itself and the surface underneath and a separately documented risk assessment and control measures are in place. - Remove if requirements are not met | 12 - Moderate Risk | 2023-07-07 | A | JB | Y | 2023-07-01 | Removed
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 1 The slide is predominately south facing and will catch the majority of the sun's heat during the day. Slide surfaces can become very warm during periods of sustained sunny weather - Monitor - No remedial work recommended | 12 - Moderate Risk | 2023-07-07 | A | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 2 There are a number of dents in the slide surface - Monitor for any further deterioration and repair as required | 12 - Moderate Risk | 2023-07-07 | M | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 3 The timber has a number of splits/shakes or air cracks and this may affect the stability or allow water ingress which will accelerate the rotting process - Monitor to ensure the splits do not cross through fixing points of the structure and/or cause any instability | 12 - Moderate Risk | 2023-07-07 | M | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 4 The bridge is making contact with the ground - Adjust fixings to raise bridge | 12 - Moderate Risk | 2023-07-07 | A | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 5 There is/are bolt cap covers missing or damaged on the item - Replace missing or damaged bolt cap covers | 12 - Moderate Risk | 2023-07-07 | A | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 6 A number of fixing(s) have worked loose - Secure all loose fixings | 12 - Moderate Risk | 2023-07-07 | A | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 7 There is some damage to the handgrips - Monitor for any further deterioration and repair as required | 12 - Moderate Risk | 2023-07-07 | M | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 8 The surfacing dimensions are short and do not meet with the requirements of the current applicable standard - Monitor - no remedial action recommended | 12 - Moderate Risk | 2023-07-07 | M | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 9 The item fails to meet the requirements of BS EN 1176 Part 1 4.2.7.2 head and neck entrapment in the barriers and/or steps - Monitor - No remedial work recommended | 12 - Moderate Risk | 2023-07-07 | M | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 10 The side of the slide extends less than 500mm above the slide surface at the start section and does not meet the recommendations of BS EN 1176 Part 3 - Monitor - No remedial work recommended | 12 - Moderate Risk | 2023-07-07 | M | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 11 There is some damage to the item - Monitor for any further deterioration and repair as required | 12 - Moderate Risk | 2023-07-07 | M | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 12 There is/are finger entrapment/s in the frame and the item fails to meet the requirements of BS EN 1176 Part 1 4.2.7.6 Entrapment of fingers - Monitor - No remedial work recommended | 12 - Moderate Risk | 2023-07-07 | M | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 13 A number of fixing(s) have worked loose on the slide starting section - Secure all loose fixings | 12 - Moderate Risk | 2023-07-07 | A | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 14 There are areas or parts of the timber on the structure that have rotted - Replace all affected timbers | 12 - Moderate Risk | 2023-07-07 | A | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 15 A number of fixing(s) have worked loose - Secure all loose fixings | 12 - Moderate Risk | 2023-07-07 | A | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | Multi Play (Junior) | Finding 16 The surface is lifting at the edges and creating trip points - Repair perimeter of surfacing to remove trip points | 12 - Moderate Risk | 2023-07-07 | A | N/A | Y | 2023-07-07 | New unit installed after PIC inspection
Howe Street | PIC Annual Report | See Saw | Finding 1 A number of fixing(s) have worked loose - Secure all loose fixings | 6 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | See Saw | Finding 2 The paint has worn off the metalwork - Rub down and repaint | 6 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | 1 Bay 1 Seat (Cradle) - Type 1 | Finding 1 There is some notable evidence of chain wear - Monitor for any further deterioration and replace when 40% worn | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 1 Seat (Cradle) - Type 1 | Finding 2 There is some wear to the shackles - Monitor for any further deterioration and replace when 40% worn | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 1 Seat (Cradle) - Type 1 | Finding 3 The seat has minor damage or wear - Monitor for any further deterioration and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 1 Seat (Cradle) - Type 1 | Finding 4 The split pins are missing from the shackles - Insert split pins to secure the shackles | 8 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | 1 Bay 1 Seat (Cradle) - Type 1 | Finding 5 There is moderate damage to the surface - Repair the damaged areas of surfacing | 8 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | 1 Bay 1 Seat (Cradle) - Type 1 | Finding 6 The shackles have been overtightened or seized transferring wear to the chain links below - Loosen shackles to ensure free movement at the pivot | 8 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | 1 Bay 1 Seat (Cradle) - Type 1 | Finding 7 The safety surface around the area is beginning to wear - Monitor for any further deterioration and repair as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 1 The seats are too close to the frame as defined in BS EN 1176 Part 2; this is a low risk failure and no remedial action is required - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 2 The surfacing width under the seat/s is / are less than 875mm when measured from the centre of the seat outwards, and fails the requirements of BS EN 1176 Part 2 - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 3 The seats are too close to each other as defined in BS EN 1176 Part 2; this is a low risk failure and no remedial action is required - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 4 The bushes are showing signs of wear - Monitor for any further deterioration and replace as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 5 There is some notable evidence of chain wear - Monitor for any further deterioration and replace when 40% worn | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 6 There is some wear to the shackles - Monitor for any further deterioration and replace when 40% worn | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 7 The chain openings are in excess of 8.6mm and do not meet the recommendations of BS EN 1176 Part 1 - Monitor - No remedial work recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 8 The connecting links are in excess of 8.6mm and less than 12mm and fail the requirements of BS EN 1176 Part 1; clause 4.2.13, Chains - Monitor use and replace with compliant links at the next maintenance cycle | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 9 The connecting lugs are worn - Replace lugs or all affected components | 8 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 10 The surface has subsided in some areas - Monitor for any further deterioration and repair as required | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 11 The paint is flaking off the metalwork - Rub down and repaint | 8 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | 1 Bay 2 Seat (Flat) | Finding 12 D250The surfacing dimensions are short and do not meet with the requirements of the current applicable standard - Monitor - no remedial action recommended | 8 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | Fence | Finding 1 There are sharp protrusions on the connections - Remove the sharp protrusions | 6 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Fence | Finding 2 The timber has a number of splits/shakes or air cracks and this may affect the stability or allow water ingress which will accelerate the rotting process - Monitor to ensure the splits do not cross through fixing points of the structure and/or cause any instability | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | Litter Bin | Finding 1 The liner of the litter bin is not secured - Ensure the lid/door is kept locked and the liner secured | 6 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Litter Bin | Finding 2 The item is slightly loose in its foundations - Monitor for any further deterioration and repair as required | 6 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | Litter Bin | Finding 3 There are post / end caps missing from the item - Replace missing post caps | 6 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Litter Bin | Finding 4 There are exposed sharp edges - Remove the sharp edges | 6 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Bench | Finding 1 There is or are fixings missing on the item - Replace all missing fixings | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | replace bench
Howe Street | PIC Annual Report | Bench | Finding 2 The grass mats are silted up, the soil is compacted and the area will become very slippery when the soil is wet. - Reinstate as required | 8 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | replace bench
Howe Street | PIC Annual Report | Football Goal | Finding 1 The area around the item has eroded and may become slippery - Reinstate eroded area | 10 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Howe Street | PIC Annual Report | Football Goal | Finding 2 NB: We have undertaken a maintenance inspection only of the football goal(s); full load testing falls outside the scope of our inspection. - Implement load testing as required | 10 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Howe Street | PIC Annual Report | Football Goal | Finding 3 The nets are damaged in areas - Monitor for any further deterioration and replace as required | 10 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | Football Goal | Finding 4 The nets are unsecured - Secure the nets | 10 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Football Goal | Finding 5 There is some tree debris on the surfacing - Remove and maintain | 10 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Football Goal | Finding 6 The net clips are missing - Replace missing components | 10 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Howe Street | PIC Annual Report | Football Goal | Finding 7 The item is loose in its foundations - Reinstall item to secure | 10 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Howe Street | PIC Annual Report | Football Goal | Finding 8 The paintwork on this item has been damaged or worn exposing the metal underneath which is rusting - Treat any rusting components and repaint | 10 - Low Risk | 2023-07-07 | A | Recreation Committee | N |  | Recreation Committee to agree and implement policy for renovation and relocation of football goalposts at all sites.
Howe Street | PIC Annual Report | Gate - Pedestrian | Finding 1 The area around the item has eroded and may become slippery - Reinstate eroded area | 10 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Gate - Pedestrian | Finding 2 The use of synthetic fillers in timber is not recommended; timber being a natural material will expand and contract as the moisture content changes and the use of fillers can exacerbate the length and depth of these cracks or shakes in the timber. The only treatment that is normally required is the removal of any rough or sharp edges unless the structural integrity of the item is affected. - Remove any rough or sharp edges and monitor timber for any further deterioration | 10 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Gate - Pedestrian | Finding 3 There are post / end caps missing from the item - Replace missing post caps | 10 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Gate - Pedestrian | Finding 4 There are openings that are less than 12mm that could trap or crush fingers - Provide a 12mm gap throughout full range of motion at both sides of gate | 10 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Gate - Pedestrian | Finding 5 The gate is not operating correctly - Take effective action to ensure the gate closes between 4 and 8 seconds | 10 - Low Risk | 2023-07-07 | A | JB | N |  | Consider in conjunction with any decision to alter closing mechanism for gate, e.g. loop arrangement rather than self-closing mechanisms.
Howe Street | PIC Annual Report | Gate - Pedestrian | Finding 6 There are projecting bolt thread(s) present - Remove excess thread length and deburr or provide cap | 10 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Gate - Pedestrian | Finding 7 A number of fixing(s) have worked loose - Secure all loose fixings | 10 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Gate - Pedestrian | Finding 8 There is some evidence of rot in the timber - Monitor for any further deterioration and replace as required | 10 - Low Risk | 2023-07-07 | M | Playground Inspector | Ongoing | Ongoing
Howe Street | PIC Annual Report | Gate - Maintenance | Finding 1 There are projecting bolt thread(s) present - Remove excess thread length and deburr or provide cap | 8 - Low Risk | 2023-07-07 | A | JB | N
Howe Street | PIC Annual Report | Sign | Finding 1 It is recommended that signage, with information including the site address, contact information for maintenance issues and emergency contact details are provided for the facility - Provide in accordance with the recommendations | 5 - Very Low Risk | 2023-07-07 | A | Clerk | Y | 23.08.2023 | Recommend approach/policy.

## Risk Assessment Matrix
Risk Assessment Matrix
Scores are multiplications of Likelihood x Severity
Likelihood | Very High probability. If the situation is not addressed an accident is almost certain | 5 | Very High | VL (5) | L (10) | M (15) | H (20) | VH (25)
| High probability. An accident is probable without any added factor. | 4 | High | VL (4) | L (8) | M (12) | H (16) | H (20)
| Moderate probability. An incident is foreseeable. | 3 | Moderate | VL (3) | L (6) | L (9) | M (12) | M (15)
| Some probability. Requires a combination of factors to take place. | 2 | Low | VL (2) | VL (4) | L (6) | L (8) | L (10)
| No significant probability. (exceptions would be lightning strikes, freak accidents) | 1 | Very Low | VL (1) | VL (2) | VL (3) | VL (4) | VL (5)
|  |  |  | Very Low | Low | Moderate | High | Very High
|  |  |  | 1 | 2 | 3 | 4 | 5
|  |  |  | No injury likely, e.g. damaged or soiled clothing, minor bruising, grazes | Minor injury, laceration or bruising requiring first aid only | Injury requiring medical intervention, e.g. cuts requiring stitches | Serious injury including concussions or fracture of long bones. | Severe injury involving potentially life changing injury or fatality.
Severity