## Sheet1
Great Waltham Parish Council - Finance & General Purposes Committee Meetings Action Tracker
May 2023 - April 2024 inclusive (with carried forward items)
2023-10-09
Meeting Date | Agenda Item Ref. No. | Agenda Item (in bold) with narrative from meeting discussion | Resolution(s), if any | Open/ Closed | X/refer | Action Owner(s) | Last Updated | Date Closed | Update Log
2023-07-31 | 11 | To receive an update on implementation and use of the new finance software package The Clerk confirmed that he has had 3 training sessions on the software. The accounts have been entered up to mid-July on the system and the accounts have been reconciled online for April, May and June. The Clerk will stop using the MS Excel sheets in August once the July bank reconciliation has been completed. The system has a number of report production features which the Committee/Council may wish to utilise. | 1. The Clerk and the Chair to review the suite of reports available and make recommendations for future meetings. | Open | 28/08/2022 (10) 23/01/2023 (9) 23/1552 | Clerk/Chair | 2023-10-09 |  | 09.10.2023 meeting: Reports to be reviewed once additional data has been loaded. Carry forward.
2023-07-31 | 13 | To consider the introduction of an internal financial control document (as indicated in the Council’s latest internal audit report). The internal audit report was discussed. In view of the existing safeguards in Financial Regulations and Standing Orders the requirements of the auditor are unclear. | 1. The Clerk to contact the internal auditor to clarify the requirements. | Open | 23/1582 |  | 2023-10-09 |  | 09.10.2023 meeting: Action Outstanding. Carry forward.
2023-10-09 | 6 | Review of the Budget Performance 2023-2024 to date. FY 2023 to 2024 Budget Spent Balance Staff Costs £32,930 £16,463 £16,466 Administration £8,341 £10,469 -£2127.83 Open Spaces £36,450 £6,207 £30,243 Allotments £1,350 £1,286 £64 Grants £2,000 £2000 £0 Some minor issues were noted in the allocation of the budget due to the transfer of data to the new system – AdvantEdge. | 1. Clerk to investigate and reallocate the funds via the journal transactions on AdvantEdge. | Open |  |  | 2023-10-09
2023-10-09 | 7 | Discuss a budget for 2024-2025.  A budget of £119,112 was proposed which is a Council Tax precept increase of £3.08 per month per Band D property type.  A lengthy debate was undertaken with all items being rigorously challenged and reviewed to test both the need for their inclusion and the amount to be allocated in the budget.  Subject to minor adjustments on staff costs and general reserves top-up amounts, the budget was reduced to £110,627. | 1. The Committee recommends a budget of £110,627, subject to any minor amendments relating to revised staff costs and general reserves amounts. | Open |  |  | 2023-10-09
2023-10-09 | 8 | Discuss and agree a precept demand on Chelmsford City Council for 2024-2025 (To be agreed in full council). The budget of £110,627 was reduced for an estimated income of £6,600 creating a precept demand of £104,027. If the tax base is the same as 2023-2024 the impact on a band D property will be £1.74 per month or £21 per year. | 1. The Committee recommends a precept of £104,027, subject to any minor adjustments relating to revised staff costs and general reserves amounts. | Open |  |  | 2023-10-09