## Sheet1
Great Waltham Parish Council - Monthly Meeting Action Tracker
May 2023 - April 2024 inclusive (with carried forward items)
2024-01-15
Meeting Date | Agenda Item Ref. No. | Agenda Item (in bold) with narrative from meeting discussion | Resolution(s)/Action(s), if any | Open/ Closed | X/refer | Action Owner(s) | Last Updated | Date Closed | Update Log
2022-06-13 | 22/1174 | Discuss membership of the Emergency Planning Sub Committee (Chair, Vice Chair plus three councillors representing all areas of the Parish) and if it is still required. A report was placed on the website with the agendas. During discussions it was noted that the committee had not met in over 8 years, but an updated Emergency Action Plan would be useful. | 1. An emergency plan to be drawn up by Cllr Steel 2. Dissolve the emergency planning committee. | Open |  | Cllr Gilbert/Clerk | 2024-01-15 |  | Carried forward from previous period August - No update September No update October - No update No Update Dec- Document has been issued to be kept as live document and discussed at the January 2023 meeting. March - Defer Cllr Steel to discuss a revision with Karen Buttress the Chelmsford City Council Community Safety Lead officer. 17/07/2023 meeting - response received from Karen Buttress - Cllr Gilbert to progress 22/08/2023 meeting: agreed to carry forward. 18/09/2023 meeting: agreed to carry forward. 16/10/2023 meeting: Work to product a document for consideration has continued, but a value against benefit reassessment may be needed given the likely resource requirements needed to keep an agreed version maintained. Carry forward. 20/11/2023 meeting: The document was reviewed. Agreed to split into 2 documents (internal & external). Cllr Gilbert to work with Clerk to develop drafts. 12/12/2023 meeting: Carried forward. 15/01/2024 meeting: Remains work in progress. Agreed that following recent weather events attending to fallen trees and temporary flooding deserves particular attention.
2023-04-24 | 23/1467 | To agree the Highways & Transport Committee's recommendation that the Council lobbies the relevant authorities/agencies to change the A120 back-up diversionary route from the B1008 to the B1256. Build a report for Highways England to lobby for the change. The B1256 is the old A120 that runs parallel to the current A120. An approach to the Department for Transport was unsuccessful. | 1. Agreed. Lobby Highways England. | Open |  | Cllr Gilbert | 2024-01-15 |  | Carried forward from previous period share with Barnston Parish Council Response from Highways England to request for data relating to road closures during upgrade work on A120 received, but they do not collect any relevant information. Recommended way forward to be discussed at H&TC meeting 24/7/2023. 22/08/2023 meeting: Further letter to Highways England sent 01/08/2023 requesting consideration of redesignation of B1008 based on evidence supplied. Reply awaited. Carry forwards. 18/09/2023 meeting: in email of 29/08/2023 Highways England agreed that our 'suggestion to designate the B1256 as the primary [diversionary] route is indeed valid' and with ECC they 'continue to review the feasibility of designating the B1256 as the main diversion route'. Agreed for chair to follow up if no further indication of action being taken. 16/10/2023 meeting: Highways England to be chased after 3 months (from their last email). 20/11/2023 meeting: Reminder e-mail sent to Highways England. 12/12/2023 meeting: Response received, but no action taken by Highways England to date. To be followed-up in 2024. 15/01/2024 meeting: Carry forward to chase Highways England.
2023-08-22 | 23/1607 | Proposal for SID pole at Church end on approach the Village. • This location is the descent into the village on Main Road travelling from Howe Street. • The Parish Council has 7 poles in the Parish funded by the Local Highways Panel (LHP), but LHP has no budget for additional ones. • Speed Watch volunteers do not currently have the authority to monitor from this new position. • The City Council ‘lamppost’ scheme for housing speed indication devices (SID) has not yet been built into a process to roll out for use. | 1. To ask the Great Waltham Speed Watch group to investigate a new site in the area. | Open | H&TC 24/07/2023 (12) | Cllr Steel/Cllr Jenkins | 2024-01-15 |  | 18/09/2023 meeting: SID pole approval request to be made via LHP 16/10/2023 meeting: Outcome of application awaited. 20/11/2023 meeting: No update available. Carry forward. 12/12/2023 meeting: Application still outstanding. Await response. 15/01/2024 meeting: Application response still awaited. Cllr Steel to chase.
2023-08-22 | 23/1609 | Given that the Ringtail Green Quiet Lane (and other suggestions), failed to be supported by the Chelmsford LHP committee due to more pressing priorities, it is proposed that GWPC submit and fully fund the schemes via the Direct Works process (noting that the LHP will not add any funding) • The meeting noted that the road at Ringtail Green meets the technical specifications for a Quiet Lane, but that LHP members have considered the request and have decided to spend the funding on what are seen as higher priority areas. • It was also noted that other previously submitted schemes for Ringtail Green and the immediate areas are unlikely to obtain favourable considerable without evidence of a significant deterioration in the issues which have been identified. • The meeting acknowledged the prioritisation/funding pressures which exist for higher authorities’ decision-makers. • It was noted that a direct process is available that the Parish Council pays for the work, but it still follows the LHP process. Works will be undertaken by Ringway Jacobs. • A proposal (per the agenda item) was made and seconded. • An amendment (as shown in the resolution below) was made and seconded: • A named vote was called: Abstain : Cllr McDevitt Support amendment: Cllrs Gilbert, Steel, Page, Jenkins, Palmer, Stephenson, Martin and Bradley • The amendment was carried. | 1. Given that the Ringtail Green Quiet Lane (and other suggestions), failed to be supported by the Chelmsford LHP committee due to more pressing priorities, it is proposed that Great Waltham Parish Council will submit an enquiry for the costs associated with a direct works application via the Direct Works process (noting that the LHP will not add any funding) | Open |  | Clerk | 2024-01-15 |  | 18/09/2023 meeting: Clerk to submit works request to Essex Highways Solutions so that Council can consider further action/self-funding options. 16/10/2023 meeting: Clerk awaiting clarification of process to ensure all submissions from PC side have been completed. 20/11/2023 meeting: Clerk to chase update on the validation process. 12/12/2023 meeting: Current position remains to be established. Review at next meeting. 15/01/2024 meeting: Clerk reports EHS feedback still awaited. Carry forward.
2023-09-18 | 23/1653 | Proposal that the Traffic Committee considers promoting and facilitating the PC and residents join the ECC funded Parish Paths Partnership Public Rights of Way - Volunteering ¦ Essex County Council (essexhighways.org). Paths are cut once a year. To increase the cuts volunteers need to be trained up and then funding may granted. There is a headland scheme in action where farmers get paid to cut. | (1) The Highways and Transport Committee to discuss in conjunction with its already open action addressing this issue. | Open | H&TC 25/09/2023 (8) | Cllr Bradley/Clerk | 2024-01-15 |  | 16/10/2023 meeting: Meeting noted discussion earlier in the day with PROW officers where options for entering a service level agreement (using own contractors) and volunteering were clarified. Work to establish PC's requirements to continue. 20/11/2023 meeting: Meeting held with the PROW officer and manager. Action owners to work up discussion paper with recommended engagement strategy. 12/12/2023 meeting: In progress. Carry forward. 15/01/2024 meeting: Cllr Bradley confirmed work is in progress and strategy paper to be offered for discussio at next H&T Committee meeting in February.
2023-11-20 | 23/1696 | Agree the Recreation Committee’s proposal to employ a cleaner for the Pavilion.  The meeting noted that increased hires of the Pavilion mean that a resource beyond that available as part of the Clerk’s role and by volunteers is required.  The process to employ the cleaner will be undertaken by the Staffing Committee. | (1) The Parish Council agrees to engage a contracted service. | Open |  | Staffing Committee | 2024-01-15 |  | 12/12/2023 meeting: No update from Staffing Committee. Carry forward. 15/01/2024 meeting: Staffing Committee has submitted advertisement to Parish News for its February issue. The Clerk will post the article on social media at the time the February PN is issued. Leave as open item to track developments.
2023-12-12 | 23/1718 | To agree to make representations to the landowner to repair and restore the cobbled area adjacent to Walthambury Stores and The Beehive. | (1) The Clerk to write a letter to the landowner to seek his views on the future improvement of the area. | Open |  | Clerk | 2024-01-15 |  | 15/01/2024 meeting: Landowner contacted. Clerk to chase response as necessary.
2024-01-15 | 23/1733 | Discuss the request from the community network to change the colour of the Banbury tree lights to white and have them higher in the tree for the Christmas tree festival 2024 See also the comments under item 23/1723. The oak tree in Banbury Square used to display the lights needs some identified tree cutting work to be completed by a tree surgeon, so it may be that work to (re)install lights can be effected at the same time. | (1) In consultation with the Community Network, investigate the purchase of new Christmas tree white lights that will cover the Banbury Square tree. | Open |  | Cllr Jackson | 2024-01-15
2024-01-15 | 23/1734 | To receive a presentation from the Chelmsford and Maldon Community Policing Team on current policing priorities and issues in the parish. The Community Policing Team was unable to attend on the night due to an operational emergency. The relevant issues raised at the meeting will be fed back to the Team so they may be considered when the presentation is rescheduled. | (1) Defer item to next month. | Open |  | Clerk | 2024-01-15
2024-01-15 | 23/1735 | To consider a request to place an anti-pylons banner on the green at Broad’s Green. The meeting noted the request from a local resident requesting permission to place a banner on the Council’s land at this location. | (1) In principle the Council agrees to the placement of a ‘Say No’ pylons banner on the green, but if there are complaints from local residents it will be removed. The banner must be placed within the circle of bollards and due consideration must be taken in relation to identifying the location of, and avoiding damage to, underground utility pipes, wires etc. | Open |  | Cllr Gilbert/Clerk | 2024-01-15
2024-01-15 | 23/1737 | To discuss and agree next steps in relation to the Ford End Average Speed Camera scheme. Cllr Cuningham, the ECC cabinet member for Highways has been contacted by both the ECC Cllr Steel and the Chair of the Parish Council but with no returning engagement to date. It is understood that it is unlikely the Highways design manager will be available to discuss in detail the reasons for the revised cost estimate for the scheme. The Parish Council has an option to pay for a new design itself – it is understood the work involved to get a new design would be £4,000 to £5,000. The meeting then considered its next steps and the following proposal was made and seconded: This Parish Council reconfirms its view that the weight, volume and speed of vehicles using the B1008 through Ford End village continues to present a risk to pedestrians and other road users and will continue to lobby Essex County Council Highways for road safety improvements. A named count was requested and called. Cllr Martin – Yes. Cllr Micklem – Yes. Cllr Bradley – Yes. Cllr Palmer – Yes. Cllr McDevitt – Yes. Cllr Jackson – Yes. Cllr Stephenson – Yes. Cllr Jenkins – Yes Cllr Gilbert – Yes. Cllr Steel – Abstain. The Proposal was passed by majority vote. | (1) Cllr Steel to chase up SERP to establish whether they would continue to support the ASC since it would be their operational responsibility once installed. (2) Cllr Steel to follow up with enquiries to establish the process for reconsidering the 3-way agreement between SERP, Essex Police and ECC needed for any scheme to progress. (3) The Parish Council to write to the Leader of ECC (Kevin Bentley) to request his intervention given the lack of engagement, and to request that any redesign costs be paid for by ECC. (4) This Parish Council reconfirms its view that the weight, volume and speed of vehicles using the B1008 through Ford End village continues to present a risk to pedestrians and other road users and will continue to lobby Essex County Council Highways for road safety improvements. | Open | 23/1523 23/1619 23/1649 23/1650 23/1736 |  | 2024-01-15