## Sheet1
Great Waltham Parish Council - Monthly Meeting Action Tracker
May 2024 - April 2025 inclusive (with carried forward items)
2024-05-20
Meeting Date | Agenda Item Ref. No. | Agenda Item (in bold) with narrative from meeting discussion | Resolution(s)/Action(s), if any | Open/ Closed | X/refer | Action Owner(s) | Last Updated | Date Closed | Update Log
2023-08-22 | 23/1607 | Proposal for SID pole at Church end on approach the Village. • This location is the descent into the village on Main Road travelling from Howe Street. • The Parish Council has 7 poles in the Parish funded by the Local Highways Panel (LHP), but LHP has no budget for additional ones. • Speed Watch volunteers do not currently have the authority to monitor from this new position. • The City Council ‘lamppost’ scheme for housing speed indication devices (SID) has not yet been built into a process to roll out for use. | 1. To ask the Great Waltham Speed Watch group to investigate a new site in the area. | Open | H&TC 24/07/2023 (12) | Cllr Steel/Cllr Jenkins | 2024-05-20 |  | 18/09/2023 meeting: SID pole approval request to be made via LHP 16/10/2023 meeting: Outcome of application awaited. 20/11/2023 meeting: No update available. Carry forward. 12/12/2023 meeting: Application still outstanding. Await response. 15/01/2024 meeting: Application response still awaited. Cllr Steel to chase. 19/02/2024 meeting: Item not discussed - agreed carry forward to next meeting. 22/04/2024 meeting: Response still awaited. Action owners will chase. Carry forward. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Obtain action owners update at next meeting. 20/05/2024 meeting: No further update - Cllr. Steel to chase response. 10/06/2024 - Action owner(s) update required.
2023-08-22 | 23/1609 | Given that the Ringtail Green Quiet Lane (and other suggestions), failed to be supported by the Chelmsford LHP committee due to more pressing priorities, it is proposed that GWPC submit and fully fund the schemes via the Direct Works process (noting that the LHP will not add any funding) • The meeting noted that the road at Ringtail Green meets the technical specifications for a Quiet Lane, but that LHP members have considered the request and have decided to spend the funding on what are seen as higher priority areas. • It was also noted that other previously submitted schemes for Ringtail Green and the immediate areas are unlikely to obtain favourable considerable without evidence of a significant deterioration in the issues which have been identified. • The meeting acknowledged the prioritisation/funding pressures which exist for higher authorities’ decision-makers. • It was noted that a direct process is available that the Parish Council pays for the work, but it still follows the LHP process. Works will be undertaken by Ringway Jacobs. • A proposal (per the agenda item) was made and seconded. • An amendment (as shown in the resolution below) was made and seconded: • A named vote was called: Abstain : Cllr McDevitt Support amendment: Cllrs Gilbert, Steel, Page, Jenkins, Palmer, Stephenson, Martin and Bradley • The amendment was carried. | 1. Given that the Ringtail Green Quiet Lane (and other suggestions), failed to be supported by the Chelmsford LHP committee due to more pressing priorities, it is proposed that Great Waltham Parish Council will submit an enquiry for the costs associated with a direct works application via the Direct Works process (noting that the LHP will not add any funding) | Open |  | Clerk | 2024-05-20 |  | 18/09/2023 meeting: Clerk to submit works request to Essex Highways Solutions so that Council can consider further action/self-funding options. 16/10/2023 meeting: Clerk awaiting clarification of process to ensure all submissions from PC side have been completed. 20/11/2023 meeting: Clerk to chase update on the validation process. 12/12/2023 meeting: Current position remains to be established. Review at next meeting. 15/01/2024 meeting: Clerk reports EHS feedback still awaited. Carry forward. 19/02/2024 meeting: Item not discussed - agreed carry forward to next meeting. 16/04/2024: At the H&TC meeting on 15/04/2024 it was noted that current LHP schemes are being re-assessed. Once a self-funded scheme application and validation has been completed there should be a clearer idea of whether this scheme is acceptable (i.e. validated) and its costs. 22/04/2024 meeting: Position in entry for 16/04/2024 above noted. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: No update due to current review of LHP. 20/05/2024 meeting: Await response and chase as necessary. 10/06/2024 - Action owner update required.
2024-01-15 | 23/1733 | Discuss the request from the community network to change the colour of the Banbury tree lights to white and have them higher in the tree for the Christmas tree festival 2024 See also the comments under item 23/1723. The oak tree in Banbury Square used to display the lights needs some identified tree cutting work to be completed by a tree surgeon, so it may be that work to (re)install lights can be effected at the same time. | (1) In consultation with the Community Network, investigate the purchase of new Christmas tree white lights that will cover the Banbury Square tree. | Open |  | Cllr. Palmer | 2024-05-20 |  | 19/02/2024 meeting: Item not discussed - agreed carry forward to next meeting. 22/04/2024 meeting: Supply options being investigated with a view to possible funding request. CARRIED FORWARD FROM 2023/24 TRACKER 20/05/2024 meeting: Supply options continue to be investigated. Carry forward. 10/06/2024 - Action owner update required.
2024-02-19 | 23/1760 | Review the quote to replace the play area gates at Great Waltham Recreation Ground. A quote from JCM was reviewed for £820 for 2 metal gates and £1,600 for 2 wooden gates. The financial regulations were waived due to a need to get the gates replaced in a short timescale. | (1) Install metal gates due to the reduction in maintenance, longer planned long life and lower cost. (2) Clerk to appoint JCM to undertake the gate work as soon as possible. | Open |  | (2) Clerk | 2024-05-20 |  | 22/04/2024 meeting: Noted that option to install gates may be affected by findings and recommendations of Recreation Ground working group. Await developments there with a view to reassessing installation plan. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Due to the proposed play area refresh it was agreed at Recreation Committee to pause this initiative as costs are £1,000 per gate. Action owner update required. 20/05/2024 meeting: Agreed to proceed per 12/05/2024 update. Leave action open to monitor developments. 10/06/2024 - Continue to monitor developments.
2024-02-19 | 23/1767 | Consider the Recreation Committee’s proposal to purchase two new adult football goals (one each at Howe Street and Ford End Recreation Grounds) and to refurbish the two adult football goals at Great Waltham Recreation Ground. | (1) Approval to purchase a set of new goals at £1,448 for goals and spend £720 for installation of sockets. Total: £2,168 (incl. VAT ) – 1 x Ford End and 1 x Howe Street. (2) Approval to refurbish 2 adult goals at Great Waltham. Shot blast and paint at a cost of £480, with socket install of £720 = £1,200 (incl. VAT) | Open |  | (1) Clerk (2) Clerk | 2024-05-20 |  | 14/04/2024: Actions in progress (discussed at Recreation Committee 09/04/2024). 22/04/2024 meeting: Position above noted. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Removal of posts for renovation and repositioning of post sockets in progress. 20/05/2024 meeting: Update of 12/05/2024 noted. 10/06/2024 - Project has progressed. Obtain update at 18/06/2024 meeting.
2024-02-19 | 23/1768 | Confirm the Council’s previous decision to purchase and locate a Defibrillator and Cabinet at Broad’s Green. | (1) Approval to spend £3,102 (incl. VAT) with The Community Heartbeat Solutions for Broad’s Green and install in the telephone box. | Open |  | (1) Clerk/Cllr. Martin | 2024-05-20 |  | 14/04/2024: Defibrillator purchased. Work to renovate the telephone box prior to installation in progress. 22/04/2024 meeting: Position above noted. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Defibrillator has been delivered. Awaiting clarification of landowner's permission before repainting telephone box and installation commences. 20/05/2024 meeting: Update of 12/05/2024 noted. 10/06/2024 - Refurbishment of telephone box remains outstanding - volunteer resource to be confirmed. Council yet to receive landowner's rights of access contract for consideration. Defibrillator has been purchased.
2024-03-19 | 23/1798 | To determine what action GWPC needs to take in response to the claim on land adjacent to Eagle Cottage The Clerk confirmed that the area is a Village Green and is recorded on the Village Green and Commons Register held by Essex County Council. It was registered in 1984 after consideration by the Commons Commissioners. The owners of Eagle Cottage have been informed in writing of the position. | (1) The owners of Eagle Cottage are invited to respond to the Council’s letter in the next 14 days so that the Council can consider its next steps. (2) Clerk to register the land with Land Registry as being owned by the Parish Council. | Open | 23/1821 | (1) Cllr. Gilbert (2) Clerk | 2024-05-20 |  | 14/04/2024: (1) Response letter received from owners of Eagle Cottage. (2) Process of registration in progress. Matter to be discussed at 22/04/2024 monthly meeting. 22/04/2024 meeting: (1) Response letter received. Close this action (see 23/1821) (2) Process of registration remains in progress. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: (2) Land registration process continues. Carry forward to await developments. 20/05/2024 meeting: Noted that land registration process continues. 10/06/2024 - Land registration process continues.
2024-03-19 | 23/1802 | Discuss an in principle expenditure of up to £1000 on replacing the wooden bridge on the tower units at Great Waltham recreation ground. The Clerk produced a report showing available options to replace the bridge which is starting to rot. | (1) The Parish Council approved expenditure up to £1,000 for this purpose. | Open |  | (1) Clerk | 2024-05-20 |  | 14/04/2024: Procurement process in progress. 22/04/2024 meeting: Position above noted. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Paused until after the annual inspection. 20/05/2024 meeting: Update of 12/05/2024 noted. Await annual inspection and then consider next steps. 10/06/2024 - Await review of findings from playground inspection report.
2024-04-22 | 23/1821 | To agree to set up a working group to discuss all aspects of and make recommendations in relation to village green (VG150) at the southern end of Church Lane, Ford End. • The owners of Eagle Cottage sent in a written response after last month’s meeting concerning the issues raised at the monthly meeting. • Issues raised over the ownership by the Parish Council and implications of the area being a designated Village Green. • Essex Highways comments required around visibility due to the fences and hedge planted. • The newly planted hedge has been vandalised. • Village Greens can be fenced – if it enhances the recreational aspect of the green. • Does the hedge and fence fall within the Essex Highways land? Must be more than 45cm away from the highway (or pavement). If it does not block the view of emerging traffic joining the B1080 it would not be a concern for that reason. • If fence is above 1m in height planning consent may be required. • This is a complex issue covering Highways’ interests, village green regulations, and other relevant legislation. | (1) Create a working group to discuss the VG150. (2) The working group to comprise Cllrs. Gilbert, Martin, Stephenson, Palmer, Bradley and McDevitt. | Open | 23/1798 | (1) Cllr. Gilbert (2) Cllr. Gilbert | 2024-05-20 |  | CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: (1) Working group to meet on 13/05/2024 & report progress to 20/05/2024 meeting. (2) Close this action. 20/05/2024 meeting: (1) Reported that Essex Highways have visited site and will report back to ECC Cllr. Steel in a few days. Agreed to await Highways comments before agreeing next steps. 10/06/2024 - (1) ECC Cllr. Steel has reported that Highways have indicated enforcement action requirements will involve removal of fence/hedge by owners of Eagle Cottage and they have written/will write to owners to confirm. In the meantime, the PC has written to the owners to detail its position with a request to engage further on the future maintenance and agreed use of VG150.
2024-04-22 | 23/1824 | To update PC on use of volunteers to side out footways, including Main Road/Pendon Hill Great Waltham/Howe Street and to discuss and agree a way forward including an appropriate budget of up to £300 to cover signage, additional high vis and any other items agreed necessary. • Concerns had been raised about the assumption of insurance cover for all types of activities, some which would have been conducted historically by higher authority employees. • In particular, the issues associated with work adjacent to national speed limit roads should be properly considered. | (1) Discuss the need for a risk assessment and to devise as necessary. (2) The Clerk to ask our insurers for their view and advice. | Open |  | (1) Cllr. Bradley (2) Clerk | 2024-05-20 |  | CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: (1) & (2) Action owners update required. 20/05/2024 meeting: Carry forward. 10/06/2024 - Action owners' updates required.
2024-04-22 | 23/1825 | To discuss and agree whether Great Waltham Parish Council should join the Parish Paths Partnership scheme offered by Essex Council Highways and in what capacity. Option to take on the annual budget and arrange the cuts. Option to work with ECC on a voluntary scheme to maintain the footpaths. Work would cover surveys, signage liaison with landowners and general maintenance. | (1) The Parish Council supports the scheme subject to resource of volunteers. | Open |  | (1) Cllr. Bradley | 2024-05-20 |  | CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Request for volunteers made at Annual Assembly - further request to be made via Parish News. Action owner to provide update on latest position. 20/05/2024 meeting: Cllr. Bradley confirmed some initial interest and will submit article to next edition of PN. Carry forward for further updates. 10/06/2024 - Action owner update required.
2024-05-20 | 24/1849 | Review and adoption of the Financial Regulations. It was noted that a new model has been issued for 2024. | (1) Adopt the current version. (2) The latest NALC revised version to be shared with the members | Open |  | (2) Clerk | 2024-05-20 |  | 10/06/2024 - (1) Close this action. (2) Complete review of new wording to assist in provision to members of advice on significance of changes. Carry action forward.
2024-05-20 | 24/1874 | To review and comment on the new Chelmsford Local Plan (8th May to 19th June)  It would reflect the view of residents if the Back Lane (14a) site is opposed.  There is a potential for 40 houses on the school (14b) site.  In the City Council’s SHELAA document 7 sites in Ford End were originally identified. The other 5 sites were discounted as not suitable or deliverable.  The delivery dates indicated for sites 14a and 14b are from 2029/2030 onwards. | (1) The Parish Council opposes any development in Back Lane (14a) due to the issues raised with the Parish Council by parishioners on flooding, heritage loss, narrow lanes and light loss. (2) The Parish Council supports the development south of the school (14b) if benefits for the community of Ford End are better traffic control and safety on the road. (3) Cllr Steel and Cllr Gilbert will draft a response for it to be submitted to Chelmsford City Council. | Closed | 23/1823 | (3) Cllr Steel & Cllr Gilbert | 2024-05-20 |  | 10/06/2024 - (1) & (2) Close these actions. (3) Consultation response submitted to CCC based upon resolutions (1) and (2), using information and feedback provided by residents. Recommend close this item.
2024-05-20 | 24/1875 | Discuss and agree the Council’s written response to the statutory consultation issued by National Grid in relation to its proposals to upgrade the transmission network between the existing substations at Norwich Main in Norfolk, Bramford in Suffolk, and Tilbury in Essex.  Cllr Micklem declared an interest– Family – Pecuniary interest.  It was agreed that the Council’s response should note reflect that: o It is based on NG proposals and parishioner feedback at various events. o The Council is disappointed NG has made minimal changes to its proposals in the non-statutory consultations. o Opposition to the proposals remains for a variety of reasons, many ones stated previously and which have still not been properly addressed. o NG has failed to properly consider both the short- and long-term harms created by the proposals. o In particular, the visual and noise blight created by pylons, loss of amenity value, loss of productive agricultural land, impact on property prices, and the financial and inconvenience impacts of disruption during construction have all been inadequately factored into the proposals. o There has been over-reliance by NG on National Policy Statement EN-5 in relation to the Government’s position ‘that overhead lines should be the strong starting presumption for electricity networks developments in general’. o The Council opposes the construction of pylons for transmission lines anywhere in its parish, or indeed elsewhere else under these proposals. o The Council’s preference remains an offshore route, but failing that any overland route should be effected using an HVDC underground solution. o NG has failed to thoroughly examine alternative solutions and essentially has chosen to reverse-engineer a scheme based on a premeditated decision to use pylons come what may. o NG has failed to consider the full overall costs in the proposals; for instance, to reflect issues such as full and fair compensation to home and business owners. These additional costs make HVDC a viable alternative. o Any overland route will require a compensation scheme of some description and that this should be based on full and fair recompense to all home and business owners, rather than a less-targeted ‘community benefits’ solution. o NG seems to have chosen to make the case for a scheme where the wishes of local people and consumers and the permanent harms to the countryside have been ignored to enable it to satisfy its own financial objectives, such as maintaining its profit margins and shareholder value. | (1) Cllr Gilbert will create a draft response and will share with the Parish Council prior to submission. | Closed |  | Cllr. Gilbert | 2024-05-20 |  | 10/06/2024 - Draft response prepared, submitted to members for review and submitted to National Grid (and posted on parish website). Recommend close this item.
2024-05-20 | 24/1877 | Discuss the provision and options for Wi-Fi for the Pavilion. Several options were supplied in a briefing note for discussion. Due to cost and short cancellation timeline the ‘3’ network was preferred. | (1) Network 3 mobile Wi-Fi approved. (2) Clerk to arrange installation of Wi-Fi. | Open |  | (2) Clerk | 2024-05-20 |  | 10/06/2024 - (2) Action owner update required.
2024-05-20 | 24/1878 | Discuss the Stansted Night Flights Consultation and the submission.  Manchester Airport Group are proposing three options for change to the current restrictions. Night flights have always been allowed (23.30 to 06.00).  After discussion it was agreed that option 3 (keeping the status quo for three years from 2025) is the preferred solution and that the response to the consultation should also include comments making the points that: o In general night flights should not be allowed. o Night time should be between 23:00 and 07:00, as the current 6.5 hours is below the recommended NHS sleep period for adults. o If some night flights are deemed essential, the noise quota limit should be reduced as planes become quieter. o It is understood that night flights maybe necessary for emergencies. o Dispensation from policy should only be allowed because of exceptional circumstances | (1) The Parish Council prefers option 3 (2) Cllr Stephenson to work with the Clerk to submit the Council’s response by the due date noting the Council’s preference and including the additional comments. | Closed |  | (2) Cllr Stephenson/Clerk | 2024-05-20 |  | (2) Consultation response submitted on agreed basis. Recommend close this item.
2024-05-20 | 24/1882 | To inform the Council of the Great Waltham Play Area Working Group’s progress to date and to discuss and agree the next steps. Members noted and discussed the confidential briefing note. | (1) The Council acknowledges that the wooden play equipment items at Great Waltham Recreation Ground are approaching the end of their serviceable lifespan. (2) The Council confirms its intention to continue to provide a children’s play area at Great Waltham with similar function (and where appropriate improved) play equipment. (3) The Council acknowledges the working group’s indicative design for this project and agrees it should be used as the basis for user consultation, fund sourcing and specifying the public tender design requirements. (4) The Council agrees the preferred method of funding the project will be grants supplemented by other fund-raising options. (5) The Council agrees the desired timescale for the project is as soon as reasonably practicable. | Closed |  | (3) Cllr Martin (4) Cllr Martin (5) Cllr Martin | 2024-05-20 |  | 10/06/2024 - (3) (4) (5) See Recreation Committee 03/06/2024 meeting minutes (item 15). Recommend close this item and continue to track project progress under Recreation Committee tracker.