## Sheet1
Great Waltham Parish Council - Highways & Transport Committee Meetings Action Tracker
May 2024 - April 2025 inclusive (with carried forward items)
2024-04-15
Meeting Date | Agenda Item Ref. No. | Agenda Item (in bold) with narrative from meeting discussion | Resolution(s), if any | Open/ Closed | X/refer | Action Owner(s) | Last Updated | Date Closed | Update Log
2022-08-15 | 22/1212 | 22/1212 Report by County Councillor - Cllr Mike Steel 20’s Plenty campaign. The scope of the campaign locally is likely to be predicated by an outstanding update by Safer Essex Roads Partnership to its Functional Route Hierarchy Review, to be followed then by a revision of the Essex Speed Management Strategy. There is no published date for completion of these reviews. | 1. The Clerk to write to Safer Essex Roads Partnership for an update on the timetable for completion. | Open |  | Clerk | 2024-04-15 |  | Carried forward from previous period Clerk to update next meeting. The H&TC meeting (17/4/2023) noted that the Clerk will chase a response to the outstanding query. 24/07/2023 meeting - noted that Hierarchy Review continues with no agreed issue date. Agreed to monitor progress, but to ensure any relevant GWPC representations continue to be fed into the process. 25/09/2023 meeting - no update 12/02/2024 meeting - no update - Carry forward. 15/04/2024 meeting: No update. Carry forward. CARRIED FORWARD FROM 2023/24 TRACKER
2023-04-17 | 5 | To note the latest positions and developments for items on the Committee’s action tracker document and to agree actions and/or make any recommendations to the Council to facilitate their completion and closure. The meeting noted that the Essex Highways defects tracking map shows approximately 80 outstanding defects of one type or another on or immediately adjacent to the B1008 in Ford End (between Kings Farm and Ford End School). | 1. Chair and Clerk to draft an e-mail to Essex Highways to confirm the status of defects noted on action tracker (as some seem to have been resolved without the EH database having been updated). 2. Clerk to request details of all defects shown as outstanding on the Essex Highways website that are in the Parish of Great Waltham. 3. Clerk to establish the existence (or not) of Playground signage for the Great Waltham Recreation Ground at both entrances. | Open |  | Cllr Gilbert & Clerk | 2024-04-15 |  | Carried forward from previous period 24/07/2023 meeting 1. & 2. requests have been made but no response to date. 12/02/2024 meeting: No responses - agreed to close these actions. 3. Clerk confirmed no playground signage at Great Waltham. The meeting agreed to establish position at FE & HS grounds, and will consider whether to discuss requesting provision of signs at next meeting. 25/09/23 meeting - Confirmed no signage at Gt Waltham. Signage at FE confusing. HS has one sign. Clerk & Handyman to confirm with photos. 12/02/2024 meeting - Report to be prepared for LHP. 15/04/2024 meeting: Report to be prepared for LHP consideration, but recognised issue unlikely to advance without resorting to self-funding option if LHP validation obtained. CARRIED FORWARD FROM 2023/24 TRACKER
2023-04-17 | 12 | To recommend that the Council lobbies for measures to ensure the B1008 is not used as a preferred route once the NE by-pass is completed (given that it would remain the shortest and fastest route between the A120 at Gt. Dunmow and the new by-pass junction on the A131 at Gt. Leighs). Because it would still be the shortest and fastest route, the meeting identified the prospect of the B1008 remaining the road of choice for drivers (and their satnav systems) despite the suggestion that the new by-pass would automatically draw traffic away. | 1. Recommend to the council that it lobbies for measures to ensure the B1008 is not used as a preferred route once the NE by-pass is completed. | Open |  | Cllr Gilbert | 2024-04-15 |  | Carried forward from previous period 24/07/2023 meeting - carry forward to next meeting as further investigatory work required to recommend position to adopt. 25/09/2023 meeting - Developer led scheme. This needs the actual scheme to be designed before action can be progressed. 12/02/2024 meeting - Partial development is likely to proceed to Wheelers Hill roundabout. Maintain watching briefing for developments. 15/04/2024 meeting: Maintain watching brief. CARRIED FORWARD TO 2024/25 TRACKER
2023-04-17 | 13 | To recommend that the Council lobbies for the reinstatement of the signage at Sheepcotes roundabout, which directs traffic to the A131/A120, so as to reduce use of the B1008. The meeting discussed securing access to the actual policy wording relevant to this item. The incongruity of having the originally installed signs which had the effect all parties desired (of signposting the use of the A131/A120 rather than the B1008) replaced by ones which now have the opposite effect simply to satisfy a policy guidance remains manifestly apparent. | 1. Recommend to the council that it lobbies for the reinstatement of signage at Sheepcotes roundabout which directs traffic to the A131/A120. | Open | 15/04/2024 (6) | Cllr Gilbert | 2024-04-15 |  | Carried forward from previous period 24/07/2023 meeting - carry forward to next meeting as further investigatory work required to recommend position to adopt. 25/09/2023 meeting - Developer led scheme. This needs the actual scheme to be designed before action can be progressed. 12/02/2024 meeting - No developments - carry forward. 15/04/2024 meeting: No developments. [Discussion at April monthly meeting made clear that Highways policy unlikely to alter for signage change to be considered. Discuss at next H&T Committee re: on whether to pursue copy of policy]. CARRIED FORWARD FROM 2023/24 TRACKER
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE203002 Barrack Lane j/w Cherry Garden Road, Great Waltham - Footway Improvements |  | Open |  | H&TC | 2024-04-15 |  | Carried forward from previous period Design team advised footway may need regrading and could need land acquisition. Due to change in scheme scope agreed at June 2022 panel to make this a Design Only as first stage Design costs - £6,500 17/04/2023. Design agreed. Works delayed due to funding prioritisations, but completion expected in 2023/24. 17/07/2023: Works schemed for 2023/24 - yet to be commenced. 24/07/2023 meeting - noted work yet to commence, continue to monitor progress. 25/09/2023 meeting - work still to commence, continue to monitor progress 12/02/2024 meeting - no update. 15/04/2024 meeting: Situation with LHP remains unclear in terms of revised schedule for agreed works. Carry forward and continue to monitor progress. CARRIED FORWARD FROM 2023/24 TRACKER
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE222014 Ringtail Green, Great Waltham - Gateway signs |  | Open |  | H&TC | 2024-04-15 |  | Awaiting highway boundary information 17/04/2023. Works delayed due to funding prioritisations, but completion expected in 2023/24. 24/07/2023 meeting - await funding decision, continue to monitor. 25/09/2023 meeting - awaiting funding decision, continue to monitor. 12/02/2024 meeting - Carry forward. 15/04/2024 meeting: Situation with LHP remains unclear in terms of revised schedule for agreed works. Carry forward and continue to monitor progress. CARRIED FORWARD FROM 2023/24 TRACKER
2023-07-24 | 9 | Action Tracker review item LHP scheme: LCHE223011 Great Waltham Primary School, South Street, Great Waltham - Signage improvements |  | Open |  | H&TC | 2024-04-15 |  | Validation - Recommends changing Patrol sign to School, need to check sign/pole as could be sticker or may need new pole/sign Total scheme budget - £6,500 17/04/2023. Low-cost scheme. Potential stickers rather than new signs. Funding decision pending. 24/07/2023 meeting - await funding decision, continue to monitor. 25/09/2023 meeting - await funding decision, continue to monitor. 12/02/2024 meeting - carry forward no information available. 15/04/2024 meeting: Situation with LHP remains unclear in terms of revised schedule for agreed works. Carry forward and continue to monitor progress. CARRIED FORWARD FROM 2023/24 TRACKER
2023-07-24 | 10 | To consider the report Proposals to address the outstanding maintenance works on the footways alongside the B1008 through Ford End and for the introduction of enhanced traffic calming measures through Ringtail Green, Ford End circulated with the agenda, and to agree recommended actions The meeting acknowledged the contents of the report and agreed that because the situation remains unsatisfactory the recommended actions cited should be pursued. | These actions are recommended to the full council for approval: 1. To further lobby all relevant authorities and agencies for traffic calming and maintenance works as they affect the footways alongside the B1008 in Ford End and the road through Ringtail Green. 2. In particular, as a minimum, given the new evidence cited in this paper, to lobby for the reconsideration of all previously contemplated schemes (that is, Quiet Lane status for the lane, ‘SLOW’ road markings at either side of the bend, and advisory road signs at either side of the bend, e.g., maximum speed and chevrons). This would be achieved by working with its city and county council representatives to formulate submission documents for improvement schemes. 3. To request a meeting with Essex Highways to discuss the interpretation of ATC data and to seek its expertise on the range of traffic calming measures available for the road through Ringtail Green (notwithstanding any current absence of funding). That is, to understand what other innovative solutions it can recommend as the subject matter expert. 4. To seek clarification of how works previously undertaken by the Highways Rangers will be carried out in future. Even if this results in an understanding that such works will not now be completed, GWPC will be able to confirm to its parishioners that a valuable service has been withdrawn and alert them to the possible consequences. 5. To establish and communicate the mechanisms available for individual residents and businesses in the parish to complain about the loss of amenity (state of the footways alongside the B1008) and the hazards imposed because of increased pedestrian traffic on the road through Ringtail Green. And in addition, to draft a template wording which complainants could consider using. | Open |  | Cllr Gilbert | 2024-04-15 |  | 24/07/2023 meeting - items to be added to agenda of August monthly meeting. 25/09/2023 meeting - awaiting confirmation of the Direct Funding option and costs involved in the schemes. 12/02/2024 meeting - carry forward no information available. 15/04/2024 meeting: Carry forward. [Footway issues have been reported for potential inclusion in latest member-led scheme. Await developments]. CARRIED FORWARD FROM 2023/24 TRACKER
2024-02-12 | 8 | To review the Council’s public transport representative role. | (1) Pause the role while the issues are monitored for volume and impact at each H&T Committee meeting. | Open | 22/02/2022 (7) | H&TC | 2024-04-15 |  | 15/04/2024 meeting: Continue to monitor need for representative. CARRIED FORWARD FROM 2023/24 TRACKER
2024-04-15 | 6 | To receive updates on all open Action Tracker items (based on the Tracker document circulated with the agenda). A number of items were reviewed and closed. The tracker tab will be updated and published on the website. The chair agreed to write to ECC Cllr. Steel for updates on the Functional Route Hierarchy Review, playground signage for Great Waltham Recreation Ground entrances and reinstatement of signage at Sheepcotes roundabout. |  | Open | 22/1212 24/07/2023 (9) 17/04/2023 (13) | Cllr. Gilbert | 2024-04-15 |  | CARRIED FORWARD FROM 2023/24 TRACKER
2024-04-15 | 8 | To consider the current position in relation to approved Local Highways Panel schemes. Noted we have three schemes in the LHP process. It was noted that the LHP system is under review. The chair agreed to write to ECC Cllr. Steel for an update on the direct funding process for introducing a Quiet Lane through Ringtail Green. |  | Open |  | Cllr. Gilbert | 2024-04-15 |  | CARRIED FORWARD FROM 2023/24 TRACKER
2024-04-15 | 9 | Discuss the Blue line painting and new signs for public car parking spaces in Great Waltham Village Hall car park. Will the Parish Council do this or will they contribute to line painting by an outsourced contractor. It was noted that in the contract maintenance of parking bays falls to the Village Hall, albeit Council members had previously been involved in the last works in this respect. | (1) Clerk to locate the blue paint and give to Cllr Palmer (for use by the Village Hall). | Open |  | Clerk | 2024-04-15 |  | CARRIED FORWARD FROM 2023/24 TRACKER