## Sheet1
Great Waltham Parish Council - Monthly Meeting Action Tracker
May 2024 - April 2025 inclusive (with carried forward items)
2024-07-15
Meeting Date | Agenda Item Ref. No. | Agenda Item (in bold) with narrative from meeting discussion | Resolution(s)/Action(s), if any | Open/ Closed | X/refer | Action Owner(s) | Last Updated | Date Closed | Update Log
2023-08-22 | 23/1607 | Proposal for SID pole at Church end on approach the Village. • This location is the descent into the village on Main Road travelling from Howe Street. • The Parish Council has 7 poles in the Parish funded by the Local Highways Panel (LHP), but LHP has no budget for additional ones. • Speed Watch volunteers do not currently have the authority to monitor from this new position. • The City Council ‘lamppost’ scheme for housing speed indication devices (SID) has not yet been built into a process to roll out for use. | 1. To ask the Great Waltham Speed Watch group to investigate a new site in the area. | Open | H&TC 24/07/2023 (12) | Cllr Jenkins | 2024-07-15 |  | 18/09/2023 meeting: SID pole approval request to be made via LHP 16/10/2023 meeting: Outcome of application awaited. 20/11/2023 meeting: No update available. Carry forward. 12/12/2023 meeting: Application still outstanding. Await response. 15/01/2024 meeting: Application response still awaited. Cllr Steel to chase. 19/02/2024 meeting: Item not discussed - agreed carry forward to next meeting. 22/04/2024 meeting: Response still awaited. Action owners will chase. Carry forward. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Obtain action owners update at next meeting. 20/05/2024 meeting: No further update - Cllr. Steel to chase response. 18/06/2024 meeting: No update yet. Cllr. Steel to continue to chase. Expectation is that proposed site will be unsuitable for Speed Watch haven. 15/07/2024 meeting: Cllr. Jenkins to continue to chase for update. 09/08/2024: Action owner's update required.
2023-08-22 | 23/1609 | Given that the Ringtail Green Quiet Lane (and other suggestions), failed to be supported by the Chelmsford LHP committee due to more pressing priorities, it is proposed that GWPC submit and fully fund the schemes via the Direct Works process (noting that the LHP will not add any funding) • The meeting noted that the road at Ringtail Green meets the technical specifications for a Quiet Lane, but that LHP members have considered the request and have decided to spend the funding on what are seen as higher priority areas. • It was also noted that other previously submitted schemes for Ringtail Green and the immediate areas are unlikely to obtain favourable considerable without evidence of a significant deterioration in the issues which have been identified. • The meeting acknowledged the prioritisation/funding pressures which exist for higher authorities’ decision-makers. • It was noted that a direct process is available that the Parish Council pays for the work, but it still follows the LHP process. Works will be undertaken by Ringway Jacobs. • A proposal (per the agenda item) was made and seconded. • An amendment (as shown in the resolution below) was made and seconded: • A named vote was called: Abstain : Cllr McDevitt Support amendment: Cllrs Gilbert, Steel, Page, Jenkins, Palmer, Stephenson, Martin and Bradley • The amendment was carried. | 1. Given that the Ringtail Green Quiet Lane (and other suggestions), failed to be supported by the Chelmsford LHP committee due to more pressing priorities, it is proposed that Great Waltham Parish Council will submit an enquiry for the costs associated with a direct works application via the Direct Works process (noting that the LHP will not add any funding) | Open |  | Clerk | 2024-07-15 |  | 18/09/2023 meeting: Clerk to submit works request to Essex Highways Solutions so that Council can consider further action/self-funding options. 16/10/2023 meeting: Clerk awaiting clarification of process to ensure all submissions from PC side have been completed. 20/11/2023 meeting: Clerk to chase update on the validation process. 12/12/2023 meeting: Current position remains to be established. Review at next meeting. 15/01/2024 meeting: Clerk reports EHS feedback still awaited. Carry forward. 19/02/2024 meeting: Item not discussed - agreed carry forward to next meeting. 16/04/2024: At the H&TC meeting on 15/04/2024 it was noted that current LHP schemes are being re-assessed. Once a self-funded scheme application and validation has been completed there should be a clearer idea of whether this scheme is acceptable (i.e. validated) and its costs. 22/04/2024 meeting: Position in entry for 16/04/2024 above noted. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: No update due to current review of LHP. 20/05/2024 meeting: Await response and chase as necessary. 18/06/2024 meeting: Cllr. Steel has received verbal confirmation that scheme (and costs) has been validated, but is yet to receive written advice. He will continue to press for written update so that GWPC can consider its options. Action owner reassigned to Cllr. Steel. 15/07/2024 meeting: Discussion now between PC and EHS. Clerk has queried apparent cost increase from previous estimate. Clerk to chase response. 09/08/2024: Action owner's update required.
2024-01-15 | 23/1733 | Discuss the request from the community network to change the colour of the Banbury tree lights to white and have them higher in the tree for the Christmas tree festival 2024 See also the comments under item 23/1723. The oak tree in Banbury Square used to display the lights needs some identified tree cutting work to be completed by a tree surgeon, so it may be that work to (re)install lights can be effected at the same time. | (1) In consultation with the Community Network, investigate the purchase of new Christmas tree white lights that will cover the Banbury Square tree. | Open |  | Cllr. Palmer | 2024-07-15 |  | 19/02/2024 meeting: Item not discussed - agreed carry forward to next meeting. 22/04/2024 meeting: Supply options being investigated with a view to possible funding request. CARRIED FORWARD FROM 2023/24 TRACKER 20/05/2024 meeting: Supply options continue to be investigated. Carry forward. 18/06/2024 meeting: No update from action owner, but believed being progressed. 15/07/2024 meeting: No update available. Carry forward. 09/08/2024: Action owner's update required.
2024-02-19 | 23/1760 | Review the quote to replace the play area gates at Great Waltham Recreation Ground. A quote from JCM was reviewed for £820 for 2 metal gates and £1,600 for 2 wooden gates. The financial regulations were waived due to a need to get the gates replaced in a short timescale. | (1) Install metal gates due to the reduction in maintenance, longer planned long life and lower cost. (2) Clerk to appoint JCM to undertake the gate work as soon as possible. | Open |  | (2) Clerk | 2024-07-15 |  | 22/04/2024 meeting: Noted that option to install gates may be affected by findings and recommendations of Recreation Ground working group. Await developments there with a view to reassessing installation plan. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Due to the proposed play area refresh it was agreed at Recreation Committee to pause this initiative as costs are £1,000 per gate. Action owner update required. 20/05/2024 meeting: Agreed to proceed per 12/05/2024 update. Leave action open to monitor developments. 18/06/2024 meeting: Meeting agreed to monitor developments. 15/07/2024 meeting: Continue to monitor developments. 09/08/2024: No developments, continue to monitor..
2024-02-19 | 23/1768 | Confirm the Council’s previous decision to purchase and locate a Defibrillator and Cabinet at Broad’s Green. | (1) Approval to spend £3,102 (incl. VAT) with The Community Heartbeat Solutions for Broad’s Green and install in the telephone box. | Open |  | (1) Clerk/Cllr. Martin | 2024-07-15 |  | 14/04/2024: Defibrillator purchased. Work to renovate the telephone box prior to installation in progress. 22/04/2024 meeting: Position above noted. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Defibrillator has been delivered. Awaiting clarification of landowner's permission before repainting telephone box and installation commences. 20/05/2024 meeting: Update of 12/05/2024 noted. 18/06/2024 meeting: Noted that refurbishment of telephone box remains outstanding. Volunteer resource has been identified and materials passed over, but work yet to commence. Council yet to receive landowner's rights of access contract for consideration. Defibrillator has been purchased. 15/07/2024 meeting: Original volunteer resource has been unable to complete the work. Contingency plan (for replacement volunteers) activated. 09/09/2024: Refurbishment of kiosk completed by new volunteers (Cllr. Martin and Steve Huggins) - Parish News article submitted extending thanks for work. Defibrillator installed and now live. Recommend close this action.
2024-03-19 | 23/1802 | Discuss an in principle expenditure of up to £1000 on replacing the wooden bridge on the tower units at Great Waltham recreation ground. The Clerk produced a report showing available options to replace the bridge which is starting to rot. | (1) The Parish Council approved expenditure up to £1,000 for this purpose. | Open |  | (1) Clerk | 2024-07-15 |  | 14/04/2024: Procurement process in progress. 22/04/2024 meeting: Position above noted. CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Paused until after the annual inspection. 20/05/2024 meeting: Update of 12/05/2024 noted. Await annual inspection and then consider next steps. 18/06/2024 meeting: Item not reported in annual inspection, but likely the rot identified will get worse. Contingency option instead of replacing bridge would be to decommission it and have two unconnected towers. Progress on Recreation Ground project may determine best course of action. 15/07/2024 meeting: Continue to monitor condition of equipment. 09/08/2024: Continue to monitor.
2024-04-22 | 23/1825 | To discuss and agree whether Great Waltham Parish Council should join the Parish Paths Partnership scheme offered by Essex Council Highways and in what capacity. Option to take on the annual budget and arrange the cuts. Option to work with ECC on a voluntary scheme to maintain the footpaths. Work would cover surveys, signage liaison with landowners and general maintenance. | (1) The Parish Council supports the scheme subject to resource of volunteers. | Open | 24/1923 | (1) Cllr. Bradley | 2024-07-15 |  | CARRIED FORWARD FROM 2023/24 TRACKER 12/05/2024: Request for volunteers made at Annual Assembly - further request to be made via Parish News. Action owner to provide update on latest position. 20/05/2024 meeting: Cllr. Bradley confirmed some initial interest and will submit article to next edition of PN. Carry forward for further updates. 18/06/2024 meeting: Cllr. Bradley confirmed will submit article to Parish News to seek volunteers needed to make engagement with the Partnership worthwhile. 15/07/2024 meeting: See item 24/1923 (PC agreed to the arrangement of arrange another meeting with Essex Highways with the intention of Great Waltham Parish Council joining the Parish Paths Partnership). Leave open to monitor progress in entering the Partnership). 09/08/2024: Action owner's update required.
2024-05-20 | 24/1849 | Review and adoption of the Financial Regulations. It was noted that a new model has been issued for 2024. | (1) Adopt the current version. (2) The latest NALC revised version to be shared with the members | Open |  | (2) Clerk | 2024-07-15 |  | 18/06/2024 meeting: (2) Agreed that Clerk and Cllr. Gilbert would review new model regulations to identify material changes and offer information and new wording to members under future agenda item. 15/07/2024 meeting: Ongoing - carry forward. 09/08/2024: Ongoing - carry forward.
2024-06-18 | 24/1898 | To agree reviewers for those Council policies/documents highlighted with red shading on the Review Schedule document circulated with the agenda. Various policies were allocated to the members for review and updates as appropriate. | (1) Members to submit items for proposed changes to existing policies (or indicate no changes) at July or August monthly meetings. | Open |  | Various/Clerk | 2024-07-15 |  | 15/07/2024 meeting: Ongoing. Some items submitted for July meeting. Carry forward. 09/08/2024: Action owners' update required.
2024-06-18 | 24/1899 | Support the Recreation Committee’s recommendation to use the donated seat at Great Waltham recreation ground as the memorial seat | (1) The donated seat to be offered as the memorial seat. | Open |  | Cllr. Palmer | 2024-07-15 |  | 15/07/2024 meeting: No update available. Note action owner is Cllr. Palmer to contact donor. Carry forward. 09/08/2024: Action owner's update required. And see Recreation Committee's recommendations in agenda items at 18/08/2024 meeting.
2024-06-18 | 24/1902 | To consider short- and/or mid-term investment opportunities to take advantage of higher interest rates. • The Council holds reserves which could be invested in financial products which yield higher interest rates than under current arrangements. • The risk associated with losing interest on a higher earning product in the event of the need for early access was discussed. Such a risk was considered to be low. • Members requested confirmation that instant/quick access to any capital sum invested in this way would be available (even if interest earned might be forfeited). | (1) The investment of £25,000 in a one-year CCLA Investment Management Ltd. financial product was approved, subject to confirmation of any notice period. | Open |  | (1) Clerk/Cllr. Gilbert | 2024-07-15 |  | 15/07/2024 meeting: Members not agreed that product approved at previous meeting was for low-risk product. Add agenda item to August meeting to agreed way forward. Cllr. Gilbert to add agenda item. 09/08/2024: Item added for agenda of 18/08/2024 meeting.
2024-06-18 | 24/1903 | To receive an update from the village green (VG150), Ford End working group, to agree the Council's position on any/all related matters and to provide further instructions for the group. • The working group has met and discussed the Village Green. VG150 is still recorded by Essex County Council in the Register of Town and Village Greens as a village green. • ECC do not own the land but do have highways boundary rights over part of VG150 and this remains applicable irrespective of ownership. • Essex Highways met with and have written to the owners of Eagle Cottage and confirmed that the hedge and fence must be removed due to the sight hazard created for road users. • A meeting was being proposed with the owners of Eagle Cottage who have issued a document to the Council supporting their actions to date. • The submission of the adverse possession claim was noted. This introduces a legal element which the Council will need to address to protect its interests. • The holes created by the missing posts were also noted. | (1) If possible, working group members to set up a face-to-face meeting within 2 weeks with the owners of Eagle Cottage to discuss the correspondence handed to the Council as the meeting. (2) The Parish Council approved a budget of up to £1,000 for initial legal costs as it seeks advice to protect its interests. (3) Clerk to raise the concern with Essex Highways that the missing posts and the holes created are a potential hazard to users. | Open | 23/1821 24/1798 24/1934 24/1938 | (1) Cllr Gilbert (2) Clerk (3) Clerk | 2024-07-15 |  | 15/07/2024 meeting: See agenda item 24/1934. (1) "After reviewing and reflecting on the information provided, the view is that the possible meeting offered previously (before the Council was aware of the adverse possession claim) has become problematic because of the legal route which has been taken". (3) "The Council has received no further information or update from Highways regarding the understanding that it (Highways) has indicated the fence and hedge installed on VG150 must be removed from its current position". Carry forward for further updates. 09/08/2024: Update 18/08/2024 meeting with developments.
2024-07-15 | 24/1920 | Discuss and approve the 2024 Risk register (circulated with the agenda). Some updates required on the document for 2024. | (1) Cllr Gilbert to update and circulate a draft before the next meeting. | Open |  | Cllr. Gilbert | 2024-07-15 |  | 09/08/2024: Item added for agenda of 18/08/2024 meeting.
2024-07-15 | 24/1921 | Discuss the Internal Audit report and review suggested actions. Following issues raised by the auditor: 1. The minutes do not show that a financial/ reputational risk assessment was carried out during the year. The Council must make certain that this issue is addressed every year. 2. A Parish Meeting must be held annually between 1st March and 1st June (both inclusive). The Annual Assembly took place on 5th June 2023. 3. The External Auditor’s report was not considered by the Council. The Council must consider the External Auditor’s report and if applicable note an action plan for dealing with any qualifications. | (1) The Council will undertake a financial/ reputational risk assessment and confirm at the August 2024 meeting. (2) The Council notes the dates and that the reason for the short delay in 2023 was caused by the logistics of securing a suitable venue. The 2024 meeting was held on the 7th May 2024. The 2025 meeting will be planned within the required dates. (3) The External auditor’s report will be considered when received later in the year and an agenda item has been planned for the Council September 2024 meeting. | Open |  | (1) Cllr. Gilbert (2) Clerk (3) Clerk | 2024-07-15 |  | 09/08/2024: (1) Item added for agenda of 18/08/2024 meeting. (2) Close this item. (3) Close this item.
2024-07-15 | 24/1926 | To agree the Finance & General Purposes Committee’s recommendation that the Council meets with Great Waltham Village Hall to review the existing agreement to lease car parking spaces from the Village Hall. | (1) Agreed. Cllr Gilbert and Cllr Micklem to represent the Council and to arrange a meeting. | Open |  | Cllrs. Gilbert & Micklem. | 2024-07-15 |  | 09/08/2024: Request submitted to chair of VH for meeting - response awaited.
2024-07-15 | 24/1935 | Discuss the Ford End Traffic issues including the recent traffic accident. Members noted the extent of the previous work of the Parish and County Councils over the last 15 years or so, and that while the road was downgraded from the A130 to the B1008 road it remains designated as a priority (PR1) route which significantly restricts the scope for new traffic calming measures. It also remains the alternative diversionary route to the A120 if there are any problems on sections of the A120 which cannot be accommodated by using the B1256. Changes to the Ford End Section of the B1008 have included: • Ford End Village Gateway signs. • Ford End flower planting by the Village Sign. • 40mph buffer zone at northern end of the Village. • 40mph buffer zone at the southern end of the Village. • Vehicle activated signs (VAS). • Raised footway kerbs at bus stops. • 20mph wig-wag signs past the school. • PR1 status – requests to change this status has been raised. • A Speed Watch group operates (records speeding vehicles – not volumes). • Alternative entrance to the school has been adopted. Members noted the considerable energies dedicated to the (ultimately unsuccessful) average speed camera project. They also noted the concerns from residents regarding the perceived increase in the volume and speed of vehicles, and agreed that up-to-date quantitative data will help to inform the nature of any future debate and lobbying activity. It was noted that the cost of commissioning an automatic traffic count (ATC) survey would be c.£350. The earliest date for a new, representative survey is likely to be in September (when traffic volumes ‘normalise’ after the summer holidays). | (1) Request/commission an automatic traffic count from Essex Highways for September. (2) Replicate the location of the previous speed checks for comparison purposes. | Open |  | (1) Clerk (2) Clerk | 2024-07-15 |  | 09/08/2024: Actions owner update required.