## Tracker of Actions
Minute Reference | Detail of resolution | Date Originated | Action By | Last Updated | Current position
22/1097 | Consider proposed revisions to those policy documents contained in the file circulated prior to the meeting • Allotment allocation policy • Disciplinary and grievance policy • Financial regulations, • Grievance procedure for employees, • Media relations policy, • Policy statement on the recruitment of ex-offenders • Training policy Resolution The Policies were approved Resolution Cllr Gilbert to draft an approved supplier process | 25.04.2022 | Cllr Gilbert | 16.11.2022 | Process has been drafted. Draft Supplier approval process has been written. Two approvers are currently reviewing the document. - Is this still required ? Both approvers have completed feedback
22/1172 | Discuss replacing the junior goal at Great Waltham recreation ground Some parents have approached the Parish Council for use of the recreation ground for football training. Consideration to remove the old single goal that needs work. £721 portable single junior goal as a guide. Around £1000 for a pair of goals. Resolution: Cllr Martin to get 3 quotes for moveable goals Resolution Purchase new sockets and Postcrete. Descale the posts and repaint with appropriate paint. Expenditure of up to £250 approved. | 13.06.2022 | Cllr Martin | 19.12.2022 | To be discussed t the Recreation Meeting on the 08.08.2022 Item was discussed and options put in to a report for the members of the committee.. Recommendation to refurbish the Junior Goals and insret new spikes in to the pitch. Poste Crete and Sockets to be purchased. Sockets have been purchased and will be dropped off at the Pavilion Handyman is working on the posts.
22/1174 | Discuss membership of the Emergency Planning Sub Committee (Chair, Vice Chair plus three councillors representing all areas of the Parish) and if it is still required. A report was placed on the website with the agendas. Resolution An emergency plan to be drawn up by Cllr Steel Resolution Dissolve the emergency planning committee Resolution Cllr. Steel to discuss a revision with Karen Buttress the Chelmsford City Council Community Safety Lead officer. | 13.06.2022 | Cllr Steel | 19.12.2022 | August - No update SeptemberNo update October - No update No Update Dec- Document has been issued to be kept as live document and discussed at the January 2023 meeting. March - Defer
11 | Inventory at the Pavilion | Preparation of inventory | Cllr Gilbert | 19.12.2022 | 18/3/2022 (WG): Await purchase/installation of cleaning equipment, items from current Parish Office. 12/04/2022 (WG): Awaiting installation of equipment, furniture etc. 26/05/2022 (WG): Agreed now in position to create inventory. AM to provide list of purchased items to SG to create document in 'house' style. Action to remain open, but transferred to PC monthly action tracker (Clerk to arrange). The Inventory list was provided 30.05.2022. Cllr Gilbert to provide the data in the in-house style A version is held in the Pavillion Hire file . Final Version to be Issues in january 2023.
22/1230 | Resolution The Clerk to contact the War Memorial Trust to understand options and time frames and report back to the Parish Council. | 15.08.2022 | CLERK | 19.12.2022 | CLERK AWAITING UPDATE Clerk to seek a new plan to cover 2023. WMT have asked for a new set of pictures. Clerk has sent in pictures. Awaiting an update. December.
22/1293 | The Parish Council has all the necessary documents and policies in place to achieve Local Council Award Scheme (LCAS) Foundation level and wishes to proceed to adjudication paying all relevant fees. • £50 registration fee to NALC. • £80 accreditation fee to EALC. Resolution Approved to start the process for LCAS accreditation. | 17.10.2022 | Clerk |  | LCAS process started. GWPV is regiestered with EALC ro start the process. £50 Invoice has been received.. Clerk arount hafway through paperwork. The Paperwork has been submitted for review.
22/1322 | To note feedback from the RCCE Village Hall training course and to agree further actions in relation to the possibility of future involvement of the Council in the administration of Great Waltham Village Hall Resolution: The Council to secure full membership of RCCE to obtain full access to its legal and best practice expertise in relation to village hall management and associated issues. Resolution: The Council to initiate formal contact with the village hall trustees to understand the possible contexts of any future request to the Council for involvement in the administration of the village hall. | 22.11.222 |  | 19.12.2022 | Clerk has written to the RCCE and asked to be invoiced.
22/1318 | To discuss and agree arrangements for the Council administered parking spaces at the Blossom Way development – Cllr Gilbert. The meeting noted the current absence of a response to Cllr. Steel’s enquiry to seek clarification from CHP of its position (see 22/1300 above). It also discussed possible interpretations of the current terms and conditions in relation to the definition of commercial vehicles and whether their actual use is relevant (e.g. the circumstance where a vehicle is used exclusively for social, domestic and pleasure purposes, even though designated as a commercial vehicle). Resolution: The Council agreed to continue to monitor the situation in anticipation of receiving clarifications of permitted uses under the lease | 22.11.222 |  | 19.12.2022 | Permison for domestically used Commercial vehicles to use the CHP parking .
22/1314 | The Recreation Committee proposes that the Council brings forward one of the 2023 projects and purchases an 8ft storage container to be positioned beside the Pavilion at Great Waltham recreation ground – Cllr Martin. Cllr. Martin detailed the advantages of installing the container in terms of consolidating the storage of Council assets at a more convenient location (principally for the handyperson) and freeing up storage space in the Pavilion itself. The potentially unsightly nature of the container was commented upon, together with the need, in any event, to both establish any planning issues and engage with neighbouring residents who may be affected. The motion as indicated was proposed by Cllr. Martin, seconded by Cllr. Huggins. The Council voted 7 to 2 in favour. Cllr. Steel asked that his objection to the proposal be noted. Resolution: The Council agrees to purchase an 8ft storage container to be positioned beside the Pavilion at Great Waltham Recreation Ground. Resolution: The Council will make all necessary enquiries to establish the position in relation to securing planning consent, if needed. Resolution: The Council will contact neighbouring residents to inform them of its intentions. | 22.11.222 |  | 19.12.2022 | Planning - Chelmsford City Council Planning. Pre Application advise would be required. Its 1.5m from the conservation area. 8 foot cube container proposed.
22/1348 | Discuss the proposal for the Parish Council to assume responsibility for the provision of defibrillators in the Great Waltham Parish. There is a briefing note on the agenda area of the Parish Council website. Ford End and Great Waltham units are available on ‘the circuit’. Howe Street is still showing as unavailable. Littley Green has the same experience. North End uses the Community Heartbeat Trust and they have a very good experience of the interface. Weekly testing of the units is mandatory. Resolution: The Parish Council will assume responsibility for the provision and maintenance of units in Great Waltham Parish and will provide an additional unit for Broads Green. Resolution: The Council approves the engagement with the Community Heartbeat trust for the maintenance and provision of defibrillators units for the Parish from April 2023 in line with our budget | 19.12.2022 | Cllr Martin | 19.12.2022 | Briefing note issued for discussion.
22/1290 | Review the provision of defibrillators within the Parish and consider whether the Parish Council should assume a role in their administration and availability. • Previously, an ex-parish councillor raised sufficient funds for three defibs and three lockable, temperature-controlled cases. • These units were purchased from SADS - Sudden Adult Death Trust. However, initial promises made about free unit inspections, free replacement of batteries and pads for the Defibs have not materialised. • One of the units was lost by the hospital and was replaced at their cost in 2020. • Units are registered on ‘The Circuit’ database but continue to show as unavailable. This has been put down to them having been deployed by the ambulance service and the system is awaiting an update from The Circuit, which takes in excess of 2 months. • The units have to be checked to ensure the batteries and contents are in order and the checking date is fed back to the network. • Replacement batteries for the two older units (Howe Street and Ford End, installed in 2016) will be needed, as they are at the end of their life. Defibs have a life span of between five and seven years based on usage and on that basis, it is assumed the FE and HS units are due for replacement in the next 12 months. • Replacements suitable for public use are available for £1,180 + VAT, cabinets if necessary are extra. • There are numerous defib providers including the Sudden Adult Death Trust, Community Heartbeat Trust, St John’s Ambulance and the British Heart Foundation. • It was stated that when the current units reach the end of their life, they will be returned to the Sudden Adult Death Trust. • Currently further information is awaited from the ex-parish councillor regarding the hosts, along with further questions on maintenance and replacements. Resolution In principle agreement that a budget for replacement defibrillators and heated cases is included for 2023/2024, including for ongoing maintenance depending on the age of the units. | 17.10.2022 | Sub Committee | 30.01.2023 | Sub Committee Formed and working
22/1368 | Following the resolution that the Parish Council will assume responsibility for the provision and maintenance of defibrillators discuss the proposal to form a working group to advise the Council and ensure a smooth transition. Resolution: Agreed Cllrs. Lockwood, Jenkins, Gilbert, and Martin will form a working group and report back. | 16.01.2023
22/1369 | Following the resolution to make all necessary enquiries to establish the position in relation to securing planning permission for the Pavilion storage container, agree to submit the planning enquiry. Resolution Agreed that pre-advice from Chelmsford City Council is to be sought for the placement of an 8-foot storage unit, with agreement also for payment of any associated fees. | 16.01.2023
22/1392 | Proposal for a sign at the Recreation Ground, perhaps temporary and placed only on the nights the Parish Council is present, pointing in the direction of the Pavilion. With the increased hire of the building and sometimes out of parish attendees, a sign would be beneficial to help users locate the building. Resolution A permanent name sign to be up to £50 to be made and installed on the noticeboard by the front gate. | 20.02.2023
22/1393 | Proposal for a location sharing arrangement between the South and North Wards for monthly meetings. Resolution: Agree to hold a quarterly meeting at Ford End. Resolution: Clerk to investigate what days are available for meetings at Ford End Village Hall. | 20.02.2023
22/1394 | To consider the Council’s involvement in events associated with the coronation of King Charles III. Last year information from national coordinators for Jubilee events was forthcoming and well prepared. This has not been the case for the coronation – the information the Council has received to date has been quite general. Aside from the proposed Ford End event, it is expected that Howe Street will have a picnic and North End will have a tea event. Resolution: Clerk to contact the various organisations that were involved in the Jubilee events to understand if they are planning anything or need any support from the Parish Council | 20.02.2023
22/1396 | To receive an update from RideLondon from Christopher Davey of London Marathon events on the 2023 and to discuss and agree any actions for the Council. • The event returns on Sunday 28th May. This year it is a one-day event only. • Town and village applications to support the event will be accepted by RideLondon • For businesses affected by the events there is support from RideLondon Events and Essex County Council. • There is a rolling one-year contract arrangement, the event being a legacy from the London Olympics. One Charity raised over £750,000 at last year’s event. • On the day there will be 3 cycle events on the day (not a race). 30, 60 and 90 miles. The longer event affects the parish. The affected roads will be closed from approximately 06:30 to 16:30. However, the organisers are working with councils to optimize opportunities to ensure there are regularly open crossing points along the route. • RideLondon is working to minimise the impact this year. The times of the road closures will be reduced compared to last year. A Google Maps feature will be live with the diversions and vehicle crossing points. Notifications are being sent to households both on the route and other who will be affected. It was agreed that the Council should maintain close links with the organisers to deal with any questions, queries and feedback it receives from residents. It will help facilitate a proposed pre-race drop-in discussion event. Resolution: Clerk to consolidate requests from the Council to RideLondon Events | 20.02.2023
22/1399 | Discuss and accept the Recreation Committee’s proposal to continue with the development works at Ford End Recreation Ground in line with the results of Consultation 2. Resolution: The Parish Council accepts this proposal. | 20.02.2023
22/1400 | Approve the Recreation Committee’s recommendation for the Howe Street Recreation Ground Multi Play replacement. The recreation committee recommends the spend of £20,398 for the Pandora metal multi play unit which is guaranteed for 25 years. Resolution: The recommendation was agreed and the Clerk will arrange the purchase the Pandora metal multi play unit as soon as possible. | 20.02.2023
22/1404 | To agree the wording of the proposed agreement between the Council and Great Waltham Horticultural Society in relation to the hut at the Brook Mead allotment garden (see document circulated prior to the meeting). Resolution: The wording of the agreement was approved. | 20.02.2023
22/1405 | To discuss and agree actions by the Council in relation to any restoration of the war memorial at Banbury Square. - Cllr. Gilbert. The meeting noted that three letters have been received raising concerns over the condition of the memorial; in particular, that some names of the fallen have become indecipherable. The Clerk provided an update on the ongoing correspondence between the Council and the War Memorial Trust (WMT). The WMT has indicated that: • Counterintuitively, regular cleaning of the stone is not advised. • Because of the transference of moisture, laying wreathes directly on the stonework on a permanent basis is not advised. • There may be opportunities to enamel the lettering on the memorial, subject to careful consideration of the type of stone, paint to be used etc. The meeting noted that the potential option to enamel the lettering was not one offered during previous discussions on maintaining the structure in good repair. Resolution: Clerk to write to the correspondents to confirm the above and that the WMT is working with us to provide a solution. Resolution A proposed strategy to renew or repair the oak posts at Banbury Square to be drafted for consideration. Resolution: Clerk to discuss enamel paint options with the WMT and the conservation officer | 20.02.2023
22/1432 | Update on the Great Waltham recreation ground storage solution and accept the Recreation Committee’s proposals. a. The committee recommends the council applies for full planning permission as recommended by the City Council planning department. Resolution: Spend up to £500 on the full planning permission application. b. The committee recommends the storage container is placed at the children’s play area side of the pavilion. Resolution: The proposal was agreed. c. The committee recommends the 8ft x 8ft storage container as the best option. Resolution: The proposal was agreed. | 20.03.2023
22/1433 | Discuss and agree to the Recreation Committee’s proposal to purchase 2 x 600l bags of topsoil to repair the goal areas at Ford End and Great Waltham recreation grounds. Resolution: The proposal was agreed. | 20.03.2023
22/1436 | To agree that the Council continues to nominate a Representative Member for Great Waltham Village Hall’s Committee of Management. Members requested clarification of the voting rights of representative members under the Village Hall’s constitution. It noted that Cllr. Gilbert will look to attend the Village Hall’s AGM as an observer (and not as Chair of the Parish Council) to ensure the Council’s future discussions are fully informed. Resolution: The Council deferred this motion and agreed to consider whether to nominate a Representative Member to the Village Hall’s Committee at its (the Council’s) AGM on 20th May 2023. | 20.03.2023
23/1454 | Proposal for funding of 2 trail cameras for Brookmead allotments. Due to 3 recent break ins. At Brook Mead allotments a padlock was cut off. Other locks have been removed. Small items have been removed such as secateurs. Proposed to install the trail cameras and gather data .Cost of approximately £100. It was noted that we will need CCTV notices and a CCTV Policy. Resolution In principle spend up to £100 on two cameras subject to establishing the legal position and requirements, | 24.04.2023
23/1455 | Discuss the grant request from Ford End Village Hall to support a community event to mark the Kings Coronation at Ford End recreation ground. Ford End Village Hall is putting on a free for all event with attendees asked to bring their own food. The Parish Council has £2,000 in the budget for grants. It is not known who will bring their own gazebo. Resolution: Cllr Palmer to contact Great Waltham School to borrow two gazebos. Resolution: In principle the Parish Council will purchase two gazebos if required. Resolution: The Parish Council will grant an amount of up to £500. Resolution: Clerk to contact JCM for an additional grass cut for Ford End recreation ground. | 24.04.2023
23/1460 | Update on the Ford End Recreation Ground CIF grant towards a perimeter path and if necessary, agree the next steps. The meeting agreed to continue with the plan. The path will be ninety-eight meters from the car park to the picnic benches. The full perimeter is 298 meters. Three quotes have been obtained but the specification created a large difference in price ranging from £42,000 (Caloo), £7,500 (JCM) to £6,000 . The work will require four inches excavated from the surface and the installation of side bars and a type 1 base, covered by compacted fine gravel. This will be suitable for ground maintenance and wheelchair access. The footpath can potentially be removed if circumstances change with the plans for the recreation area. Resolution The Parish Council resolves to spend up to £5000 (exclude Vat) of CIF grant subject to agreement from EALC to make a slightly shorter path than originally proposed for the grant. Resolution: Suspend financial regulations to accept the quotation from CAW Building Services as it has been difficult to get quotes and the funding is time limited. | 24.04.2023
23/1461 | To agree whether the Council prints an annual report to summarise its activities during 2022/23. The report would be printed as part of the Parish News rather than a separate insert. The report then will be delivered and received by every member of the Parish. Resolution: The Council agreed on the need for a printed annual report. Resolution: The Council agrees to spend up to £300 for inclusion of the report in Parish News. | 24.04.2023
23/1462 | To agree the Council’s presentation format at the Annual Assembly. Plan for a presentation of around 5 minutes to open the meeting. The Annual Assembly is at Ford End Village Hall. Resolution: A short presentation by the Chair. The presentation will be a precis of the reports from the committees’ chairs. | 24.04.2023
23/1466 | To agree the Highways & Transport Committee's recommendation to purchase and install replacement permitted parking signs at the Blossom Way car park. Potential material in Correx or a harder wearing material. Resolution: Budget of up to £50 for a new sign(s). | 24.04.2023
23/1467 | To agree the Highways & Transport Committee's recommendation that the Council lobbies the relevant authorities/agencies to change the A120 back-up diversionary route from the B1008 to the B1256. Build a report for Highways England to lobby for the change. The B1256 is the old A120 that runs parallel to the current A120. An approach to the Department for Transport was unsuccessful. Resolution: Agreed. Lobby Highways England. | 24.04.2023
23/1468 | To agree the Highways & Transport Committee's recommendation that the Council lobbies for measures to ensure the B1008 is not used as a preferred route once the NE by-pass is completed. What will be planned into the Northeast (NE) bypass design for the use of the new bypass? What will be done as part of the NE Bypass to encourage usage? Lobby the Essex County Council Cabinet Member and Cllr Steel. Work to influence the design rather than react after its been built. Resolution: Agreed. Lobby the Cabinet Member for Highways and Cllr. Steel at Essex County Council. | 24.04.2023
23/1469 | To agree the Highways & Transport Committee's recommendation that the Council lobbies for the reinstatement of signage at Sheepcotes roundabout which directs traffic to the A131/A120. Three of the six roundabout signs between Sheepcoates and the A131 are already marked for the M11. The signage policy is unclear. Signage of the NE Bypass at the Great Dunmow end (prioritizing use of the new route to the A12 at Springfield) is an important consideration. Resolution: Agreed. Cllr Steel to confirm management/control of the NE Bypass signage design policy, with a view then to lobbying the ECC Cabinet Member for Highways. | 24.04.2023
23/1470 | Agree the purchase of a magnetic whiteboard for the Pavilion. 1800mm whiteboard that can be used for writing on and used by the projector. This will replace the tripod Flipboard chart and separate projector screen. Resolution: Spend up to £200 on a new board. | 24.04.2023
5 | To agree the procurement of an external ground maintenance resource for an immediate one-off exercise of cutting back all ‘communal areas’ vegetation at the Brook Mead and Bury Lane allotment sites. There are several areas of long grass and cow parsley at both plots. There have been a variety of factors that have culminated in this issue arising. Both allotment sites are overgrown. There are more vacant plots than we have had in several years. Any areas of the allotments not hired out needs to be maintained by the Parish Council in addition to the communal areas. A discussion was held on delaying any works until August to allow the wildlife time to mature. A two-part cut could be undertaken to allow the wildlife to migrate. Consideration was given to hiring a petrol brush cutter with a metal blade for £61 a week and for the handyman to complete the work. However, it was felt that time would be against the handyman due to his other tasks. Two formal quotes have been received. A potential first cut could be undertaken week commencing 5th June and Brook Mead with Bury Lane the following week subject to a quote being received. Resolution: As the state of the allotment sites is very poor and overgrown suspend financial regulations and accept two quotes for review and decision. Resolution: Proceed with the lower quoted price. Subject to evidence of public liability insurance. Resolution: All available covering fabric to be shared with the contractor. Resolution: Clerk to contact contractor for copy of public liability insurance and action the quote for Brook Mead at £120. Resolution: Additional quote required for Bury Lane allotment plot. Resolution: Chair authorised to spend up to a value of £500. | 1st June 2023
6 | To consider and agree the long-term strategy for the routine maintenance of those areas of the Brook Mead and Bury Lane allotment sites which are the Council’s responsibility. Move the 2 hours a month allotment maintenance out of the handyman role. Appoint an outside contractor to maintain the allotments as a separate resource that can be called upon to maintain the standard required. Suggested the role is for a total of 24 hours annually (principally during the growing season). Trial for 6 months . Resolution: The strategy was accepted. Resolution: Clerk to discuss with the handyman. Resolution: Chair authorised to sign a contract. Resolution: Suspend financial regulations to accept a single quote due to the short horizon timing. Resolution: Clerk and Allotment Inspector to contact all plot holders via e-mail and WhatsApp/Facebook to confirm the decision of the Council. | 1st June 2023
23/1520 | To agree actions and activities in relation to co-option of councillors for the new council. (Cllr. Gilbert) Resolution: Start the process to identify and select new councillors as laid out in the Councillor Co-option Policy document. | 22 05 2023
23/1521 | Review new information in relation to the previous resolution to purchase a whiteboard for the pavilion. The meeting noted the cost (£376) for a projector friendly whiteboard. The advantages for this solution would be its potentially attractiveness for hirers and for use by the Council at its meetings. This item went to a vote to purchase the projector friendly version. The votes cast being equal, the Chair’s deciding vote carried the motion. Resolution: The improved whiteboard to be purchased. | 22 05 2023
23/1522 | To agree allocation of due policy document reviews (see review schedule circulated with the agenda of the meeting. A number of policies due for review were considered and agreed earlier in the meeting. A number of documents relating to the use of the Pavilion remained to be allocated. Resolution Pavilion documentation review allocated to Cllr Gilbert and Cllr Martin. | 22 05 2023
23/1523 | To agree that the Council seeks to secure a loan to fund one-half of the costs to install an average speed camera system on the B1008 through Ford End village (see briefing note circulates with the agenda of the meeting). • Cllr Steel declared an interest as ECC and LHP member and withdrew from the vote. • The meeting noted the information in the briefing note (see Parish Council Agendas section on parish website). • Members noted it likely that the cost of raising the loan would ultimately fall to all parishioners as part of the precept request, during a time of increased economic pressure. • The possibility of the scheme has been mooted for a number of years and the Council has continued to maintain an earmarked reserve (of £10,000) for this purpose. • Currently Essex Highways will not consider other traffic calming solutions for Ford End village. • Option 2 in the briefing note provides details of the basis of the motion. That is, GWPC agrees to seek the loan required for it to request that LHP match funds and authorises the scheme. The loan would be for either £50,460 (that is, 50% of current costs less the £10,000 in its budget) or for 50% of the revalidated scheme costs (subject to an upper limit which if reached would require further GWPC approval). • A named vote on the motion was requested and agreed. • The motion was: To agree that the Council seeks to secure a loan to fund one-half of the costs to install an average speed camera system on the B1008 through Ford End village. Cllr Martin – proposed. Cllr Gilbert – seconded. Cllr Steel withdrew from the vote. Cllr Jenkins – Abstain Cllr Palmer – Abstain Cllr Bradley – Abstain Cllr McDevitt – No Cllr Jackson – No Cllr Gilbert – Yes Cllr Martin – Yes The vote was tied at 2 for and 2 against. Cllr Gilbert exercised the Chair’s vote for the motion. Resolution: The motion was carried. | 22 05 2023

## Recreation
Date Of meeting | Minute Reference | Agenda Item | Detail of resolution | Action By | Last Updated | Current position
2022 11 07 | 8 | Update on discussions regarding the Horticultural Society Hut at Brook Mead and any implications identified for GWPC. The Chairman of the Great Waltham Horticultural Society (GWHS) has confirmed that they hold insurance and own the building. The provision of tool storage space for allotment users was discussed and agreed that it was not within the Council’s remit to offer space in the hut. | Resolution Cllr Gilbert to review the allotment hire conditions. | Clerk | 2023-05-01 | Clerk to confirm letter has been sent. Face two face meeting to be arranged. Version 2 send after the Face 2 Face meeting.
2022 11 07 | 9 | Update on the status of the overgrown trees at Brook Mead allotments. It is noted that the trees are under tree protection orders (TPO). The landowner is waiting on Chelmsford City Council tree officer to visit the site. The Parish Council is concerned that the tree is causing problems for the allotments. There is a concern that the trees may cause damage to the allotments and GWHS building if any branches fall. | Resolution: Allotment Inspector to continue to monitor the situation. | Cllr Palmer | 2023-05-01 | Barrack Lane tree has been trimmed (TPO) around the CHP . Cllr Palmer to make enquires of the Tree Officer. Plans have been submitted.
2022 11 07 | 14 | Discuss recent vandalism to the perimeter fence at Ford End recreation ground and consider the quote to add further security fencing. A quote to replace 10m of security fence to close this gap £1870 (+vat) had been obtained. There was a discussion about the ongoing trespass through to the fields and the need to keep the Recreation Ground play area secure. | Resolution The committee to recommend to the Parish Council to plan to repair the fence at Ford End recreation ground. | All | 2023-05-01 | Potential task to be done depending on the rest of the project
2022 11 07 | 16 | Review responses to the consultation invitation to identify a suitable Multi-play replacement for the Howe Street recreation ground and agree next steps. It has previously been agreed that the wooden play equipment needs replacement as it has aged. The consultation was contained within the September edition of the Parish News, however there were no responses. The Local Parish Councilor proposes to replace the existing unit with a similar multi play for 3–12-year-olds. The budget is in the region of £15,000. | Resolution: Cllr Jackson, Cllr Palmer, Cllr Huggins and Cllr Martin to make a decision on the appropriate piece of equipment. The information should be shared with residents in an article for Parish News , post through letter boxes , the school’s newsletter and social media. | Cllrs Jackson , Palmer , Huggins and Martin | 2023-05-01 | On the agenda Due to install June 3/4
2022 11 07 | 18 | Pavilion update including bookings and feedback and outstanding work to include storage container options update. Door blinds and obscuration film had been considered but it was suggested that a removable fire proof curtain is a better option for the door and side panels at night to give some hirers some privacy. In the last few weeks the exterior of the building has been re pointed by Cllrs Martin and Huggins. A second quote on the shutters has been sought and found to be more competitive. It is anticipated that there will be a 3-week manufacturing time for the units after the order has been placed. It was also discussed that there is an option to pull forward the purchase and installation of the storage container into this financial year as some unexpected CIL income has be remitted to the Parish Council. An 8 foot ex shipping container would be within budget. | Resolution The committee recommends the purchase of a single use shipping container for placement beside the pavilion. | All | 2023-05-01 | Pre Application advice has be sought. Application has been made. Update June 13.
|  | Junior Goals - to be rfurbished | We have paint , got the sockets
|  | Fe Goals to be filled | Sil is at ford end.

## F&GP
Minute Reference | Date Of meeting | Agenda Item | Detail of resolution | Action By | Last Updated | Current position
10 | 25.08.2022 | To consider and agree enhancements in financial reporting, including identifying additional accounting tools (such as software packages) to streamline processes and improving access to management information. | Consider potential options to reduce the resource investment by the RFO and consider potential savings by moving to a software package. The RFO to investigate potential options and feedback tp the committee. |  |  | 9. Review of software packages and recommendation to this committee. The Clerk provided an overview of both commercially available and specific parish council software. The Committee requested clarification on several areas of the recommended (AdvantEdge) software: • If possible, testimonials from local users of the software. • How many councils overall use the software? • What happens to the playground inspection sheets if the software company ceases to trade? • When can a new system be implemented? E.g. is a mid-financial year implementation possible? The Committee also requested a cost benefit analysis which can be used to support what is currently an unbudgeted expenditure. Resolution The Clerk to gather the data requested for the Committee.
11 | 23.01.23 | Review the budget for the Howe St Multi Play replacement and consider recommending an increase. | There are sufficient funds within the capital works budget to accommodate the increased costs if the HAGS unit is approved. It was noted that some other planned items may be deferred. To recommend that in the consultation document to Howe Street residents the HAGS unit is cited as the preferred option, subject to its costs being approved by the Council. |  |  | Advert placed in the Feb 2023 parish News.

## Transport and Highways
HIGHWAYS AND TRANSPORT
Reference | Open/Closed | Capital / Maintenance / Future items | Detail of resolution | Date Originated | Action By | Last Updated | Current position
1 | Open |  | Ford End Average Speed Cameras |  | All | 2023-04-09 | DfT: It was also suggested that DfT be contacted in relation to the B1008 through Ford End and its status as a back-up for the A130. I have spoken to the Transportation Planning & Infrastructure Manager at ECC Highways whose initial reaction was that DfT would not contribute any funds to a speed camera. I followed up on the verbal conversation with a request to ask DfT to downgrade the road so it was no longer a back-up route. This is the response I have received. “As you are aware he issue with the B1008 has been around now ever since the reclassification on the section of A130 from the A131 to Great Dunmow was undertaken. When DfT approved the reclassification they did heavily caveat that the section from the A131 to Great Dunmow was required to remain available for all traffic as it was the route that traffic would expect to use if there was any event on the A120 or A131, that meant that no physical traffic calming, or weight limits could be applied. The situation to be reviewed when the Chelmsford Northeast bypass was completed. We have previously investigated speed cameras and there is not a speeding issue or a collision problem therefore no justification. Traffic calming will create more issues than it solves, may increase emissions and noise as well as possible ground borne vibration. I appreciate this is not new as such to you but reflects where we are at present.” . Recommendation for the Parish Council to re iterate its support for this cameras. Cllr Lee Scott is to confirm funding is available for 50% of the Unit. Cllr. Scott confirmed (3/4/2023): 'In terms of any LHP Match Funding I believe it was always the case that the Panel were waiting on GWPC to arrange their part of the funding. The Panel has to date not been informed that GWPC has their Match Funding contribution available'.
21/705 (Apr 2021) | Open |  | To address the reduction of pavement widths in the parish due to encroachment of the verges and determine what action can be taken to recover them. Several Pavement footpaths are becoming overgrown in Ford End, Main road, Great Dunmow end of Ford End , Sandon Hill, main Road Ford End , Main road Chelmsford. Also footpath between Ford End and North End, and footpath rom Langley’s South lodge to Ash Keys. Resolution Ford End highway pavements to be raised with Highways Rangers. Resolution Other areas identified to be added to the action tracker for future referral to Highway rangers | 2021-04-26 | Clerk | 2023-04-09 | Highways Rangers wont work on the footpath from Kings farm down in to the Village as it has no backing. Highways Rangers recommend a LHP approach. Reported to Essex Highways 2726389 LHP scheme in use LHP have now archieved the item. 09/04/2023 Essex Highways website: Enquiry Reference: 2726389 Issue: footway defects - The Street: Main Road, Chelmsford Last updated: 16/10/21 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues.
2755500 (Essex Highways) | Open |  | Hoe Lane . Blocked Drain. Reported Essex Highways. 31.12.2021 | 31.12.21 | Clerk | 2023-04-09 | Blocked Culvert recorded. Repairs to be scheduled. 09/04/2023 Essex Highways website: Enquiry Reference: 2755500 Issue: highway drainage problems Street: Hoe Lane, Chelmsford Last updated: 09/02/22 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues.
2758382 (Essex Highways) | Open |  | Cherry Garden Road near number 62. Drain cover appears to be blocked. | 19.01.2022 | Clerk | 2023-04-09 | 09/04/2023 Essex Highways website: Blocked drain. To be considered for repairs. Issue: highway drainage problems Street: Cherry Garden Road, Chelmsford Last updated: 02/02/22 Status: A defect has been identified, the issue will be programmed for repair according to how we prioritise highway issues.
2771004 (Essex Highways) | Open |  | Dead Ash Tree at corner of Lucks Lane , main road , Howe Street . Potential to close thr road. Dead Ash tree. | 29.03.2022 | Clerk | 2023-04-09 | 09/04/2023 Essex Highways website: Enquiry Reference: 2771004 Issue: vegetation problems Street: Lucks Lane, Chelmsford Last updated: 23/03/23 Status: The issue was reported on a road that has been inspected and identified issues are recorded and actioned in line with our maintenance strategy.
22/1177 (Jun 2022) | closed |  | Discuss a request for double yellow lines at the junction of Duffries Close and South Street – both ends. Resolution Move to the action tracker. Resolution Clerk to write to write to resident and confirm that we will continue to monitor | 13.06.222 | All | 08.09.2022 | The Parish Council will monitor the situation Continue to monitor
2788600 (Essex Highways) | Closed |  | Church Lane. Ford End. Overgrown trees and hedges | 31.07.2022 | Clerk | 2023-04-09 | Potential to be done this week 09/04/2023 Essex Highways website: Enquiry Reference: 2788600 Issue: vegetation problems Street: Church Lane, Chelmsford Last updated: 23/03/23 Status: The issue was reported on a road that has been inspected and identified issues are recorded and actioned in line with our maintenance strategy.
22/1204 (Jul 2022) | closed |  | To consider the merit of requesting roadside parking restrictions adjacent to the Hatchfields entrance gate to Great Waltham Recreation Ground. The meeting noted the poor condition of some parts of the wooden entrance gate. The case for applying for parking restrictions was discussed. The relatively low volume of traffic and the need for residents’ parking spaces were mentioned. Resolution: Clerk to get a quote to replace the wooden entrance structure with the same style of structure. Resolution: Clerk to add advisory signs to the new structure reminding people exiting the park about the dangers of the road (inside) and asking drivers not to park directly adjacent to the gate (outside). Resolution: Any traffic restrictions to be delayed and the situation monitored. | 18.07.2022 | Clerk | 08.9.2022 | New fence being quoted on. Once the fence is added a notice to be attached. Continue to monitor. Is ther any playground sign at theis point
22/1133 (May 2022) | Open |  | To discuss actions to be taken at Ringtail Green following the extraordinary meeting at Ford End. A report was circulated with 4 proposals: 1. Install Ringtail Green Name plates with a drive slowly message. 2. Pursue Quiet Lane status for the lane – approximate cost £2,000. 3. Paint Slow road markings at either side of the bend. 4. Advisory road signs at either side of the bend e.g., maximum speed and chevrons. Resolution Item 1 – Clerk to contact the street naming team at Chelmsford City Council Resolution Clerk to raise LHP requests via Cllr Steel for items 3 and 4. | 23.05.2022 | Clerk & Highways Committee | 18.07.2022 | Item 1 - Has been sent in to the LHP - this has been validated and will now go into the queue for funding. Item 2 - Is already in the LHP queue. - this will not proceed as this did not get the support of the other members of the LHP.“Awaiting Funding” list – LCHE212014 Item 3 - LHP request to be raised by the Clerk - On item 3 – Painted ‘Slow’ road markings at either side of the bend I discussed this with the LHP Manager. He believes that to have SLOW written on the road, you also have to have a triangular warning sign as well. This would be determined as part of the design process. However, it would need to get through the LHP validation process first to go to the design stage, which is unlikely to happen given that the recorded speeds were an average 22mph, 85th percentile 27mph and there are no reports of accidents in that area . These measurements were made on the straight patch as specified by GWPC. However, if GWPC wish to fund this option, the LHP Manager estimated a cost between £5K and £10K. To refine the cost estimate would need the design work to be undertaken, which is usually about a third of the cost Item 4 - LHP request to be raised by the Clerk - Advisory road signs at either side of the bend, e.g. advisory max speed or right/left hand bend signs Advisory speed limits would have the same issues as Item 3 above – maybe more onerous scrutiny. The Price guide suggests that “Change of single speed limit which is uncontentious and where minimal infrastructure is required. £15,000” As this is not actually a change, it may not be as high as that. Again, to refine the estimate would need a funded design
22/1212 (Aug 2022) | Open |  | 20’s Plenty campaign. The scope of the campaign locally is likely to be predicated by an outstanding update by Safer Essex Roads Partnership to its Functional Route Hierarchy Review, to be followed then by a revision of the Essex Speed Management Strategy. There is no published date for completion of these reviews. Resolution: The Clerk to write to Safer Essex Roads Partnership for an update on the timetable for completion. | 2022-08-15 | Clerk | 2023-04-09 | Clerk to update next meeting.
22/1233 (Aug 2022) | closed |  | To report back to the Parish Council on the online seminar hosted by Essex association of Local Councils on - 20’s Plenty - attended by Cllrs Palmer and Martin. Resolution Fact finding from other councils and consideration of further engagement and action deferred to the Highway and Transport Committee. | 2022-08-15 | Cllrs. Palmer & Martin | 2023-04-09 | Cllrs. Palmer & Martin to update next meeting.
H&TC_9/22 7 | closed |  | Clerk to investigate if the Public Transport forum of Essex County Council plans to hold meetings where the Committee can be represented. | 2022-09-01 | Clerk | 2023-04-09 | Transport Meetings March 2023. Meeting agenda was passed to the parish transport representative 2nd Feb. Clerk to update next meeting.
H&TC_9/22 7 | Open |  | Cllr Palmer to prepare a draft of the role of the Parish Council Public Transport Representative. | 2022-09-01 | Cllr. Palmer | 2023-04-09 | Outstanding.
H&TC_9/22 7 | Closed |  | Cllr Gilbert to be the point of contact for all transport related matters. | 2022-09-01 | N/a | 2023-04-09 | N/a
H&TC_9/22 8 | Closed |  | Add a column to the tracker to indicate if items are capital items, maintenance, or ongoing issues. | 2022-09-01 | Clerk | 2023-04-09 | Completed.
H&TC_9/22 8 | Closed |  | Recommendation to the Parish Council to confirm its commitment to installing average speed cameras through Ford End. | 2022-09-01 | Cllr. Gilbert | 2023-04-09 | Completed. Agenda item and resolution at September monthly meeting: 22/1269 To consider and agree the Highways & Transport Committee's recommendation that the Council remains committed to the installation of average speed cameras through Ford End. Resolution The £10,000 earmarked reserve for the speed camera to be retained for another 12 months.
H&TC_9/22 8 | Closed |  | Recommend to the Parish Council that the Committee writes to Cllr Scott (ECC Highways Maintenance and Sustainable Transport cabinet member) and explain its initiation and to request a meeting to discuss how strategic projects will influence the situation in Ford End in particular, and the parish in general. | 2022-09-01 | Cllr. Gilbert | 2023-04-09 | Completed. Agenda item and resolution at September monthly meeting: To consider and agree the Highways & Transport Committee's recommendation that it contacts ECC's Highways, Maintenance and Sustainable Transport cabinet member to arrange a meeting to discuss how strategic ECC projects will influence road usage in the parish. Resolution This recommendation was agreed. The meeting took place in December 2022.
H&TC_9/22 8 | Closed |  | Discuss [Quiet Lane – Ringtail Green] with Cllr Scott at the proposed meeting. | 2022-09-01 | Cllr. Gilbert | 2023-04-09 | Completed. Discussed at meeting in December 2022.
H&TC_9/22 8 | closed |  | Consider adding [scheme to address reduction of pavement width in Ford End] to a list of potential LHP projects | 2022-09-01 | Clerk | 2023-04-09 | Clerk to update next meeting.
H&TC_9/22 8 | Closed |  | Perceived speeding in Howe Street. Close this item. | 2022-09-01 | N/a | 2023-04-09 | N/a
H&TC_9/22 8 | Closed |  | Cllr Martin to invite Ford End speed watch to the next meeting to raise the profile and discuss how the Committee can support speed watch initiatives. | 2022-09-01 | Cllr. Martin | 2023-04-09 | Completed. Update at February 2023 meeting.
H&TC_9/22 8 | Closed |  | South Street double yellow lines. Close this item. | 2022-09-01 | N/a | 2023-04-09 | N/a
H&TC_9/22 8 | Closed |  | Variety of Highways references for reported defects. Clerk to review the references and update with latest information from Essex Highways website. | 2022-09-01 | Clerk | 2023-04-09 | Completed.
H&TC_9/22 8 | Closed |  | The Committee has no objection and supports the introduction of the northern 40MPH buffer . Were there any technical reasons why the 40MPH zone does not begin earlier? | 2022-09-01 | N/a | 2023-04-09 | N/a. Scheme has been completed.
H&TC_9/22 8 | closed |  | Clerk to write to the LHP and share the resolution of the committee [that the Committee has no objection and supports the introduction of the northern 40MPH buffer]. | 2022-09-01 | Clerk | 2023-04-09 | Completed. Scheme has now been completed.
H&TC_9/22 8 | Closed |  | Update the action tracker so that the Highways tab includes items on the current LHP project list. | 2022-09-01 | Clerk | 2023-04-09 | Completed.
H&TC_2/23 7 | Closed |  | Recommend that the Parish Council Supports the 20’s Plenty for Essex campaign and drafts a letter for Essex County Council to confirm its stance. | 2023-02-01 | Cllr. Gilbert | 2023-04-09 | Completed. At February 2023 monthly meeting: 22/1407 To agree the Highways and Transport Committee's recommendation that the Council supports the 20's Plenty in Essex campaign, and if agreed, for the Council to write to Essex County Council asking it to note the decision. Resolution: The recommendation was approved.
H&TC_2/23 10 | Closed |  | Continue to use the SID in the current format. | 2023-02-01 | N/a | 2023-04-09 | N/a
H&TC_2/23 10 | Open |  | Standing invitation to Committee meetings for the parish’s Speed Watch co-ordinators. | 2023-02-01 | Clerk | 2023-04-09 | Clerk to update next meeting. ADD AS SA STANDING ITEM
H&TC_2/23 15 | Closed |  | To consider future requests to the Local Highways Panel. Resolution: Items should be passed to the Clerk for discussion at a subsequent meeting. | 2023-02-01 | All | 2023-04-09 | N/a
H&TC_2/23 15 | Open |  | To consider future requests to the Local Highways Panel. Resolution: List of potential schemes to be created for the next meeting. | 2023-02-01 | Clerk | 2023-04-09 | Clerk to update next meeting.
H&TC_2/23 16 | Open |  | Discuss the poor condition of the footway between Bennett’s Lane and Parsonage Lane on the B1008 on the North End side. Resolution: Add to the list of LHP requests for discussion. | 2023-02-01 | Clerk | 2023-04-09 | Clerk to update next meeting.
H&TC_2/23 17 | cLOSED |  | To consider the installation of deer signs around the village due to the increased levels of deer. Resolution: Add to the list of LHP requests for discussion should further information be forthcoming. | 2023-02-01 | Cllr. Lockwood | 2023-04-09 | Update required.
H&TC_2/23 18 | Closed |  | To agree whether to recommend that the council responds to the Chelmer Village Park and Ride expansion – Public online consultation survey. Resolution: The Committee recommends no action on this consultation. | 2023-02-01 | N/a | 2023-04-09 | N/a
LHP Schemes
|  | Status | Scheme | Description | Scheme stage | Budget | Comments
LCHE182009 | Open | Funded | B1008 Ford End - Kerbing improvements | Height of kerbs through Village | Total scheme | 48000 | Raised kerbs at six bus stops through village as first stage
LCHE203002 | Open | Funded | Barrack Lane j/w Cherry Garden Road, Great Waltham - Footway Improvements | Footway improvements | Design | 6500 | Design team advised footway may need regrading and could need land acquisition. Due to change in scheme scope agreed at June 2022 panel to make this a Design Only as first stage
LCHE202036 | Open | Funded | Littley Park Cottages, Littley Park Lane, Hartford End - Road markings | SLOW road markings for existing bend warning signs | Total scheme | 10800 | Signage improvements and vegetation clearance, possible SLOW road marking
LCHE182010 | Open | Awaiting Funding | B1008 Ford End - Footway improvements | Width of footway through Village | Validation | N/A | Highway Rangers to routinely side existing footways to fully open up available footway width
LCHE192028 | Open | Awaiting Funding | Ford End - Average speed cameras | Average speed cameras | Implementation | 60460 | Scheme was design only in 2020/21, new revised costing £120,920. Suggestion previously was Match Funding from Parish Council and LHP, which would now require £60,460 from each source
LCHE212013 | Open | Archived | Ringtail Green, Great Waltham - Traffic management improvements | Request for speed reduction 60mph to 40mph and Quiet Lane status | Validation | TBC | Validation - 30mph - Northeast bound 21.8mph & Southwest bound 22.1mph. Very good speed compliance. Parish would still like consideration of Quiet Lane status,
LCHE222014 | Open | Awaiting Funding | Ringtail Green, Great Waltham - Gateway signs | Signage to identify the hamlet | Validation | TBC | Awaiting highway boundary information
LCHE223011 | Open | Awaiting Funding | Great Waltham Primary School, South Street, Great Waltham - Signage improvements | Sign to show School not School Crossing Patrol | Total scheme | 6500 | Validation - Recommends changing Patrol sign to School, need to check sign/pole as could be sticker or may need new pole/sign

## Closed Items
Minute Refrence | Detail of resolution | Date Originated | Action By | Last Updated | Current position
19/176 | To address concerns about the untidy state of the front garden of 73 Cherry Garden Road Resolution: An initial request to clear the area be sent to the resident. | 19th August 2019 | Clerk | 2019-09-01 | Letter sent to the resident. No Response. Noted that some of the debris has been removed.
20/464 | 20/464 Discuss quote to remove Ash tree at the Brook Mead allotments that is suffering from Ash Die Back. Resolution The removal of the tree was approved. Resolution As only one quote has been received Cllr Palmer to seek additional quotes. The Clerk to award the work to the lowest cost for cutdown and removal from site. | 2020-08-17 | Cllr Palmer |  | 16.11.2020 - Three quotes received. 16.11.2020 - Tree has been cut down this week.
20/473 | 20/473 Safety concerns of footpaths in the vicinity of agricultural reservoirs and the possible effects of adverse weather conditions. Concern raised about clay lined agricultural reservoirs drying out in the hot weather and then a deluge of water may cause cracking. ECC confirmed that the reservoir maintenance is the Landowners responsibility. Any issue with the footpath will be discussed by the Public Rights of Way officers with the Landowner. The 1975 Reservoirs Acts places an inspection regime in place depending on the volume of water above water level. Resolution The Clerk to write to the environment agency to verify if the inspections are taking place in Great Waltham Parish. | 2020-08-17 | Clerk | 01.10.20 | Information sent out to the Council on Reservoirs.
20/571 | 20/571 Consider results of traffic survey through Broads Green Review of the data supplied by Highways did not show a speed problem but did determine that the HGV volumes were around 1% and the LGV/MGV around 11%The survey is not able to determine whether this is traffic traversing the hamlet, or accessing it. On the basis of these volumes, it is highly unlikely that a weight restriction will be granted but we may be able to get “unsuitable for large Vehicles” signs Resolution Clerk to explore the possibility of requesting the Local Highways Panel to install an “Unsuitable for Large Vehicles/HGV” sign at either end of the Broads Green. | 16.11.2020 | Clerk | 14.12.2020 | LHP Bid submitted . Chased again 14.12.2020 LHP will not take this item forward.
20/432 20/470 20/568 | Proposal to discuss with the village hall increasing the trade bin in size to accommodate rubbish generated by the Parish for which the Parish is responsible for. Discussion on the types of waste generated in the Parish by the public. General waste and the dry mixed recycling. Resolution Agree with proposal to increase the general waste bin at the Village Hall to a suggested 660L unit and to add a new DMR unit of 660L.Costs to be split 50/50. Resolution Purchase recycling bins with Lids for the recreation areas in the Parish. Bins to have clear plastic bags. 20/470 Discuss proposal from the Village Hall on joint waste collection and Dry Mixed Recycling. The VH committee have made a proposal to jointly fund a larger fortnightly collection of general waste and a weekly collection of Dry Mixed Recycling. Costs of £57 pcm to be split equally between the Village Hall and the Parish Council. Resolution The proposal was accepted Resolution Cllr Huggins to prepare Work instructions / process for the teams. 20/568 Proposal to share cost of waste and recycling with GW Village Hall Cost of approximately £31 per month. Village Hall have agreed to an initial estimate of dry mixed recycling and general waste. One collection receptacle for Dry Mixed Recycling and one collection receptacle for general waste will be installed. Resolution Cllr Huggins approved to contract with the Village Hall with a delegated authority to agree any potential increase up to 10%. | 20/07/2020 17/08/2020 | 1. VH Committee 2. Cllr Huggins 3 Clerk | 2020-11-16 | Waiting on the Village Hall Committee. Reset due to chnages at VH. 16/11 - Cllr Huggins discussing with the VH as per minutes of the 16/11/2020 Agred with VH to 50/50 on costs - item closed
20/512 | To consider making an induction file for new councillors Cllr Gilbert offered his assistance to pull together with Cllr Palmer and the Clerk. This is not to replace the EALC training but is aimed at co-opted Councillors. Resolution Induction file to be created. | 2020-09-22 | Clerk & Cllr Palmer | 08.02.2020 | Cllr Gilbert has created a file with a lot of details. Additrional review required.
Recreation June 2020 | GW changing room • Quotes for Phase 2 – Doors, Windows and shutters Resolution The Current front doors to be retained Resolution New windows to be installed Resolution New wooden Shutters to be built by Cllr Huggins | 2020-06-22 | Sub Committee | 2020-09-01 | Update at the monthly Meeting
20/537 | Sheepcotes Roundabout – Removal Of M11 Direction Signs Signposts that point motorists to M11/Stansted from Sheepcote roundabout via the A130 were put in by the LHP some years ago. The recent upgrade of Sheepcote roundabout had removed these. Resolution: Clerk to write to Cllr Bentley to reinstate the original signs to point the M11 access via Great Leighs. Cllr Martin to support with the letter. | 01.11.2020 | Clerk & Cllr Martin | 15.02.2021 | Letter sent and received from Cllr Bentley Cllr Steel . Martin & Aldridge to have a meeting with Cllr Bentley to discuss - 2021 Meeting Held. Problem with consequential roundabouts and signage for M11
Recreation September 2020. Item 8 | 8. Discuss installing a drop down post at Broads Green so that the contractors Tractor can enter the green to cut it. Resolution Clerk to investigate if wooden lockable bollards are possible. | 2020-09-07 | Clerk | 20.09.2020 | Woodscape Contacted for quote. Quotes availabe on a wood effect drop down post £500.
Recreation September 2020. Item 8 | 8. Discuss installing a drop down post at Broads Green so that the contractors Tractor can enter the green to cut it. Resolution Cllr Steel to inspect the bollards and the one at Duffries close |  | Cllr Steel
20/569 | 20/569 Agree to purchase and install new football goals at Great Waltham Recreation Ground. A set of New Junior goals to be installed at Great Waltham Recreation ground on the main pitch. Chelmsford City Council to be contacted to arrange the installation of sufficient sockets to enable the goal posts to be moved to avoid wear patterns. After reviewing the three quotes it was approved to place the order on Stadia Sports at a cost of £674.40 and likely cost of £400 per goal from Chelmsford City Council. Resolution Clerk to order units from Stadia Sports Resolution Clerk to arrange socket installation with Chelmsford City Council. Resolution Position the goals on the recreation ground to provide a football pitch suitable for under 9/10 junior football. Cllr Martin, Cllr Huggins and the Clerk to agree location. | 16.11.2020 | Clerk | 08.02.2021 | delay ordering the Goals as there is a requirement to Co ordinate - Chelmsford City Council , Goal Post Delivery and Recreation room works. Pause the ordering of the goals as there is currently no requirment for additional Junior goals.
20/592 | Proposal to install a seesaw at Howe Street, provided free by Broomfield Parish Council, for just the installation cost Resolution Agreed to proceed and use reserves. | 12.01.2021 | Cllr Steel | 18.01.2021 | Cllr Steel Has been in contact with Playquip to arrange installation. Cllrs Martin and Jackson to be notified of installation.
20/442 20/472 | Recommendations Following Recreation Ground RoSPA Reports Review of the workload split down by skill set for internal and external workload. Resolution Additional meeting required to review the high cost items. Resolution Cllr Martin to review the play equipment and make recommendations. 20/472 Update on the Playground equipment maintenance works. The report was reviewed and accepted. It was noted that no new wooden equipment had been installed since 2009-2010. Resolution Reporting and Maintenance communication to be improved Resolution Identify an appropriate company or competent person to carry out remedial work Resolution A revised list of defect work to be passed to the handyman Resolution A schedule of repairs and replacement of defective equipment to be developed and agreed | 20/07/2020 24/08/2020 | Cllr Martin | 03.03.2021 | Spreedsheet of defects and workload built and issued Issues from 2020 reviewed and status agreed on items closed. Working Party created 03.03.2021
20/570 | 20/570 Agree to progress the next stage of work at Great Waltham Recreation Ground Changing Rooms. The three quotes were carefully reviewed and the additional quote to consolidate phase 2 and 3 in to one phase was approved as this will reduce overall cost.(It was agreed that henceforth we would refer to the building as the “Pavilion”) Resolution Agree the layout as shown in the meeting of a single accessible toilet, a kitchen area and a large single open space. Resolution: The work to be awarded to Bg Premier Bathrooms & Plumbing. Resolution: Confirm whether a Change of Use, or Building Regulations application is required | 16.11.2020 | Clerk | 15.03.2021 | Building Control to be filled with CCC Additional Costs due to Insulation of approx £1000
19/175 | To propose further communication and initiate action on cobbled area at shop / beehive. Concerns had been passed to Councillors about the trip hazard at the cobbles area. Resolution : The Clerk to write to the landowner to highlight the concerns and request proposals to make changes | 19th August 2019 | Clerk | 2019-09-01 | Landowner agred that a proposal can be sent from the Parish Council to make chnages.
19/172 20/468 | 19/172 Discuss the complaint about parking at the Rose and Crown on the pavement during a recent event. Recent correspondence received by the Clerk had complained about car drivers parking on the pavement and not leaving space for Pedestrians. There is no restrictions on parking on the roads around the Rose & Crown. The Parish Council is pleased that the business is continuing to be a success and has already extended its own car park. Resolution: The Clerk to write to the Landlord to request patrons are advised to park on the road. 20/468 To consider complaints from the public in regard of Rose and Crown users cars parked along Chelmsford Road causing pavement to be blocked. Several complaints about the pavement being blocked to pushchairs and mobility scooters were received by Councillors. The item was discussed previously at the 19th August 2019 meeting. It is currently not illegal to park on the pavement outside of London, blocking the pavement may be. Even with cars part parked on the pavement, single file traffic still applies this would be the same if the cars were parked on the road. Resolution Cllrs Palmer / Bloomfield / Huggins to meet with landlord to discuss his plans | 19th August 2019 17th August 2020 | Clerk Cllrs Huggins / Palmer / Bloomfield | 01/09/2019 01/09/2020 | Letter Sent to the Landlord. Landlord put posters up on the surrounding area. LandLord of the pub is looking in to flyers for windscreens , In discussion for additional parking space for customers or staff, Looking to Council to cut back the grass that spread over the pavement and looking to add parking bays to the car park. Noted there is currently government consultation on parking on the pavement.
21/753 | Review of the Council’s policy for dealing with the press/media. • Great Waltham Parish Council media relations policy Resolution Cllr Steel to review | 2021-05-17 | Cllr Steel | 31.05.2021 | Added to Agenda on the 28th June 2021 Agenda as file
21/754 | Review of the Council’s employment policies and procedures. • Equal Opportunities Policy • Recruitment of Ex-Offenders Policy Resolution Cllr Gilbert to review | 2021-05-17 | Cllr Gilbert | 21.6.2021 | Added to the 28th June 2021 Agenda as files have been edited.
21/768 | To consider concerns raised by Howe Street residents on speed of vehicles and difficulty of entering road from lane to Mill Cottage. Two households in the lane raised concerns about turning right out of the lane. Potholes have been highlighted to Essex highways. The Hedges won’t be cut until the cutting season. Resolution Clerk to Contact the two households. | 01.07.2021 | Clerk |  | Contacted Both Households. Households feedback they are completing some temporary themselves.
21/778 | Discuss and agree a policy and threshold on petitions. Resolution The Policy was discussed and approved. | 01.07.2021 | Clerk |  | Complete
21/780 | Discuss and agree the update to the Media Policy – Cllr Steel Resolution Review and re-issue | 01.07.2021 | Clerk |  | Complete
21/773 | Discuss and agree proposed changes to Council’s Equal Opportunities Policy. Resolution Approved Resolution Clerk to upload to the website | 01.07.2021 | Clerk |  | Complete
21/752 | Review of the Council’s policies, procedures and practices in respect of Its obligations under freedom of information and data protection legislation • Data protection notice Resolution Clerk to review | 2021-05-17 | Clerk | 18.06.2021 | Reviewed. No chnages required.
Recreation September 2020. Item 8 | 8. Discuss installing a drop down post at Broads Green so that the contractors Tractor can enter the green to cut it. Resolution Clerk to discuss additional grass cutting costs with JCM |  | Clerk |  | No update Costs Increased
21/750 | Review of inventory of land and other assets including buildings and office equipment Resolution Clerk to create a Red / Amber / Green condition on the asset list. Resolution Conditions of asset list to be issued to Council for review | 2021-05-17 | Clerk Councillors | 15.05.2021 | Clerk issue Red / Amber / Green list - May 2021
21/770 | Ringtail Green - Ford End – Traffic Issues raised: It was noted that the turning to Ringtail Green now had a derestricted sign on entrance as a result of it being the reverse of the 40mph sign on exit – concern that this encouraged faster speeds. Resolution Apply to LHP via County Cllr to reduced speed from 60 MPH to 40MPH Resolution Apply to LHP via County Cllr for the lane to be changed to a Quiet Lane | 28.06.2021 | Clerk | 01.07.2021 | Both Schemes submitted to LHP.
21/774 | Dunmow Lane – Byway – What can be done to protect the surface? Concerns about vandalism and fly tipping on Dunmow Lane – might be reduced if motorized vehicles could be stopped from entering. Resolution The Parish Council wishes to have Dunmow lane changed to a restricted byway. Resolution Clerk to raise an LHP request | 28.06.2021 | Clerk | 01.07.2021 | LHP submitted and approved by County Councillor
21/796 | Discuss the Rowan tree offered to the Parish Council for planting on Broads Green. Members raised concerns that Rowan tree berries are poisonous and that suitable trees for that area are more likely to be a Walnut Tree. It was also noted that previous request to plant trees at Broad Green had been met with resistance. Resolution Clerk to contact the Parishioner and decline the offer as the tree is unsuitable. | 20.07.21 | Clerk | 21.07.21 | Contact Parishoner. They responded that CCC Plant Rowan Trees.
21/801 | To consider that both sides of Pendon Hill corner should be cut. Resolution Clerk to Contact Jcm to cut late July / August and again Christmas to allow seeding. | 20.07.21 | Clerk | 21.07.21 | JCM confirm the instruction received.
21/748 | Proposal to defer the Face-to-Face meeting in June Resolution Move the next meeting from the 14th June to the 28th June to be in step with government guidelines on the pandemic. Resolution Meeting will be face to face and start at 7.30pm | 17.05.2021 | Clerk |  | Ongoing
21/814 | To discuss the Chelmsford City Council Housing Strategy for Chelmsford for the period 2022-2027. Resolution Cllr Gilbert to review and share his conclusions | 20.07.2021 | Cllr Gilbert | 01.08.2021 | Draft submisson shared with Council. Submitted to the Council.
21/813 | Clerk to engage with EALC on spinal point as Sp17 is the top of the LC1 Substantive range. Resolution Clerk to Speak to EALC | 20.07.2021 | Clerk | 25.07.2021 | 25.07.2021 Clerk contacted EALC - Parish Support Concluded with the Staffing Committee
21/707 | Does the Parish Council wish to reinstate the Asset of Community Value listing (valid for 5 years) on the Walnut Tree Public House in Broads Green? Resolution: Clerk to work through the process to reinstate the asset of community Value. | 2021-04-26 | Clerk | 08.7.2021 | The Walnut tree is back on the list
21/798 | Report and possible actions on the trees at the perimeter of the Great Waltham recreation ground. The Trees are not within the Conservation area. Options explored to include reducing all the trees in height equally and removing the 10 Ash trees as they have Ash die back. It was agreed to seek a professional opinion on creating a tree maintenance strategy . Resolution The Clerk to contact City Council / Writtle Forest Tree request a quote for a Tree Survey – GW Rec Ground, Broads Green, Resolution The Clerk to get 2 more quotes for cutting back the Ash trees – One Quote received already. | 20.07.2021 | Clerk | 25.07.2021 | 25.07.2021 Clerk contacted - The Public Sector Enviromental Consultancy 25.07.2021 Clerk Contacted Writtle Forest Consultancy 25.07.2021 Clerk Contacted Tracey Clerke Consultancy Services On the Agenda 21.09.2021
21/802 | Discuss the creation of a working party to create compost bins at Brook mead. Resolution Approved for Cllr Palmer to proceed. | 20.07.2021 | Cllr Palmer |  | Working on the allotemnts on 09.10321
21/799 | Should the parish council consider distributing to every household a map showing all rights of way within the parish. Concerns raised about people not adhering to the PROWs and would a map of PROWs distributed to every household help. It was agreed that in the first instance that GWPC would point people to official PROWs but to consider the possibility of a PROW parish map. Resolution Clerk to Create a Parish News article pointing at PROWs websites and asking people to adhere to them. Resolution Clerk to put similar article on Facebook concerning PROWs Resolution Clerk to add the information on PROWs to the Parish Website Resolution Cllr Palmer to collate and Create a document of all the rights of way in the Parish. | 20.07.2021 | Clerk | 25.7.2021 | 25.07.2021 Article Reused from October 2020 for September edition 25.07.2021 Information added to Website 25.07.2021 Information Added to Facebook
21/859 | Should we continue to pay for a domain name at £25.07 per annum and E-mail support at £6.59 per month (£79.08 per annum). Total payment to fast host £104.15 per annum Resolution Clerk to investigate multiyear domain deal with Fast Host and make a recommendation to the Council. | 21.09.21 | Clerk |  | Item Closed
21/867 | Discuss the Ford End recreation ground tree aftercare' Session on 5th August. 18 volunteers attended (incl 3 Parish Councillors), large trees being watered every 3 weeks. City Council recommended that one metre er outside the fence be not mown and allowed to grow wildflower And they would be happy to seed this area. Resolution Cllr Dunn to take up the offer of wildflowers. | 21.09.21 | Cllr Dunn |  | Trees Plant. JCM informed.
21/892 | To consider request for help from Parish News to address shortfall in advertising income due to Covid.
| The Parish News supports the Parish Council as every household gets a printed copy delivered by the volunteers which contains a precis of the meeting minutes, PC notifications and the Annual Report. GWPC considers it a valuable resource |  |  |  | Grant paid.
Resolution Parish Council to support the Parish News with a grant of £1050 this financial year.
21/899 | Update on the Pavilion renovation at Great Waltham. The Kitchen units have been installed. Electric Heaters to be installed. Kitchen goods have been installed. Locality fund can now be claimed for the £1000 from ECC. Resolution Clerk to claim the £1000 Locality fund grant. |  |  |  | Locailty Fund Claimed.
21/894 | Discuss the quotes for renovating our wooden assets to prolong their service life Resolution Approved to proceed with all the jobs works quoted to Bus Shelters and Noticeboards. Resolution Clerk to contact GST Home Maintenance to proceed | 18.10.2021 | Clerk |  | Northend Complete. Butchers Arms Bus Shelter complete. Howe Street Shelter Complete. All areas complete.
20/641 and 21/703 | 20/641 To review whether the GW Noticeboard needs repairing or renewal, and its location | 15.02.21 | Clerk | 15.11.2021 | Handyman aware. Waiting on availability if Clerk to remove and store in Handyman shed for a week to dry out before repair. On List of tasks for better weather. Consider this job for george. Strip down the noticeboard and install in the Bus Shelter at Great Waltham.
Cllr Micklem declared an interest and took no part in the discussion
Resolution Take it down, Repair up to £100 and return To review and concerns and associated actions in relation to the need to stand on the cobbled area to read the Parish Council Annoucements on the GW noticeboard Resolution: When the noticeboard is refurbished it is to be placed on the Beehive side of the board and move the community board to the cobbled side to increase visibility of the Parish Council notices.
21/893 | The Movement of the Sid machine around the Parish. The SID is meant to cycle around the designated sites. It was also noted that previous meeting had agreed that readings would be taken on Breeds Road 40mph entry point, and then the SID would go to Howe street next. The issue was that the batteries were not holding charge. Resolution Buy 2 New Batteries Immediatley as the older batteries have become unreliable with short life. Resolution Issue the 7 Sid pole rotation plane | 18.10.2021 | Clerk | 01.11.2021 | 2 batteries have been purchased. 01.11.2021
20/598 | Does the Parish Council want to replace the bin at Great Waltham Bus stop at the war memorial? Resolution Agree in principle to replace the bin subject to requirements of Chelmsford City Council street clean team. Resolution Clerk to confirm any requirement for a license | 12.01.2021 | Clerk | 30.11.2021 | City Council to Confirm Bin size / type and cost. Confirmation of license requirement awaited - Move yellow bin from South Street to the Bus Shelter (once we have a license) Bin installed. Discuss with the School about a Recycling Bin. Recreation Working Group to Discuss. Chelmsford City Council to provide a Recysling bin - 2 setion Recylcing / general waste. GWPC to empty the Recycling and CCC the General waste.
20/682 | Great Waltham Bus Shelter Bin – should a new recycling facility be ordered? Move Yellow bin from Outside GW school to the GW Bus Shelter | 15.03.2021 | Clerk | 30.11.2021 | Move yellow bin from GW school once new bin in place at school Enquiry in with CCC on types of bin Bin chased up with Tim at CCC Bin installed
20/649 | Discuss the options of making a 2021 Community Initiative Fund Grant Application. Disscussion on Fored End Recreation ground path with estimates of between £8,000 and £12,000 Resolution A CIF aplication to be created for the Ford end path at 100% | 15.02.21 | Cllr Martin | 08.02.21 | Update at Recreation Meeting July 2021 The Grant bid has been entered has been submitted and a decision in November. Award is Imminent Award of £5000 accespted Jan 2022.
21/910 | Condition of Pump Green, in North End. Photographs were shared showing that although the green was well maintained – the field edge had grown up with weeds and brambles. Resolution Clerk to arrange with Highway’s rangers to cut back the vegetation. | 18.10.2021 | Clerk | 16.11.2021 | Cllr McDevitt confirmed that the Green is Common Land. Tnere is no connection to Highways so quote requested from JCM. Clearance of Pump green verge and ditch line. Bramble to be mulched to ground level Elder tree reduced to a coppice. All trees located on pump green to have crowns raised. Red Oak to be reduced heavily due to UKPN heavily disrupting crown to a poor standard pruning. All waste chipped and removed from site - £540 (Incl Vat) Agreed work to be carried out by JCM at meeting on 15.11.2021 work to take place 05.01.2022
19/342 21/842 | To highlight the concerns with vehicular parking on greens and unauthorised access over greens for parking in front of homes. A proposal to explore the options for alleviating congestion/ parking difficulties in Cherry Garden Road. To engage highways and CHP in management/ cooperation in finding solutions where possible. The area does not provide enough off-road parking for modern households and road parking is a problem. Cars and Vans are parking on the green areas, causing contention and damage. The green areas are owned by Chelmsford City Council. Requests for driveways across the greensward appear to be addressed inconsistently by the Chelmsford City Council Planning department. Associated drop kerbs and driveways need to paid for by individual houseowners. The Parish Council can appreciate that residents should have more of a say in their environment and it is important to understand their views. Resolution: The Parish Council to create a specific survey of Cherry Garden Road and discuss the results with CHP and CCC if appropriate. Update on and review of resolution 19/342 (The Parish Council to create a specific survey of Cherry Garden Road and discuss the results with CHP and CCC if appropriate). Concerns raised that a varying approach had been taken by City Council, over several years, on applications for cross green driveways on Cherry Garden Road. Before challenging them, GWPC need to know the collective preference of residents in terms of retaining the greens or giving some up for off road parking or access. Cllr Gilbert and Cllr Palmer to create a survey for review by the Parish Council. | 17th Febuary 2020 17.08.2021 | Clerk Cllr Palmer and Gilbert | 19.01.2022 | Survey created. To be debated at Oct 2020 meeting. Item Paused due to the Pandemic Cllr Steel to engage CCC in a productive discussion on their position. Surveys issued to residents.Clerk getting copies. Survey Created by Cllr Palmer and Gilbert and to be discussed 18th october 2021 Survey Has been issued and some responses received. 30 responses received by the 1st december 2021. Cllr Gilbert showed his anaalysis of the 35% feedback at the meeting on the 17.01.2022
21/803 | Discuss options to ensure a proper removal system or procedure for dealing with green waste from Parish council. Resolution Cllr Huggins to create a report and proposal Resolution Clerk to contact other parish Councils for information on how they deal with green waste. | 20.07.2021 | Clerk | 19.01.2022 | 25.07.2021 Clerk asked EALC to put an item in the Weekly Bulletin on how other Councils deal with their Green waste. No feedback from Clerk community. Cllr Huggins confirmf that there is no commercially available Green waste solution.
21/751 | Review of the Council’s complaints procedure. • Code of Practice for handling complaints • Code of practice for handling vexatious complaints Resolution Cllr McDevitt to review both policies | 2021-05-17 | Cllr McDevitt | 01.03.2022 | March meeting available for conclusion
21/984 | To consider proposed revised Councillor Co-option Policy wording. - Cllr Gilbert Resolution: Review the Poicy | 17.01.2022 | Cllr Gilbert
21/985 | To consider proposed revised Playground Safety Inspections Policy wording. Resolution: Policy to be reviewed | 17.01.2022 | Cllr Gilbert
21/997 | To discuss the recommendations contained in the report on the findings of the Cherry Garden Road parking survey. 36% responses with a variety of recommendations from the residents. Resolution Cllr Gilbert to prepare a term of reference for a working group | 17.01.2022 | Cllr Gilbert | 21.02.2022 | Working committee of Cllr Gilbert and Cllr Palmer The Working Group was cloased.
21/1052 | Note completion of review and no recommended changes to policy documents contained in the file circulated prior to meeting. Clerk to Upload the new versions as PDF on the website | 21.03.2021 | Clerk | 01.4.22 | Uploaded
21/1053 | Consider withdrawing the Policy on Bee Keeping on the Brook Mead allotments. Resolution: Approval withdraw from the website | 21.03.2021 | Clerk | 01.4.22 | removed
21/1054 | Consider the inclusion of a specimen Allotment Agreement in the policy files on the parish website. Resolutiion: Load on the website | 21.03.2022 | Clerk | 01.4.22 | Loaded
21/1060 | Discuss the previous agenda item 21/908 To consider SEPP recommendation to extend South Street Double Yellow Lines by 20m rather than the one car length requested by GWPC. SEPP recommendation is to extend the Double yellow lines for 20m along South Street from their current position to just beyond the tactile dropped Kerbs. SEPP view is that there should be restricted parking at tactile drop Kerbs. This will bring the area up to the latest regulations. Resolution Clerk to write to Essex Highways and request the removal of the tactile kerb. Resolution Clerk to contact SEPP to withdraw the request for any changes. | 21.03.2022 | Clerk | 12.04.2022 | Sepp acknowledged letter. Sepp has withdrawn the proposal. Item raised with Highways.
21/831 | Discuss the quote for painting the Broads Green phone box with paint provided by the Parish Council. Resolution Clerk to Appoint contractor to paint the phone box. | 17.08.2021 | Clerk | 16.05.2022 | George has blasted and primed the phone box. Slight delay as new paint had to be ordered. Outside of the Box has been painted. Internal paitng of the Box delayed due a a paint istmatch by X2 Connect - the Only paint supplier. Paint Supplier have suggested we used an older tin of paint which is why we have a mismatch in colurs. Clerk inspected the phone box inside and out and took photos. Finish is good no more action required at this time.
21/1057 | Consider a proposed positioning statement concerning future development of green areas along Cherry Garden Road. Cllr Gilbert to draft the response for all households in Cherry Garden Road. | 21.03.2022 | Cllr Gilbert / Clerk | 01.05.2022 | Draft releaswed to Members Letter issued to households
21/1065 | Review the decision not to supply mowers for allotment use. Resolution The Two Mowers that were placed erroneously on the asset register many years ago are to be written off as the assumption is they were donated. Resolution Write to all allotment holders at brookmead and remind them it’s their responsibility to keep their plots tidy and the grass cut. Resolution The Parish Council will maintain the mowers when required for this season only. Clerk to write to the allotment holders to inform them that they will need to make their own arrangements to cut their plots and can use the mowers, but the parish council will accept no liability or responsibility for use of the donated mowers. | 21.03.2022 | Clerk | 12.04.2022 | 1. Assets Written Off 2. Laminated Notices prepared. 3. Cllr Palmer asked to arrange review of one of the 'owned' mowers. Service of the Mower arranged. Letters and E-maisl send to the allotment holders at Brookmead.
21/1059 | Following presentation by Ride London, to review impact on GW parish and what actions, if any, GWPC wish to take. Resolution Clerk to draft a letter to the leader of Essex County Council with concerns about the lack of consultation with affected Parishes as a contact has been signed for a 5-year period. The Parish Council believes there is a lack of consideration about care receivers especially on the Sunday event. Concerns about the engagement officer being unable to answer questions. | 21.03.2022 | Clerk | 01.06.2022 | Letter Hs been Issued. Clllr Bentley acknowledged. Response awaited. Response recived and sent out to the Councillors. Item closed.
22/1127 | Review of inventory of land and other assets including buildings and office equipment. Resolution Add the Beacon to the 2022 Asset List at a replacement value. Resolution Clerk to remove the Ford End Village Gates from the Asset List as the gates were replaced by Highways and now belong to them. | 23.05.2022 | Clerk | 04.06.2022 | Asset list updated.
22/1137 | Discuss the Broomfield Parish Path proposal Resolution The Parish Council Supports this initiative. Clerk to make organiser aware that there might be bulls or cows in the field at Langley’s. Also, this is a rural footpath on private land – users must remain on the designated paths. | 23.05.2022 | Clerk | 04.06.2022 | Clerk wrote to the organiser.
22/1138 | Discuss the outcomes of the Annual assembly • Streetlight in Barrack Lane. • Grass cutting regime by ECC. • The cobbled area by Walthambury Stores/The Beehive needs attention. Resolution Clerk to reissue the grass cutting regime to the Council. Resolution Clerk to write to the landowner and asked them to tidy the cobbled area. | 23.05.2022 | Clerk | 04.06.2022 | Clerk issued the information from the city council. Clerk wrote to the Landowner - Her representative acknowledged and stated its on the list of jobs but quite far down.
22/1141 | Discuss an annual donation of £250 to the Great Waltham Charities. The pavilion lease is currently for recreation use for the next 18 years. The agreement with the Landlord will change to add the use of the pavilion for Hire purposes, a Parish office, Meetings and Storage. Cllr Micklem declared an interest. | 23.05.2022 | Clerk | 04.06.2022 | Clerk wrote to the landowner and included the suite of documents.
22/1144 | Consider a response to the current East Anglia GREEN consultation Agreed that the Council should respond to the consultation to make known its objections to the proposals. Resolution Cllr Gilbert to draft a response. All councillors are encouraged as individuals to write in with their views of the consultation. | 23.05.2022 | Cllr Gilbert | 043.06.2022 | Draft Prepared for issue by deadline.
21/1063 | Update on the Jubilee plans and the Beacon Resolution The Parish Council has agreed to pay for a jubilee tree at North end on to the common land. | 21.03.2022 | Clerk | 16.04.2022 | No Update Item closed as action complete.
22/1144 | Consider a response to the current East Anglia GREEN consultation Agreed that the Council should respond to the consultation to make known its objections to the proposals. Resolution Cllr Gilbert to draft a response. All councillors are encouraged as individuals to write in with their views of the consultation. | 23.05.2022 | Cllr Gilbert | 13.06.2022 | Draft Prepared for issue by deadline. Clerk to issue the information to National Grid.
22/1096 | Discuss measures we can take to reduce the impact of Graffiti to the buildings and playground equipment. Discuss holding a stock of suitable materials to clean up any graffiti – Pink Paste, graffiti Wipes, Resolution Approved to hold a stock of items – discuss with the handyman and Caretaker. | 25.04.2022 | Clerk | 04.06.2022 | Handyman suggets Pink Paste. Graffitti wipes in the Pavillion. Clerk to Move paint to the Pavillion for the Chilrfdrens Play equipment.
22/1166 | To consider the draft response to East Anglia GREEN consultation circulated prior to meeting. Resolution: The report issued to the meeting was approved. Resolution: Clerk to e-mail in the response direct rather than go through the Portal to avoid the initial question. | 13.06.2022 | Clerk | 13.06.2022 | Clerk has sent in the response from the Parish Council and recived an acknowledgement.
1 | Response from landlord to confirm agreed use of Pavilion and any change to tenancy wording. | Continue to seek update from landlord | 2022-03-18 | 2022-03-31 | 18/3/2022 (WG): Response from landlord awaited. 09/04/2022: Response still awaited. 12/04/2022 (WG): Response from landlord still awaited. Agreed PJ to contact Clerk to confirm current position, with a view to then contacting landlord. Agreed that without formal confirmation from landlord to document verbally agreed usage the Pavilion cannot be used for PC meetings or hirings. 13/04/2022: Clerk has confirmed to PJ that landlord has provided written consent to holding April PC meeting at the Pavilion. 03/05/2022: Clerk confirmed meeting with landlord has taken place and verbal agreement to conduct all activities requested, subject to £250 annual charitable donation. These items to be discussed at next (May) full PC meeting. DIscuss need to secure written confirmation of interpretation of lease. Review position at next WG meeting (after May PC meeting). 26/05/2022 (WG): Following resolution at 23/5 PC meeting to make annual £250 donation to GW Charities to satisfy landlord's agreement to new uses of Pavilion, agreed Clerk to write to landlord to confirm PC's understanding of previous conversation with him and to provide copy of PAV02 (Policy for Hiring document). Action to remain open, but transferred to PC monthly action tracker (Clerk to arrange). Item closed.
Draft and secure sign-off for Guidance/Checklist for Hirers | 2022-03-18 | 2022-04-30 | AM/SG | Closed | 18/3/2022 (WG): AM to prepare draft for WG review. Intention to secure Council sign-off at meeting 25/4/2022. 12/04/2022 (WG): AM to progress. Agreed document not essential until we are able to accept hirers. Completion date extended to 30/4. 03/05/2022: AM has drafted proposed document. SG to effect further agreed changes. To be shared before next WG meeting. 26/05/2022 (WG): Wording as proposed agreed. This document becomes PAV07. PAV08 (operating instructions for heaters) to accompany PAV07 when sent to hirers (with PAV 04 & PAV06) when a hiring is confirmed and paid. Agreed all documents relevant to hirers to be made accessible to Responsible Person(s) on site in laminated format in a folder. Clerk to source folder and laminate documents. Action to remain open, but transferred to PC monthly action tracker (Clerk to arrange). Item closed.
Insurance | When finalised, forward suite of documentation to brokers/insurers | 2022-03-18 | 2022-04-30 | Clerk | 18/3/2022 (WG): Awaiting completion and sign-off of documentation. 12/04/2022 (WG): Await document sign-off. 26/05/2022 (WG): Now documents signed off, Clerk to form suite to brokers/insurers for reference & retention on their records. Action to remain open, but transferred to PC monthly action tracker (Clerk to arrange). Item closed.
21/864 | Discuss the Tree survey and agree next steps. The survey contracted to Writtle Forest Consultancy was considered. This breaks activities out to: Work to be carried out within 6 months Work to be carried out within 12 months Work to be carried out within 24 months It was agreed that quotes for the 6 months and 12 month’s works should be obtained. There was a suggestion that in some cases removal of deadwood might be better substituted with the whole removal of the tree. Resolution Cllr Micklem to update the survey with advice on a deadwood cut versus a full felling of a tree (6 and 12months). Resolution Clerk to request 3 quotes for the tree works with a focus on the 6 month and 12-month work on the report. | 21.09.21 | Cllr Micklem and Clerk | 08.07.2022 | Tender has been released to 4 companies for pricing. One Supplier has submitted a price by the deadline. 6 Month work completed. Next setps to be confirmed. 12 months work out to tender. Feedback by 13.06.2022. Agreed that the 12 months woek be awarded to JCM and work undertaken 13.06.2022 112 Months work now complete.
22/1169 | To discuss and agree nominations to County Councillor for the Member Led Carriageway Pothole Repair Programme 2022. Two potholes were discussed in Barrack lane, but they were dismissed as they were not on the carriage way. New nomination of Church Lane in Ford End due to a large dip causing vehicles to dip. Resolution: Members to provide nominations of potholes by the start of July 2022 | 13.06.2022 | Clerk | 01.07.2022 | Two Nomination received - Bury lane and Church Lane and littley green road.
25 | External Walls | Consider strategy for cladding/g/painting external walls. | 2022-05-10 | 2022-06-30 | 10/05/2022: Quote for cladding received. Review costs cf. to alternatives at next WG meeting. 26/05/2022 (WG): Quote for cladding received (£3,900). Quote for rendering (with a view to then painting) £4670 Third alternative is to scrape out and fill gaps and repaint ourselves. Agreed to await quote for rendering. Also on agenda to discuss at Recreation Committee meeting 30/03/2022. Action to remain open, but transferred to PC monthly action tracker (Clerk to arrange). Item Closed as Parish Council does not wish to update the external walls.
21/898 | Discuss the Ford End 40mph Northern Buffer Zone. Cllr Steel declared a conflict of interest and did not take part in the debate but sought to Clarify the Parish Council’s needs. There have been various speed data monitors on the approach to Ford End, but the Village has changed with a business Park outside the Village and houses being developed. Speeding is a concern at the Northern End. Safe approach to and through Ford End. Move the 40MPH north of the business Park. The Traffic is entering the 30MPH too fast. It was noted that it can take up to 15minutes to cross the road. Resolution Clerk to write to the Essex County Councilor to Request another traffic / data count at a to be agreed point and raised several areas of concern. Resolution Clerk to draft the letter and share with the full Council. Cllrs Martin and Gilbert to provide the statistical data input. |  | Clerk | 2021-11-15 | ECC Cllr Steel Confirmed receipt of the letter LHP to keep this in the funded list and the 40mph is scheduled to be installed in Q4 of this financial year.
21/988 | Request from North End residents to add power back into the BT telephone box where North End have installed a defibrillator and heated cabinet. Resolution Clerk to ask BT if they can reinstate the power. | 17.01.2022 | Clerk | 13.6.2022 | There is no power in this telephone box. Potential to use solar power. Cost from UK power networks is around £1000 but is only for work on the Island and not for connecting up to the mains which would be a separate charge and supplier. BT will not reinstate the power. Only Option appears to be a solar option No update June 2022 - leave on the tracker. No update July 2022 - leave on the tracker.
22/1116 | Proposal for formation of a Highways and Transport Committee – Cllr Dunn Proposal for formation of a Highways and Transport Committee – Cllr Dunn Should there be a separate meeting for this committee’s suggested terms of reference? Suggestion that the Council’s existing transport representative role reports into the new committee. Resolution The Parish Council agrees to the creation of the Committee. Resolution The Terms of Reference to be drafted for the next meeting. | 23.05.2022 | Cllr Dunn | 26.07.2022 | Item differed until next meeting July 2022 Membership agreed 18.07.2022. Meeting to be held to agree the terms of reference. Meeting held on Tuesday 26th - Draft terms of reference have been created.
22/1167 | To consider authorisation for the Clerk and one other councillor to attend EALC village hall training modules. EALC Cost of £150 per Councillor and £37.50 for the clerk. The Council considered a lower cost model by using the Rural Community Council of Essex (RCCE). Resolution: Cllr Palmer to contact RCCE for advice and any potential training. | 13.06.2022 | Cllr Palmer | 15.08.2022 | Clerk wrote to RCCE for assistance. Cllr palmer to chase through. Cllr Palmer has contacted RCCE for advice. Advice was recieved.
24 | Village Hall | Consider mechanism for moving Parish Office to Pavilion. | 2022-04-05 | 2022-05-31 | 05/04/2022: Confirmation Parish Office facilities can be moved (both in accordance with lease and physically) to Pavilion. Then consider strategy for ending current arrangement with VH. 12/04/2022 (WG): Agreed any engagement with VH should only begin when Pavilion fully operational for all required usages. In meantime SG to circulate copy of current agreement with VH for information. 26/05/2022 (WG): Agreed item to be added to next PC monthly meeting agenda to initiate discussion on whether to engage with VH (SG/Clerk to ensure item added). Clerk will move the remaining office equipment Clerk cleared out of the Parish Hall .
22/1197 | Discuss the terms of reference and membership of the Highways and Transport Committee. The terms of reference for the Committee will be reviewed and agreed at an informal meeting for presentation to the August meeting of the Parish Council. The membership of the Committee was discussed and agreed. Resolution: Membership of the committee to be the Parish Council Chairman , Vice-Chairman and four members. Resolution: Councillors Dunn, McDevitt and Lockwood were elected to the committee. Cllr Palmer was elected (in absentia) as Transport representative. Resolution: Draft terms of reference to be circulated by Cllr Dunn to members of the Committee. | 18.07.2022 |  | 15.08.2022 | Meeting held 26.07.2022 The TOR was adopted at the meeting on the 15.08.20022
22/1168 | To discuss and agree the Council’s options and its future position in relation to the continued hire of a parish office space at the village hall. The current lease on the Great Waltham Village Hall Blue room has a break clause of October 2023 It is felt that the Parish office in the Village Hall no longer meets our needs. Resolution: Clerk to contact the Chairman of the Village hall and arrange a meeting to discuss the break clause in the contact with Cllr Dunn and Cllr Gilbert. | 13.06.2022 | Clerk | 18.07.2022 | Receipt by Chairman of the Village Hall trustees Acknowledging. Meeting held with the Chairman of the GWVH by the Chair of the GWPC and the Clerk Correspondence with Pre school - Meeting to be arranged for sub letting Meeting to be arranged with pre School management team late August 2022 to discuss. Waiting on Pre School Managers returning from Holiday Agreement with preschool in principle. Village Hall Commitee to approve the agreement.
22/1199 | To consider for approval these draft documents (required for LCAS accreditation) circulated prior to the meeting: bio-diversity policy, crime and disorder policy, publications scheme. The meeting considered the revised draft of the crime and disorder policy document circulated to members prior to the meeting by Cllr McDevitt. Some minor changes to the wording of the biodiversity policy document were proposed and agreed. Resolution: The revised Crime and Disorder policy wording as proposed by Cllr McDevitt was approved with some minor changes. Resolution: The Biodiversity policy was approved with some minor changes in relation to allotments and the wooded area on Ford End recreation ground. Resolution: The publication scheme wording was approved. | 18.07.2022
22/1170 | To review the success of the Blossom Way public parking facility, including complaints and whether any actions need to be taken. Concerns raised over commercial vehicles parking in Blossom way. Resolution : Highlight Public parking is available in Blossom way. Resolution: Cllr Steel to create and post the Blossom Way parking regulations on the Scout fence | 13.06.2022 | Cllr Steel | 18.08.2022 | Cllr Gilbert has drafted a notice. Cllr Steel has published the notice on the Scouts Fence .
22/1201 | To agree the Council’s representatives at the Remembrance Sunday events at Great Waltham and Ford End. Resolution: Cllr Gilbert will represent the Parish Council at Great Waltham. Resolution: Cllr Martin will represent the Parish Council at Ford End. | 18.07.2022 | Clerk | 15.08.2022
22/1195 | Report on the meeting with the Great Waltham Village Hall Chairman to discuss exiting the Parish Office by October 2023. The Chairman of the Parish Council and the Clerk met with the Chairman of the Village Hall to seek a compromise and potential early exit from the lease on the Blue Room. The Parish Council hold a lease until October 2023 and the Village Hall indicated it requires this to be honoured. Since the facility no longer meets its requirements, the Parish Council has given notice to terminate the lease – which has been accepted by the Village Hall. For the period to October 2023 the Parish Council is looking to introduce a replacement leaseholder. Resolution: All members asked to pass on any enquiries from suitable replacement leaseholders to the Clerk | 18.07.2022 | Cllrs Dunn , Gilbert and the Clerk | 18.08.2022 | Waiting on managers returning from Holiday to hold a meeting or an e-mail exchange. Meeting has been held and there is a proposal to be discussed by the Parish Council.
21/860 |  | Discuss options for the perceived speeding in Howe Street Some members of the public contacted the Parish Councillors with concerns and suggestions. Move the 60MPH from just outside the Village to beyond the bungalow called – ‘straight’. Suggestions included solid lines on the road, speed bumps, chicanes. The report from the County Council shows GWPC SID measurements were avg 34mph and that there are no collisions recorded. It was suggested that the SID readings are done again and that residents be invited to join the Community Speed Watch (CSW). Part of the process requires that CSW submit a requirement for a “safe” site in Howe Street which needs to be done by the GW coordinator. Resolution Consider adding Howe Street members to the GW speed watch group and registering a safe site in Howe Street Resolution Move SID to Howe Street to run latest data set one week covert, one week with display. | 21.09.21 | Clerk | 01.11.2021 | Sid Data to be run.
20/469 |  | 20/469 To consider public request to extend double yellow lines on South Street slightly beyond the point where the road starts to widen. A request from the public has asked if the double yellow lines could be extended further along South street, from the Chelmsford Road junction, such that vehicles were prohibited from parking until the road further widens. Resolution Reduce the on-street parking by one parking space the space nearest to the junction. Resolution The Clerk to make the request to the South Essex Parking Partnership. | 2020-08-17 | Clerk | 15.11.2021 | South Essex Parking Partnership to assign a technican to inspect the road and make a recommendation. Technican agrees. But wants to extend by 20m rather than the 2 or 3 m request. No comment from the Parish Council. Lines will be created once funding is available. One Complaint received
2771174 |  | Remove the tactile kerb outside the Great Waltham Village Hall | 30.03.2022 | Clerk
2778851 |  | Streetlight Issues outside the School | 25.05.2022 | Clerk
22/1178 | Approve the next round of tree management works. 5 Quotes were sought but only one was received by the deadline. Resolution: The Parish Council approved the quote from JCM of £2392.80 (IncVAT) Resolution: On completion of all the works budget for another tree management survey in 3 to 5 years. | 13.06.2022 | Clerk | 14.06.2022 | JCM were asked to proceed with the works. Week Commencing 4/the July Tree works completed. Clerk to Forward Plan next tree survey 2024-2025 and add to the Budget.
22/1269 | To consider and agree the Highways & Transport Committee's recommendation that the Council remains committed to the installation of average speed cameras through Ford End. Resolution The £10,000 earmarked reserve for the speed camera to be retained for another 12 months. | 19.09.2022 | All |  | Marked in the reserve for 12 months as earmarked reserves
21/1058 | Consider a proposal that the Council seeks Local Council Award Scheme Foundation level status (see details on p.6-9 of document circulated prior to meeting). Resolution Approved to seek Foundation status. | 21.03.2022 | Cllr Gilbert / Clerk | 15.08.2022 | Review of actions. Clerk to get input from EALC LCAS structure reviewed and agreed to work on. Documents to be agreed the July Meeting. ¦Clerk to build up ¦CPD points and gather additional documents. Cllr Gilbert has completed Gap analysis and identified work needed. The polices have been drafted and will be approved during the July meeting. The main item outstanding is the Accessibility report.This has been submitted for review to the Chairman.
22/1200 | To confirm that the Council will lead on November Remembrance Sunday events and form a committee including the British Legion, church, and other local organisations. Cllr Gilbert updated the meeting on the initial meeting held with the Royal British Legion , Parish church representatives and others on 11th July. That meeting agreed the arrangements for 2022 will very much follow the format of recent years. Volunteers at the event will again be covered by the Council’s insurance arrangements. The next meeting of the organising committee is on 6th September. Resolution: The Parish Council to lead on the Remembrance Sunday events at Great Waltham. Resolution: The Parish Clerk to apply for the road closures in Great Waltham. | 18.07.2022 | Clerk | 17.10.2022 | Clerk has applied for the road closures. Clerk is dealing with some minor details. As agreed with Cllr Steel - Nick Binder has been contacted for support and resolution. All actions Complete
22/1202 | To authorise the purchase of two wreaths for the Remembrance Sunday services. Cost expected to be around £50. Resolution: Parish Clerk to arrange the supply of two wreaths from the local branch of the British Legion | 18.07.2022 | Clerk | 21.10.2022 | Clerk Contacted British Legion Local Branch Cllr Gilbert highlighted to the committee that two wreaths will be required.
22/1226 | Resolution The Clerk to contact Chelmsford City Council to understand when the final verge cut will take place on behalf of Essex Highways | 15.08.2022 | CLERK | 17.10.2022 | CLERK HAS CONTACTED OFFICERS FOR ROUGH DATE. No information recived. Request no longer relevant.
22/1262 | To discuss and agree the Council’s response to Chelmsford City Council’s Review of Adopted Local Plan – Issues and Options Consultation 2022 (copy circulated with the agenda). The consultation has been extended to the 20th of October 2022. During Summer 2023, a draft of the new plan will be issued. In Early 2024 a pre-submission plan will be issued. The consultation document has a number of Spatial Options. Approach C indicates the potential addition of up to five hundred houses to be built across six villages – two of which are Great Waltham and Ford End. The plan overall is for eight thousand houses to be built across the Chelmsford Area. Resolution: As an indication to the author of the draft response there was a vote for none of the options that include sizable developments in this Parish. Resolution: Cllr Gilbert to review the options, draft a response and bring back to the next meeting. | 19.09.2022 | Cllr Gilbert | 17.10.2022 | The consultation was released to Chelmsford City Council after it was approved.
22/1264 | To consider and agree costs associated with the Great Waltham Remembrance Sunday Parade. See also comments in 22/1247 above. The traffic signs and notifications will be supplied at no cost for this year due to South Essex Parking Partnership (SEPP) agreeing to the use of local volunteer marshals who will be covered by the Parish Council Public Liability insurance. Resolution Cllr Gilbert to confirm with the Royal British Legion that the wreaths are on order. Resolution £50 Donation for the wreaths | 19.09.2022 | Cllr Gilbert | 17.10.2022 | All action completed.
22/1237 | The PC spent a significant sum clearing brambles and nettles from Pump Green in North End, action 21/928 refers. This action was necessary because the area had not been mown by the handyman in the past and this resulted in the need for remedial work to cut down the brambles. The original proposal also referred to the need to ensure that future regular mowing be implemented by the handyman to prevent regrowth of the brambles. Unfortunately, this has not been implemented and the brambles are beginning to regrow at an alarming rate, I therefore propose that regular mowing of the green up to the fence be included in the handyman’s future maintenance schedule unless the handyman is unable to do this, which case, if necessary, the PC will take advice to determine the best approach to maintaining the recently cleared area. The land is registered as common land. Resolution The Clerk to arrange for JCM to cut the brambles on an annual basis at Pump Green at a cost this year of £168 (inc. VAT). | 15.08.2022 | CLERK | 17.11.2022 | JCM asked to proceed. JCM has not undertaken the work yet - October Novermber - Confirmation of completion required.
19 | Wi-Fi Access | Investigate and report back to working group on options to secure Wi-Fi access | CLERK | 17.11.2022 | 18/3/2022 (WG): AM to report back to WG. 12/04/2022 (WG): AM to initiate discussions re: optimal way forward once electrical equipment installation completed. Completion date extended to 30/4. 26/05/2022 (WG): Feasibility yet to be established once meter conversion process progresses. Action to remain open, but transferred to PC monthly action tracker (Clerk to arrange). Clerk to contact BT to arrange WIFI for the pavilion. Clerk working to get Royal Mail to accept the site as a delivery point so that BT can work to a fixed site. The Post Box has been fitted so that the unit can receive file. The Post box has been vandalised twice. The second time its been destroyed. A new Stronger and more expensive unit purchased. WiFi is available as a Mobile option.
22/1236 | To consider the Council's involvement and role in the walkover surveys being planned by National Grid's East Anglia GREEN enablement project Resolution The Parish Council will take no direct involvement in the walkover surveys but will continue to monitor the project. | 15.08.2022 | CLERK | 17.11.2022 | No update
22/1260 | Review complaints about vehicles parked at Blossom Way public car park which contravene the terms and a motion to determine and implement necessary actions. Issue raised by residents about a caravan being parked in the public parking spaces this has now been removed. There was a discussion on types of commercial vehicle, and it was confirmed that two vans are parked in the public spaces. One resident of Cherry Garden Road and one resident of Duffries Close. Although there is plenty of parking space the terms of the Council’s lease with CHP prohibits the parking of commercial vehicles in these bays. Resolution Clerk to draft and write letters to the commercial vehicles’ owners parked in the spaces highlighting the terms of the lease and asking them to make alternative arrangements. | 19.09.2022 | Clerk | 17.11.2022 | two commercial vehicles were 'ticketed' in October. Novermber agenda
22/1265 | Discuss and agree allotment hiring fees for period 1/4/2023 to 31/3/24.-Cllr Gilbert. The meeting noted and discussed the timing issues related to how hiring fees are invoiced to plot holders – in particular, that the Council has to give 6 months’ notice of increases. The charging year is September 2022 to September 2023 in line with the agreement with the landlord. The current charge that has already been shared with plot holders will run until April 2023. The meeting noted the continued level of subsidy for the provision of allotments (40% - 50% in a typical year), and that this year the cost for the provision of water on the sites will exceed the budget provision. Resolution Charge new rent from 1st April 2023 - £4.00 per rod for 6 months Resolution Service Charge from 1st April 2023 - £7.00 per plot for 6 months | 19.09.2022 | Clerk | 17.11.2022 | Allotment Agreement being signd 07.11.2022 Allotment agreement signed by the Parish Council. Invoices issued December.
22/1266 | Pavilion Review, to include bookings update and feedback received and to consider the Recreation Committee’s proposal to replace the wooden shutters with metal roller shutters and to resolve storage issues by purchasing and positioning a small metal storage container at the end of the Pavilion. There are a variety of current and anticipated bookings for the use of the facility. These include clubs for bridge, art, history, dance, toddlers, and health & wellbeing. There was a social hire for a 70th birthday party and there is a Christmas carols hire planned. Feedback from users has been a requirement for privacy screens for the glass doors, a coat rack, additional outside lighting, and changes to the external wooden shutters. Resolution A spend of up to £150 for internal blinds for the door was approved. Resolution A spend of £20 for an external solar light was approved. Resolution Approval to install window shutters . Recommendation to have metal roller shutters. Quote for £2610 (+vat) approved . Resolution Budget for a storage container for the Great Waltham Recreation Ground to be included for 2023-2024 Resolution A shutter on the door to be reviewed at a future date | 19.09.2022 | Cllr Martin | 17.11.2022 | October - The Light is fitted. , The Blinds are being ordered , the Shutters - a new supplier being reviewed. Container is under consideration and has been added to the budget. Shutters have been orde3red.
22/1268 | Agree the Recreation Committee's recommendation to accept the landlord's proposed updated terms and conditions for leasing the Brook Mead and Bury Lane allotment sites. Cllr Micklem declared an interest. Proposed 5-year lease with a rent review at each 2-year anniversary. Resolution The Parish Council accepted the proposed terms and conditions. Resolution Clerk to contact the landlord for a clean copy of the new agreement. | 19.09.2022 | Clerk | 17.11.2022 | The agreement to be signed once a clean copy is presented. Clean Copy is available for signature 07.11.2022 The Allotment agreement has been signed by the Parish Council.
22/1286 | Clerk’s Report and actions. • The Clerk and the Handyman timesheets were reviewed with the information submitted prior to the meeting. The Clerk highlighted the type of work undertaken over the last period and the planned work. • The Handyman plans to prepare Banbury Square for the Remembrance Sunday parade amongst the more usual work of litter picking, strimming, hedge cutting, leaf collection and equipment inspections. • Speed indication device (SID) reports have been submitted to members for review. • Clerk has built the budget for next week’s meeting and plans to issue the annual allotment invoices once the new agreement has been signed by the landlord. • It was acknowledged that the Clerk is working in excess of his contract 21 hours which triggers overtime payments. Resolution: The Clerks hours and job specification to be reviewed by the Staffing Committee to consider whether all tasks being undertaken are appropriate to the role. | 17.10.2022 | Staffing Committee | 17.11.2022 | Meeting held . Data reviewed. Agenda Item Novermer Monthly Meeting.
22/1328 | Discuss the statutory consultation on National Grid Anglia Green Resolution: The Council agreed that Cllr. Gilbert should contact The Planning Inspectorate as appropriate to ensure the Council’s objections to the project as proposed are sustained. | 17.11.2022 | Cllr Gilbert | 10.12.2022 | Information e-mailed through
22/1267 | Review the provision of defibrillators within the Parish and consider whether the Parish Council should assume a role in their administration and availability. A recent incident in the Parish highlighted that of the 6 units in the Parish 3 were unavailable. These units were installed by public donations through a previous Parish Councillor. The units of concern are: – Ford End VH – Ford End. – Fitz Andrews Farm – Howe Street. – Walthambury Stores – Great Waltham. Resolution Cllr Martin to discuss with Cllr Palmer Resolution Cllr Lockwood to discuss with Fitz Andrews Farm. | 19.09.2022 | Cllrd Martin and Lockwood | 17.11.2022 | An ongoing review to be undertaken. Parish Council to budget to replace the units as they become unuseable. Entered on the GWPC budget 2023-2024
22/1203 | To consider and agree whether the Great Waltham Recreation Ground’s perimeter hedging requires remedial work. Cllrs Dunn and Martin shared a report at the meeting that highlighted two gaps in the hedge and the level of rot in the wooden entrance at Hatchfields. It was agreed that the perimeter hedge close to the Hatchfields gate should be infilled with new hedge where necessary. Resolution: The hedge to be repaired with a post and rail fence section with chicken wire. Resolution: Hedging to be planted behind the fence. Resolution: The Parish Handyman to install the fence and plant the hedge at the appropriate time of year. Resolution Suspend the financial regulations to allow a single quote to be accepted due to the concerns about the collapsed state of the hedge and fence line. Resolution Quote from JCM for £1698 to be accepted. | 18.07.2022 | Clerk | 19.12.2022 | Discuss at the Recreatio9n Committee in September. JCM quote being reviewed.# Recreation Committee recomends all work undertaken by JCM due to the nature of the compacted soil. The work has been ordered. Waiting on JCM to start the work. 10.11.2022 - JCM asked to get on with the work. Clerk to Follow up. Completed January 2023
LCHE182051 | Funded | B1008, Northern approach to Ford End - 40mph buffer | 40mph buffer | Total scheme | 10500 | Implement a 40mph buffer, will require a TRO | Q4 | G | 2022-23
22/1270 |  | To consider and agree the Highways & Transport Committee's recommendation that it contacts ECC's Highways, Maintenance and Sustainable Transport cabinet member to arrange a meeting to discuss how strategic ECC projects will influence road usage in the parish. Resolution This recommendation was agreed. |  |  |  | Meeting has been held - Decmber 2022
22/1321 |  | To note feedback from the latest 20's Plenty presentation and agree the Council's next steps Cllrs. Gilbert and Martin reported on the latest 20’s Plenty presentation (webinar) as facilitated by EALC. The overarching objectives of the pressure group’s campaign are persuasive in that they seek to reduce traffic speeds and reduce the hazards when motor vehicles are more likely to mix with pedestrian and cycle traffic. However, whether the proposed solution (an Essex-wide 20mph default speed limit with agreed higher exceptions) is more a reaction borne of parish councils’ frustration in securing action for their specific local traffic/speeding issues, than a viable practical way forward is perhaps debatable. The webinar setting was not the opportunity for a more detailed dialogue to secure a firm assessment of how the campaign’s proposals would improve road safety in the parish. Resolution: It was agreed that organisers of the 20’s Plenty campaign in Essex should be invited to the Council’s next Highways & Transport Committee to secure a firmer understanding of any benefits to be obtained by the Council endorsing the campaign | 22.11.2022
|  | 20 is Plenty Campaign | 07.09.2022
21/1028 |  | Feedback on the bus services in the Parish The changes by First have affected several parishioners. The X10 and X30 have created a lot of confusion and drivers do not always stop at North End. Barnston is the changeover point to get to Great Dunmow. The Service is viewed as not fit for purpose and will drive more people to use cars or alternative means of transport. Resolution Clerk & Cllr Palmer to write to the MD of FirstBus to raise concerns about the poor service. | 21.02.2022 | Cllr Palmer | 13.02.2023 | Clerk has provided Name of Bus MD. Cllr Palmer to provide the detail for the complaint. Cllr Palmer has sent the letter to the MD. - No respo nse Cllr Palmer to Chase up. DigiBus is working well. Close this item
22/1233 |  | Resolution Fact finding from other councils and consideration of further engagement and action deferred to the Highway and Transport Committee.
2022 11 07 | 7 | Update on the review into allotment labour requirements. | Resolution Cllr Palmer and Cllr Micklem to make a recommendation before the monthly meeting on the 21st of November. | Cllr Palmer and Cllr Micklem |  | 2 hours for brookmead and 2 hour for bury lane per month.
2022 11 07 | 13 | Consider the view that land drainage is not an option for Ford End recreation ground and to progress the option to verti-drain and roll the ground. The problem of water retention in the ground at Ford End was discussed and it was reported that the suggestion of land drains had been investigated but it was felt by the contractor that there would be limited benefit for the potential cost and suggested that verti-drain and rolling would be the preferred option to improve the surface. | Resolution Defer this item subject to the second consultation being accepted by the Parish Council. | Cllr Martin |  | defer until finalised
2022 11 07 | 15 | Review the Ford End Recreation Ground Consultation 2 results and propose recommendations to the full Council. Thirty-eight responses have been received via post , e-mail and hand delivered. The consultation posed five different questions with a number of response options for each question. Some of the results show clear preference. The overall trend supports the initial Parish Council consultation. It is noted that the two sets of Parish Council results are different to the petition undertaken by a resident of Ford End. The Consultation 2 results indicated a preference for the following: • Picnic benches should be placed within the planned picnic area • Benches should be scattered around the field • The installation of a Multi Use Games Area (MUGA) • The provision of a perimeter path • The play area should not be fenced. In addition several comments were provided to the questions asked. The detailed results are available to view on the Parish Council website. | Resolution The Consultation to be recommended to the Parish Council to accept the results of consultation two. | All |  | to continue
2022 11 07 | 17 | 17. Update on PSS software demonstration. The supplier can create a free demonstration for the Parish Council. This could be used for the Play equipment and allotment inspections. Cost of approximately £200 per annum using a ‘pay as you go’ model. The information is stored on the web. The data can be exported if we were to stop using the service. The software can be accessed by smartphone, tablet or computer. It was also discussed that there is a potential to combine the need for the allotments, playgrounds, asset management, pavilion bookings and accounts into a single system. | Resolution: Cllr Palmer will arrange a demonstration with PSS for all members. Resolution Clerk to arrange free demonstrations for all member of the committee as these will be webinars. | Cllr Palmer |  | ongoing
2022 11 07 | 23 | Update on the Allotment Supervisor role, inspection process and associated administration. A transparent process of inspections to be drafted. Currently we use a monthly report. Report to be split into Spring / Summer / Autumn. The inspections will include the following aspects: • Has cultivation started? • Is the plot being worked / unworked / monitor (monthly report) • Is the plot free of weeds? • Are paths strimmed / cut ? • Any chemicals on the plot ? • Any glass or hazards on the plot ? • Are all belongings within the plot ? • Nothing against the fences? | Resolution: Cllr Gilbert will build a spreadsheet for the allotment inspector. | Cllr Gilbert |  | Spreadsheet has been built
2023.02.06 | 6 | Update on allotment invoicing for 2022-2023. 10 allotments were outstanding on the 1st Feb. | The Clerk to continue to follow up with allotment holders. | Clerk
2023.02.06 | 8 | Discuss the latest information relating to the Howe Street Multi Play replacement. The Report is availabe online in the agenda area of the Parish Council website. | Recomment the Pandora metal unit as its guarenteed for 20 years at a cost of £20,398.34
2023.02.06 | 9 | Discuss arrangements for the 2023 Play in the Park date | Add to the tracker. 16th August . Cllr Jenkins to take a lead on the day and support.
2023.02.06 | 17 | Proposal for an allotment open day in April, an opportunity to work alongside GWHS (promoting membership) and encouraging take up on our allotment sites. | A date in April to be agreed. The committee supports this initiative.
2023.02.06 | 10 | Discuss and consider income generation opportunities. | Discuss with the landowner on potential commercial opportunities. Potential opportunities to be raised at the next meeting. |  |  | Landonwe declined to have Council events.
2023.02.06 | 14 | To discuss a draft strategy for recreation grounds within Great Waltham parish and make a recommendation to the Parish council | Review other parish Council documents to aid the build of the document. Add this item to the tracker document. |  |  | Has been agreed.

## Rules agreed
Minute Refrence | Detail of resolution | Date Originated | Action By | Last Updated | Current position
23.04.2018 Item 35. | The Chairman stated that he wanted future agenda items to be made in writing and phrased in terms of a proposal or motion and these are to be clear and unambiguous on what the item is about. This is in line with EALC guidelines to ensure that other Cllrs and members of the public know enough about the issue so as to be prepared in advance. The Clerk would ensure these objectives were met and that the agendas included the name of the proposer so that they can introduce the item at the meeting. Therefore, this section is no longer required. | 23.04.2018 | ALL | N/a
19/378 | 19/378 Discuss Media Channels – Facebook, Tick/Tock and Instagram Resolution Promote the website Resolution Promote the Agendas and Minutes on Waltham and Broomfield face book. | 16.03.2020 | Clerk | 2020-09-01 | Ongoing
20/373 | Discuss the recent spate of vandalism around Great Waltham Village and Park. The frequency of incidents appear to have increased. Residents are being encouraged to report to 101 or police on-line, and also to CHP ASB site if applicable. Police and CHP have been engaged and the number of incidents appear to have reduced. Resolution: Continue to monitor the situation. | 22nd April 2020 | All | 2020-09-01 | Use 101 on any incidents
20/436 | To consider what action GWPC can take to address hedges overhanging pavements and causing safety hazard Overgrown hedges are an offence under the 1980 Highways act. Discussion on hedges being cut back to within the householder’s boundary. 3 properties identified in Great Waltham and Howe street. Resolution Cllr Palmer to be point of contact for issues in Great Waltham and Cllr Jackson to be point of contact for Howe Street. Ford End to be dealt with by the Clerk via letter. Other Cllrs to raise any issues with the Clerk for passing these on. | 20th July 2020 | All | 2020-09-01 | Householders have been contacted in person.
20/445 | To review the need for the provision of a GWPC mower at Bury Lane Allotments following new information that allotment holders have not had access to the “communal mower”, and are using their own to keep their surrounding area tidy Resolution Communal areas to be strimmed by Handyman, plot holder to continue to mow their surroundings. | 20th July 2020 | Handyman | 2020-07-01 | Ongoing
FGP - Line item 5 | Resolution Review the Office equipment spend Resolution Split the Pension Payments in to Employee and Employer for the next budget Resolution review the accuracy of the budget for the next precept | 27th July 2020 | RFO | 2020-09-01
20/474 | Blanket authorization for the Clerk to use Facebook sites – The Waltham Grapevine, Broomfield & the Waltham’s and Ford enders to improve community engagement by broadcasting any relevant Govt notifications and consultations. | 17th August 2020 | Clerk | 2020-09-01 | Ongoing
19/017 | 19/017. To reflect on the biannual parish litter pick with reference to frequency and publicity. During the debate it was agreed that the nomination of a coordinator in each Village or hamlet would make the process better. Ford End currently do not have a nominated person. Additional Publicity from the coordinator should improve attendance. Resolution: Clerk to ensure that the item is on the agenda in January and August to enable publicity. | 15th April 2019 | Clerk | 01.08.2020 | Ongoing
Monthly Meeting 23.04.2018 - Item 35 | 35. Items for the Next Agenda The Chairman stated that he wanted future agenda items to be made in writing and phrased in terms of a proposal or motion and these are to be clear and unambiguous on what the item is about. This is in line with EALC guidelines to ensure that other Cllrs and members of the public know enough about the issue so as to be prepared in advance. The Clerk would ensure these objectives were met and that the agendas included the name of the proposer so that they can introduce the item at the meeting. | 23rd April 2020 | Clerk |  | Ongoing
20/536 | Clarify Parish Council Standing Orders In Relation To The Allocation Of Tasks. It was decided that resolutions would be clear and defintitive in line with standing orders. Resolution: To be clear on allocation of tasks and support. | 19.10.2020 | Clerk |  | Ongoing
21/809 | The Recreation Committee recommends that a record of repairs forced by vandalism be recorded and an annual report generated to highlight the annual cost of vandalism within the parish. Information to be reported on Facebook and information held on the accounts. Create and add to the accounts for tracking expenditure. Resolution All Vandalism Damage to be Collated and issued. | 20.07.2021 | Clerk |  | Move to Rules agreed.
21/990 | Clarify the purpose of the Highways tracker as part of the Action Tracker. Expand the highways tabs to includes highways related matters. Potential to have a highways and transport committee. Resolution: Expand the information and review in May. | 17.01.2022 | Clerk
22/1240 | Resolution Anyone who undertakes an authorised volunteering activity on behalf of the Council must be registered as a volunteer. For organised group events, volunteers must be registered with the event co-ordinator and the event itself registered by the co-ordinator with the Chair of the Parish Council. | 15.08.2022
22/1258 | Resolution At the discretion of the Clerk, keys can be given to hirers where required due to a lack of availability of key holders. | 26.09.2022
22/1323 | To agree an increase of hours for the Clerk/RFO roles, in accordance with recommendations provided by the Staffing Committee – Staffing Committee Resolution: Agreed that all requests for overtime over and above the 25 hours per week to have prior authorisation from the Staffing Committee (or in their absence, the Chair). | 21.11.2022
22/1313 | The Recreation Committee proposes that the Council accepts the results of the Ford End Consultation 2 – Cllr Martin. The meeting noted that each of the questions posed in the consultation achieved a majority preference. Resolution: The Council accepts the results of the consultation which will now be used to inform future decisions on the design and allocation of resources at Ford End Recreation Ground | 21.11.2022

## Land within the Parish unowned
Description of the area | Update | Village / Hamlet
Small piece of grass between the Shop and the CHP bungalows at Brook Mead | The Ownership is unknown | GW
The Land between Hatchfields entrance and the CHP bungalows backing on to Main road | The Ownership is unknown | GW
The Car Park and green area in DickeyMoors - Sits outside of South House Trust | The Green areas were passed to Chelmsford City Council Control | GW
The Ownership of the Car park is unknown
The Domestic heating Oil Pump Station building = Junction of The Old School House / Village Hall/ Hatchfields | The Ownership is unknown | GW
The Path in to the Churchyard through the "Millenium Gateway" at Great Waltham | The Ownership is unknown | GW
Land between Eagle Villas and The Old Spread Eagle at Ford End Village Entrance | The Ownership and maintenance is unknown | FE