## Rural Grass
2025 Rural Grass Cutting Programme |  |  | scheduled work | 2024
work started
|  |  | work completed | 1 | 2 | 3 | 4 |  |  | 5 | 6 | 7 | 8 | 9 |  |  | 10 | 10 | 11 | 12 | 13 |  |  | 14 | 15 | 16 | 17
|  |  | 2025-04-14 | 2025-04-01 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-17 | 2025-09-22
Parishes | Area | Ward | District area | 1st Junction visibilty Cut | [7 empty] | 2nd Junction Visiblity Cut | [7 empty] | 3rd Junction Visibility Cut
Turweston | North Buckingham | Buckingham West | Aylesbury
Westbury | North Buckingham | Buckingham West | Aylesbury
Shalstone | North Buckingham | Buckingham West | Aylesbury
Biddlesden P | North Buckingham | Buckingham West | Aylesbury
Lillingstone Dayrell | North Buckingham | Buckingham East | Aylesbury
Leckhampstead | North Buckingham | Buckingham East | Aylesbury
Lillingstone Lovell | North Buckingham | Buckingham East | Aylesbury
Akeley | North Buckingham | Buckingham East | Aylesbury
Stowe | North Buckingham | Buckingham East | Aylesbury
Water Stratford | North Buckingham | Buckingham West | Aylesbury
Radclive cum Chackmore | North Buckingham | Buckingham West | Aylesbury
Maids Moreton | North Buckingham | Buckingham East | Aylesbury
Foscote | North Buckingham | Buckingham East | Aylesbury
Thornton | North Buckingham | Winslow | Aylesbury
Beachampton | North Buckingham | Winslow | Aylesbury
Whaddon | North Buckingham | Winslow | Aylesbury
Nash | North Buckingham | Winslow | Aylesbury
Thornborough | North Buckingham | Buckingham East | Aylesbury
Buckingham | North Buckingham | Buckingham North | Aylesbury
Tingewick Parish Council | Winslow and Claydons | Buckingham West | Aylesbury
Barton Hartshorn | Winslow and Claydons | Buckingham West | Aylesbury
Chetwode | Winslow and Claydons | Buckingham West | Aylesbury
Preston Bissett | Winslow and Claydons | Buckingham West | Aylesbury
Hillesden | Winslow and Claydons | Buckingham West | Aylesbury
Gawcott with Lenborough | Winslow and Claydons | Buckingham West | Aylesbury
Padbury | Winslow and Claydons | Winslow | Aylesbury
Adstock | Winslow and Claydons | Winslow | Aylesbury
Great Horwood | Winslow and Claydons | Winslow | Aylesbury
Addington | Winslow and Claydons | Winslow | Aylesbury
Winslow | Winslow and Claydons | Winslow | Aylesbury
East Claydon | Winslow and Claydons | Grendon Underwood | Aylesbury
Steeple Claydon | Winslow and Claydons | Grendon Underwood | Aylesbury
Twyford | Winslow and Claydons | Grendon Underwood | Aylesbury
Poundon | Winslow and Claydons | Grendon Underwood | Aylesbury
Marsh Gibbon | Winslow and Claydons | Grendon Underwood | Aylesbury
Charndon | Winslow and Claydons | Grendon Underwood | Aylesbury
Edgcott | Winslow and Claydons | Grendon Underwood | Aylesbury
Calvert Green | Winslow and Claydons | Grendon Underwood | Aylesbury
Middle Claydon | Winslow and Claydons | Grendon Underwood | Aylesbury
Quainton | Winslow and Claydons | Great Brickhill | Aylesbury
Grendon Underwood | Winslow and Claydons | Grendon Underwood | Aylesbury
Hogshaw | Winslow and Claydons | Great Brickhill | Aylesbury
Granborough | Winslow and Claydons | Winslow | Aylesbury
North Marston | Winslow and Claydons | Great Brickhill | Aylesbury
Oving | Winslow and Claydons | Great Brickhill | Aylesbury
Whitchurch | Winslow and Claydons | Wing | Aylesbury
Hardwick | Winslow and Claydons | Wing | Aylesbury
Pitchcott | Winslow and Claydons | Great Brickhill | Aylesbury
Little Horwood | Brickhills | Winslow | Aylesbury
Swanbourne | Brickhills | Great Brickhill | Aylesbury
Mursley | Brickhills | Great Brickhill | Aylesbury
Newton Longville | Brickhills | Great Brickhill | Aylesbury
Drayton Parslow | Brickhills | Great Brickhill | Aylesbury
Stoke Hammond | Brickhills | Great Brickhill | Aylesbury
Great Brickhill | Brickhills | Great Brickhill | Aylesbury
Soulbury | Brickhills | Great Brickhill | Aylesbury
Stewkley | Brickhills | Great Brickhill | Aylesbury
Dunton | Brickhills | Great Brickhill | Aylesbury
Hoggeston | Brickhills | Great Brickhill | Aylesbury
Creslow | Brickhills | Great Brickhill | Aylesbury
Cublington | Brickhills | Wing | Aylesbury
Watermead | Brickhills | Wing | Aylesbury
Weedon | Brickhills | Wing | Aylesbury
Aston Abbotts | Brickhills | Wing | Aylesbury
Bierton with Broughton | Brickhills | Aston Clinton & Bierton | Aylesbury
Hulcott | Brickhills | Aston Clinton & Bierton | Aylesbury
Wingrave | Brickhills | Wing | Aylesbury
Rowsham | Brickhills | Wing | Aylesbury
Mentmore | Brickhills | Ivinghoe | Aylesbury
Slapton | Brickhills | Ivinghoe | Aylesbury
Cheddington | Brickhills | Ivinghoe | Aylesbury
Wing | Brickhills | Ivinghoe | Aylesbury
Marsworth | Brickhills | Ivinghoe | Aylesbury
Pitstone | Brickhills | Ivinghoe | Aylesbury
Ivinghoe | Brickhills | Ivinghoe | Aylesbury
Edlesborough | Brickhills | Ivinghoe | Aylesbury
Ludgershall | West Central | Grendon Underwood | Aylesbury
Kingswood | West Central | Grendon Underwood | Aylesbury
Woodham | West Central | Grendon Underwood | Aylesbury
Wotton Underwood | West Central | Grendon Underwood | Aylesbury
Westcott | West Central | Stone & Waddesdon | Aylesbury
Waddesdon | West Central | Stone & Waddesdon | Aylesbury
Cuddington | West Central | Stone & Waddesdon | Aylesbury
Nether Winchendon | West Central | Stone & Waddesdon | Aylesbury
Ashendon | West Central | Stone & Waddesdon | Aylesbury
Upper Winchendon | West Central | Stone & Waddesdon | Aylesbury
Chearsley | West Central | Bernwood | Aylesbury
Long Crendon | West Central | Bernwood | Aylesbury
Chilton | West Central | Grendon Underwood | Aylesbury
Dorton | West Central | Grendon Underwood | Aylesbury
Boarstall | West Central | Grendon Underwood | Aylesbury
Oakley | West Central | Grendon Underwood | Aylesbury
Worminghall | West Central | Bernwood | Aylesbury
Ickford | West Central | Bernwood | Aylesbury
Shabbington | West Central | Bernwood | Aylesbury
Coldharbour | West Central | Aylesbury West | Aylesbury
Haddenham | South Central | Bernwood | Aylesbury
Dinton with Ford and Upton | South Central | Stone & Waddesdon | Aylesbury
Stone Bishopstone & Hartwell | South Central | Stone & Waddesdon | Aylesbury
Kingsey | South Central | Bernwood | Aylesbury
Aston Sandford | South Central | Bernwood | Aylesbury
Stoke Mandeville | South Central | Wendover, Halton & stoke Mandeville | Aylesbury
Weston Turville | South Central | Aston Clinton & Bierton | Aylesbury
Halton | South Central | Aston Clinton & Bierton | Aylesbury
Aston Clinton | South Central | Aston Clinton & Bierton | Aylesbury
Buckland | South Central | Aston Clinton & Bierton | Aylesbury
Drayton Beauchamp | South Central | Aston Clinton & Bierton | Aylesbury
Wendover | South Central | Wendover, Halton & stoke Mandeville | Aylesbury
Little Kimble | South Central | Ridgeway East | Aylesbury
Radnage | North Chiltern | Ridgeway West | High Wycombe
Bledlow cum Saunderton | North Chiltern | Ridgeway West | High Wycombe
Bradenham | North Chiltern | Ridgeway West | High Wycombe
Hughenden | North Chiltern | Ridgeway East | High Wycombe
Downley | North Chiltern | Downley | High Wycombe
West Wycombe | North Chiltern | West Wycombe | High Wycombe
Lacey Green | North Chiltern | Ridgeway West | High Wycombe
Great and Little Hampden | North Chiltern | Ridgeway East | High Wycombe
Ellesborough | North Chiltern | Ridgeway East | High Wycombe
Princes Risborough | North Chiltern | The Risboroughs | High Wycombe
Longwick cum llmer | North Chiltern | The Risboroughs | High Wycombe
Parish Council | North Chiltern |  | High Wycombe
Hazlemere | North Chiltern | Hazlemere | High Wycombe
Hambleden | South & West Chilterns | Chiltern Villages | High Wycombe
Fawley | South & West Chilterns | Chiltern Villages | High Wycombe
Medmenham | South & West Chilterns | Chiltern Villages | High Wycombe
Great Marlow | South & West Chilterns | Chiltern Villages | High Wycombe
Marlow | South & West Chilterns | Marlow | High Wycombe
Marlow Bottom | South & West Chilterns | Chiltern Villages | High Wycombe
Turville | South & West Chilterns | Chiltern Villages | High Wycombe
Ibstone | South & West Chilterns | Chiltern Villages | High Wycombe
Lane End | South & West Chilterns | Chiltern Villages | High Wycombe
Stokenchurch | South & West Chilterns | Ridgeway West | High Wycombe
Piddington and Wheeler End | South & West Chilterns | West Wycombe | High Wycombe
Little Marlow | South & West Chilterns | Flackwell Heath, Little Marlow & Marlow South-East | High Wycombe
Wooburn & Bourne End | South & West Chilterns | The Wooburns, Bourne End & Hedsor | High Wycombe
Hedsor | South & West Chilterns | The Wooburns, Bourne End & Hedsor | High Wycombe
Chepping Wycombe | South & West Chilterns | Tylers Green & Loudwater | High Wycombe
Iver | South Bucks East | Iver | Amersham
Wexham | South Bucks East | Stoke Poges and Wexham | Amersham
Stoke Poges | South Bucks East | Stoke Poges and Wexham | Amersham
Hedgerley | South Bucks East | Gerrards Cross | Amersham
Fulmer | South Bucks East | Denham | Amersham
Denham | South Bucks East | Denham | Amersham
Gerrards Cross | South Bucks East | Gerrards Cross | Amersham
Dorney | South Bucks West | Cliveden | Amersham
Taplow | South Bucks West | Cliveden | Amersham
Burnham | South Bucks West | Farnham Common & Burnham Beech | Amersham
Farnham Royal | South Bucks West | Stoke Poges and Wexham | Amersham
Penn | Amersham West | Penn Wood & Old Amersham | Amersham
Seer Green | Amersham West | Chalfont St Giles | Amersham
Beaconsfield | Amersham West | Beaconsfield | Amersham
Coleshill | Amersham West | Chalfont St Giles | Amersham
Little Missenden | Amersham West | Great Missenden | Amersham
Amersham | Amersham West | Amersham and Chesham Bois | Amersham
Chalfont St Giles | Chalfonts | Chalfont St Giles | Amersham
Chalfont St Peter Parish Council | Chalfonts | Chalfont St Peter | Amersham
Little Chalfont | Chalfonts | Little Chalfont & Amersham Common | Amersham
Chenies | Chalfonts | Chess Valley | Amersham
Chesham Bois | Chesham | Amersham and Chesham Bois | Amersham
Latimer & Ley Hill | Chesham | Chess Valley | Amersham
Chesham | Chesham | Chesham | Amersham
Ashley Green | Chesham | Chesham | Amersham
Chartridge | Chesham | Chiltern Ridges | Amersham
Cholesbury cum St Leonards | Chesham | Chiltern Ridges | Amersham
The Lee | Chesham | Chiltern Ridges | Amersham
Great Missenden | Chesham | Great Missenden | Amersham

## High Speed roads 2025
RURAL GRASS CUTTING DATES FOR DUAL CARIGEWAYS , 2025
1st cut
Date for works | Site Location | PERMIT NO | Works location | Road length | Center reservation
Grass in m2
Tuesday 22nd april | A412 - FIVE POINTS TO SLOUGH |  | center black park to 5 points | 3.2 km | 64000m2
Wednesday 23rd april | A412 - FIVE POINTS TO SLOUGH |  | center slough to black park | 3.2 km
Thursday 24th april | A412 - FIVE POINTS TO SLOUGH |  | lane ones | 3.2 km
Friday 25th april | A412 - M40 TO SOUTHLANDS |  | center and lane ones | 1.2 km | 7200m2
Monday 28th april | A40 - M40 TO TATLINGEND |  | lane ones | 2.8 km | 38000m2
Tuesday 29th april | A40 - M40 TO TATLINGEND |  | centres | 2.8 km
Wednesday 30th april | A413 - CHALFONT ST PETERS TO A40 |  | lane ones | 4.8 km | 38400m2
Thursday 1st may | A413 - CHALFONT ST PETERS TO A40 |  | center viaduct to tatlingend | 4.8 km
Friday 2nd may | A413 - CHALFONT ST PETERS TO A40 |  | center chalfont to viaduct | 4.8 km
Tuesday 6th may | A413 - AMERSHAM SCHOOL LANE |  | centres | 2.4 km | 36000m2
Wednesday 7th may | A413 - AMERSHAM SCHOOL LANE |  | lane ones | 2.4 km
Thursday 8th may | A355 - BEACONSFIELD TO M40 |  | centers and lane ones | 650 m | 5200m2
Friday 9th may | A40 - BEACONSFIELD TO RECYLING |  | centers and lane ones | 750 m | 6750m2
Monday 12th may | A355 - M40 TO SERVICES |  | centers and lane ones | 500 m | 4500m2
Tuesday 13th may | A4155 MARLOW |  | centre and lane ones | 400 m | 4000m2
Wednesday 14th may | A421 -TINGEWICK BYPASS |  | lane ones tingewick to finmere | 3 km | zero
Thursday 15th may | A41 TECHTWICK |  | centre and lane ones | 500 m | 5000m2
Friday 16th may | A41 -ASTON CLINTON BYPASS |  | centre | 4km | 26000m2
Monday 19th may | A41 -ASTON CLINTON BYPASS |  | centre | 4km
Tuesday 20th may | A41 -ASTON CLINTON BYPASS |  | lane one aylesbury to boundary | 4km
Wednesday 21st may | A41 -ASTON CLINTON BYPASS |  | lane one boundary to aylesbury | 4km
2nd Cut
Monday 30th june | A412 - FIVE POINTS TO SLOUGH |  | center black park to 5 points | 3.2 km | 64000m2
Tuesday 1st july | A412 - FIVE POINTS TO SLOUGH |  | center slough to black park | 3.2 km
Wednesday 2nd july | A412 - FIVE POINTS TO SLOUGH |  | lane ones | 3.2 km
Thursday 3rd july | A412 - FIVE POINTS TO SLOUGH |  | lane ones | 3.2 km
Friday 4th july | A412 - M40 TO SOUTHLANDS |  | center and lane ones | 1.2 km | 7200m2
Monday 7th july | A40 - M40 TO TATLINGEND |  | lane ones | 2.8 km | 38000m2
Tuesday 8th july | A40 - M40 TO TATLINGEND |  | lane ones | 2.8 km
Wednesday 9th july | A40 - M40 TO TATLINGEND |  | centres | 2.8 km
Thursday 10th july | A40 - M40 TO TATLINGEND |  | centres | 2.8 km
Friday 11th july | A413 - CHALFONT ST PETERS TO A40 |  | lane ones | 4.8 km | 38400m2
Monday 14th july | A413 - CHALFONT ST PETERS TO A40 |  | center viaduct to tatlingend | 4.8 km
Tuesday 15th july | A413 - CHALFONT ST PETERS TO A40 |  | center chalfont to viaduct | 4.8 km
wednesday 16th july | A413 - CHALFONT ST PETERS TO A40 |  | lane ones | 4.8 km
Thursday 17th july | A413 - AMERSHAM SCHOOL LANE |  | centres | 2.4 km | 36000m2
Friday 18th july | A413 - AMERSHAM SCHOOL LANE |  | lane ones | 2.4 km
Monday 21st july | A355 - BEACONSFIELD TO M40 |  | centers and lane ones | 650 m | 5200m2
Tuesday 22nd july | A40 - BEACONSFIELD TO RECYLING |  | centers and lane ones | 750 m | 6750m2
Wednesday 23rd july | A355 - M40 TO SERVICES |  | centers and lane ones | 500 m | 4500m2
Thursday 24th july | A4155 MARLOW |  | centers and lane ones | 501 m | 4500m3
Friday 25th july | A421 -TINGEWICK BYPASS |  | lane ones | 3 km | zero
Monday 28th july | A421 -TINGEWICK BYPASS |  | lane ones | 3 km | zero
Tuesday 29th july | A41 TECHTWICK |  | centre and lane ones | 499 m | 5000m1
Wednesday 30th july | A41 -ASTON CLINTON BYPASS |  | centre | 4km | 26000m2
Thursday 31st july | A41 -ASTON CLINTON BYPASS |  | centre | 4km
Friday 1st aug | A41 -ASTON CLINTON BYPASS |  | lane one boundary to aylesbury | 4km
Monday 4th aug | A41 -ASTON CLINTON BYPASS |  | lane one aylesbury to boundary | 4km
3rd cut
Monday 15th sept | A412 - FIVE POINTS TO SLOUGH |  | center black park to 5 points | 3.2 km | 64000m2
Tuesday 16th sept | A412 - FIVE POINTS TO SLOUGH |  | center slough to black park | 3.2 km
Wednesday 17th sept | A412 - FIVE POINTS TO SLOUGH |  | lane ones | 3.2 km
Thursday 18th sept | A412 - FIVE POINTS TO SLOUGH |  | lane ones | 3.2 km
Friday 19th sept | A412 - M40 TO SOUTHLANDS |  | center and lane ones | 1.2 km | 7200m2
Monday 22nd sept | A40 - M40 TO TATLINGEND |  | lane ones | 2.8 km | 38000m2
Tuesday 23rd sept | A40 - M40 TO TATLINGEND |  | lane ones | 2.8 km
Wednesday 24th sept | A40 - M40 TO TATLINGEND |  | centres | 2.8 km
Thursday 25th sept | A40 - M40 TO TATLINGEND |  | centres | 2.8 km
Friday 26th sept | A413 - CHALFONT ST PETERS TO A40 |  | lane ones | 4.8 km | 38400m2
Monday 29th sept | A413 - CHALFONT ST PETERS TO A40 |  | center viaduct to tatlingend | 4.8 km
Tuesday 30th sept | A413 - CHALFONT ST PETERS TO A40 |  | center chalfont to viaduct | 4.8 km
Wednesday 1st oct | A413 - CHALFONT ST PETERS TO A40 |  | lane ones | 4.8 km
Thursday 2nd oct | A413 - AMERSHAM SCHOOL LANE |  | centres | 2.4 km | 36000m2
Friday 3rd oct | A413 - AMERSHAM SCHOOL LANE |  | lane ones | 2.4 km
Monday 6th oct | A355 - BEACONSFIELD TO M40 |  | centers and lane ones | 650 m | 5200m2
Tuesday 7th oct | A40 - BEACONSFIELD TO RECYLING |  | centers and lane ones | 750 m | 6750m2
Wednesday 8th oct | A355 - M40 TO SERVICES |  | centers and lane ones | 500 m | 4500m2
Thursday 9th oct | A4155 MARLOW |  | centers and lane ones | 501 m | 4500m3
Friday 10th oct | A421 -TINGEWICK BYPASS |  | lane ones | 3 km | zero
Monday 13th oct | A421 -TINGEWICK BYPASS |  | lane ones | 3 km | zero
Tuesday 14th oct | A41 TECHTWICK |  | centre and lane ones | 499 m | 5000m1
Wednesday 15th oct | A41 -ASTON CLINTON BYPASS |  | centre | 4km | 26000m2
Thursday 16th oct | A41 -ASTON CLINTON BYPASS |  | centre | 4km
Friday 17th oct | A41 -ASTON CLINTON BYPASS |  | lane one boundary to aylesbury | 4km
Monday 20th oct | A41 -ASTON CLINTON BYPASS |  | lane one aylesbury to boundary | 4km